## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Preparation of DPR for augmentation of existing Mahatpur, (Block -Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000147/2021-2022 | 146/AE-I/NACD-II | 16/11/2021 | 26/11/2021 | UMWELT ENGINEER PVT LTD. | 3.79 | 3.79 | 100 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Preparation of DPR for augmentation of existing Mahatpur (Phase-II), (Block -Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000173/2021-2022 | 756/NACD-II | 16/09/2021 | 26/09/2021 | SIRCON ENGINEERING SERVICE | 4.84 | 4.84 | 100 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Relaying of Rising Main by D.I. pipeline replacing the damaged old UPVC Pipe at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division -II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000240/2021-2022 | 97/NACD-II | 10/02/2022 | 27/03/2022 | M/S RAJESH CONSTRUCTION | 13.55 | 13.55 | 99.97 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000207/2021-2022 | 992/NACD-II | 30/12/2021 | 13/02/2022 | SANDIP BISWAS | 97.95 | 97.86 | 99.9 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Installation of Electrical appliances and other allied works under retrofitting of Mahatpur PWSS under Chapra Block. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000204/2021-2022 | 192/AE-I/NACD-II | 29/12/2021 | 18/01/2022 | CHINMOY BISWAS | 4.84 | 4.84 | 100.09 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also construction of steps with earth filling at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000189/2021-2022 | 981/NACD-II | 27/12/2021 | 27/03/2022 | SINGHA ROY & CO. | 145.05 | 144.95 | 99.93 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and Bamboo Pilling at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000032/2021-2022 | 525/NACD-II | 14/06/2021 | 29/07/2021 | NILAY KUMAR BHATTACHARYA | 68.03 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension) at Mahatpur (Vill- Jamnidanga) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000227/2020-2021 | 289/NACD-II | 23/02/2021 | 16/03/2021 | JOY HIND TUBEWELLS | 41.12 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Construction of Boundary wall with Grill Gate at Mahatpur Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000250/2021-2022 | 108/NACD-II | 10/02/2022 | 27/03/2022 | PARTHA DAS | 8.55 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000005/2021-2022 | 990/NACD-II | 28/12/2021 | 28/12/2021 | Resource Division | 93.39 | 0 | 0 | 0
11 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Electrical and Civil works and other allied works under retrofitting of Mahatpur PWSS under Chapra Block | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000198/2021-2022 | 186/AE-I/NACD-II | 29/12/2021 | 18/01/2022 | CHINMOY BISWAS | 4.96 | 4.96 | 100 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Mahatpur water supply scheme (Phase-II) under Chapra Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09687 | Retrofitting | Jungle cutting at Mahatpur,Patharghata,Baliadanga,Helenchi Zone-III,Joyghata and Damodarkhali Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000122/2024-2025 | 820/AE-I/NACD-II | 25/07/2024 | 01/08/2024 | BABA LOKNATH ENTERPRISE | 0.16 | 0.1 | 61.93 | 100
Total | [13 empty] | 486.23 | 274.89 | 56.53