## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Preparation of DPR for augmentation of existing Thanapara, (Block -Karimpur-II) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000151/2021-2022 | 150/AE-I/NACD-II | 16/11/2021 | 26/11/2021 | UMWELT ENGINEER PVT LTD. | 3.88 | 3.88 | 100 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Preparation of DPR for augmentation of existing Thanapara (Phase-II), (Block -Karimpur-II) piped water supply schemes | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000171/2021-2022 | 750/NACD-II | 15/09/2021 | 25/09/2021 | SIRCON ENGINEERING SERVICE | 4.94 | 4.94 | 100 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 4th Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000242/2021-2022 | 99/NACD-II | 10/02/2022 | 27/03/2022 | TAPAN SAHA | 7.74 | 6.6 | 85.28 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000214/2021-2022 | 03/NACD-II | 03/01/2022 | 17/02/2022 | M/S SHILL & CO. | 88.07 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000238/2021-2022 | 902./NACD-II | 22/11/2021 | 06/01/2022 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 73.33 | 73.31 | 99.97 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000272/2021-2022 | 47/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | BISHAL CONSTRUCTION | 4.9 | 4.69 | 95.76 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Sinking of 1 no. 300 mm X 200 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at 4th pump house site with UPVC pipe (CD) & strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000234/2021-2022 | 91/NACD-II | 08/02/2022 | 25/03/2022 | JOY HIND TUBEWELLS | 12.33 | 12.33 | 99.99 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Construction of Boundary wall with Grill Gate at Thanapara Water Supply Scheme 3rd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000273/2021-2022 | 48/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | BIPLAB BHOWMICK | 3.64 | 3.63 | 99.63 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Outstanding as framed by Resource Division for supply of materials for augmentation/retrofitting of Thanapara, Damodarkhali & Madhabpur under Nadia Arsenic Civil Division-II, PHE dte. |  |  | VCH/000718/2021-2022 | 212, 213, 214 | 18/01/2022 | 18/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 124.39 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | SUPPLY OF MATERIALS FOR THANAPARA,DAMODARKHALI,MADHABPUR AND BALIADANGA W/S. SCHEME UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. |  |  | VCH/000646/2021-2022 |  | 07/01/2022 | 07/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
11 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | OUTSTANDING BILL PAYMENT FOR SUPPLY OF MATERIALS FOR THANAPARA, DAMODARKHALI, MADHABPUR, BALIADANGA AS FRAMED BY RESOURCE DIVISION PHE DTE. |  |  | VCH/000643/2021-2022 |  | 05/01/2022 | 05/01/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 143.43 | 0 | 0 | 0
12 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, 10 mm dia gun-Metal ferrule, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair, & also Rising Main replacement by DI pipe) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000036/2021-2022 | 529/NACD-II | 14/06/2021 | 29/07/2021 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 78.79 | 78.72 | 99.91 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Thanapara Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000163/2021-2022 | 166/AE-I/NACD-II | 22/11/2021 | 29/11/2021 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.97 | 4.97 | 100 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair, & also Rising Main replacement by DI pipe) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000226/2021-2022 | 984/NACD-II | 27/12/2021 | 27/03/2022 | MONDAL ENTERPRISE | 149.3 | 0 | 0 | 100
15 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000230/2021-2022 | 01/EE/NACD-II | 03/01/2022 | 17/02/2022 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 95.95 | 0 | 0 | 100
16 | NADIA |  | Nadia Arsenic Civil Division II | Retrofitting of Thanapara water supply scheme (Phase-II) under Karimpur-II Block by providing Functional House Tap Conection under Jal Sapno Mission in Nadia District, under Nadia Arsenic Civil Division-II, P.H.E. Dte | SM/09697 | Retrofitting | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000301/2021-2022 | 03./NACD-II | 03/01/2022 | 17/02/2022 | M/S SHILL & CO. | 88.07 | 0 | 0 | 100
Total | [13 empty] | 1027.16 | 193.07 | 18.8