## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Preparation of DPR for augmentation of existing Bagakhali Zone-I, (Block -Tehatta-I) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000145/2021-2022 | 144/AE-I/NACD-II | 16/11/2021 | 26/11/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 3.11 | 3.11 | 100 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair and also piling work) at Bagakhali Zone-I ( Vill- Chhatina) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000208/2021-2022 | 996/NACD-II | 30/12/2021 | 13/02/2022 | SANJIB DEY | 97.06 | 96.43 | 99.35 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Construction of Boundary wall with Grill Gate at Bagakhali Zone-I 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000259/2021-2022 | 41/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | SHYAM SUNDAR SAHA | 4.08 | 4.05 | 99.29 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Bagakhali Zone-I Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000254/2022-2023 | 1009/NACD-II | 29/11/2022 | 28/01/2023 | DEBASISH DEY | 15.07 | 14.69 | 97.54 | 95
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000230/2021-2022 | 01/EE/NACD-II | 03/01/2022 | 17/02/2022 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 95.95 | 95.91 | 99.96 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I W/s Scheme (Vill- Sahapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000293/2021-2022 | 128/NACD-II | 21/02/2022 | 22/05/2022 | NANDY ENTERPRISES | 102.45 | 99.01 | 96.64 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair ) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000229/2021-2022 | 995/EE/NACD-II | 30/12/2021 | 13/02/2022 | CHANDA CONSTRUCTION | 98.72 | 98.7 | 99.98 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bagakhali Zone-I (vILL- Sahapur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000053/2022-2023 | 223/NACD-II | 05/04/2022 | 04/07/2022 | NANDY ENTERPRISES | 20.12 | 20 | 99.39 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000354/2022-2023 | 207./NACD-II | 07/02/2023 | 08/05/2023 | JOY GOPAL GUPTI | 5.51 | 5.51 | 100 | 95
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Khanjipur & Bagakhali Zone-I, W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000303/2021-2022 | 768./NACD-II | 22/09/2021 | 06/11/2021 | TARUN KUMAR BHATTACHARYA | 84.44 | 40.26 | 47.67 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Continuation Order for Collection of House Hold Details at Prescribed Format through Mobile App / Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte in soft copy for different PWSS under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000038/2023-2024 | 589/NACD-II | 22/05/2023 | 20/08/2023 | JOY GOPAL GUPTI | 5.51 | 5.51 | 100 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bagakhali Zone-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000104/2023-2024 | 1149/NACD-II | 10/10/2023 | 31/10/2023 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000396/2022-2023 | 414/NACD-II | 30/03/2023 | 24/03/2024 | SAJAL SAHA | 4.98 | 3.64 | 73.01 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000397/2022-2023 | 414./NACD-II | 30/03/2023 | 24/03/2024 | SAJAL SAHA | 4.98 | 0.37 | 7.35 | 0
15 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Repair and Renovation work at Bagakhali Zone-I H/W site with Plaster , Concrete and other allied works. Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000028/2024-2025 | 135/AE-II/NACD-II | 11/06/2024 | 11/07/2024 | DEBASISH DEY | 2.79 | 0 | 0 | 0
16 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Repair and Renovation work at Bagakhali Zone-II H/W site with Plaster , Concrete,Earthwork in filling and other allied works under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000049/2024-2025 | 133/AE-II/NACD-II | 11/06/2024 | 11/07/2024 | VAI ENTERPRISE | 4.81 | 0 | 0 | 0
17 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Continuation Work order for Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal. (From 01/04/2024- 30/06/2024) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000002/2024-2025 | 503/NACD-II | 01/04/2024 | 30/06/2024 | SAJAL SAHA | 1.24 | 1.16 | 93.16 | 0
18 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Repair and Renovation work at Bagakhali Zone-I 2nd Pump house site with Reinforced Barbed Tape , Plaster and other allied works. Under Under Nadia Arsenic Division-II, P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000077/2024-2025 | 163/AE-II/NACD-II | 14/06/2024 | 29/06/2024 | UJJWAL ROY | 0.63 | 0 | 0 | 0
19 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bagakhali Zone-I W/S Scheme of Tehatta-I Block Mouza Ramjibanpur & Gopalpur of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000217/2023-2024 | 617/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | MALLICK ENTERPRISE | 0.86 | 0 | 0 | 100
20 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bagakhali Zone-I W/S Scheme of Tehatta-I Block Mouza Bagakhali,Sahapur,Chatiana of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000216/2023-2024 | 616/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | MALLICK ENTERPRISE | 0.93 | 0 | 0 | 100
21 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Collection of Household Details at Prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. in soft copy for Bagakhali Zone-I PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000036/2024-2025 | 747/AE-I/NACD-II | 18/06/2024 | 17/08/2024 | JOY GOPAL GUPTI | 4.84 | 0 | 0 | 98
22 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000062/2024-2025 | 203/AE-II/NACD-II | 01/07/2024 | 26/06/2025 | SAJAL SAHA | 4.98 | 0.4 | 8.03 | 0
23 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bhagakhali Zone-I & Jitpur Water Supply Scheme of capacity 27 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000289/2023-2024 | 196/NACD-II | 12/02/2024 | 12/04/2024 | SANDIP BISWAS | 103.73 | 0 | 0 | 0
24 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Continuation Work Order for Collection of Household Details at Prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. in soft copy for Bagakhali Zone-I PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000199/2024-2025 | 898/AE-I/NACD-II | 09/09/2024 | 08/11/2024 | JOY GOPAL GUPTI | 2.5 | 0 | 0 | 0
25 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAGAKHALI ZONE-I WATER SUPPLY SCHEME IN TEHATTA-I BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09867 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 15/04/2023 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 0 | 0
Total | [13 empty] | 767.01 | 494.64 | 64.49