## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Preparation of DPR for augmentation of existing Bahirgachi Zone-I, (Block - Chapra) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000152/2021-2022 | 151/AE-I/NACD-II | 16/11/2021 | 26/11/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.61 | 2.61 | 100 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Supply of CIDF Sluice valve and DI specials for vavle for facilitate Functional House Hold Connection of Bahirgachhi Zone-I Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000305/2021-2022 | 280/AE-I/NACD-II | 04/03/2022 | 09/03/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.88 | 4.88 | 100 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Bahirgachhi Zone-I ( Vill-Kukra Daha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000215/2022-2023 | 821/NACD-II | 10/11/2022 | 09/01/2023 | ABDUL ALIM MONDAL | 14.27 | 14.23 | 99.77 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Continuation work order for Supply of CIDF Sluice valve and DI specials for vavle for facilitate Functional House Hold Connection of Bahirgachhi Zone-I Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000318/2021-2022 | 302/AE-I/NACD-II | 17/03/2022 | 22/03/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.77 | 4.77 | 100 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Bahirgachhi Zone-I W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000370/2022-2023 | 349/NACD-II | 22/03/2023 | 11/04/2023 | SAMARESH GHOSH | 1.04 | 1.03 | 99.51 | 85
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Bahirgachi Zone-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000095/2023-2024 | 1115/NACD-II | 06/10/2023 | 27/10/2023 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline at BAHIRGACHI ZONE-I ( Vill- BAHIRGACHI AND SURROUNDING AREA) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte |  |  | ORD/000253/2023-2024 | 230/NACD-II | 21/02/2024 | 06/04/2024 | SAFTI PRIVATE LIMITED | 38.98 | 0 | 0 | 0
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Bahirgachi Z-I Water Supply Scheme of capacity 40 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000316/2023-2024 | 207/NACD-II | 15/02/2024 | 15/05/2024 | SATYABRATA CHAKRABORTY | 143.08 | 0 | 0 | 0
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-I W/S Scheme of Chapra Block Mouza Mathurapur & Kukradaha of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000212/2023-2024 | 613/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | MALLICK ENTERPRISE | 0.97 | 0.97 | 100 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Bahirgachi Zone-I W/S Scheme of Chapra Block Mouza Bahirgachi of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000214/2023-2024 | 614/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | P. BISWAS & CO | 0.45 | 0.45 | 100 | 100
11 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to accommodate FHTC under Bahirgachi (Z-I) (Source Augmentation, Mathurapur) PWSS under Block_ Chapra Dist. - Nadia under EMD, PHE Dte. SM/09868 | Assistant Engineer |  | ORD/000027/2025-2026 | 697/EMD | 04/04/2025 | 04/05/2025 | M/S. MANDAL ENTERPRISE | 10.55 | 0 | 0 | 0
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Improvement of connecting road within Ichapur Road and the Head Works site of Madhabpur and Bahirgachhi Zone-I Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000004/2025-2026 | 17/AE-I/NACD-II | 11/04/2025 | 10/06/2025 | GHOSH ENTERPRISE | 4.84 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BAHIRGACHHI ZONE-I WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09868 | Augmentation | Comprehensive augmentation in technical regards including aquifer management with extraction, compliance of Ground water contamination removal as per IS 10500 with subsequent amendments and composite RCC Cum masonry structures at Mouza- Mathurapur (under Bahirgachi zone I Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000450/2024-2025 | 330/NACD-II | 11/03/2025 | 10/05/2025 | TARUN GHOSH | 54.03 | 0 | 0 | 0
Total | [13 empty] | 286.37 | 34.85 | 12.17