## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Preparation of DPR for augmentation of existing Baranaldaha, (Block -Tehatta-II) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000148/2021-2022 | 147/AE-I/NACD-II | 16/11/2021 | 26/11/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.87 | 2.87 | 100 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baranaldaha (Vill- Kolony para) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000227/2021-2022 | 890/NACD-II | 16/11/2021 | 31/12/2021 | M/S ANUBHAB CONSTRUCTION | 52.36 | 52.2 | 99.71 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Repairing of Distribution system of UPVC pipes, bamboo pilling & earth filling at Pashimpara under Baranaldaha Ground water based PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000398/2021-2022 | 32 /AE-I/NACD-II | 24/06/2021 | 04/07/2021 | TAPAN SAHA | 2.08 | 2.08 | 99.98 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Construction of Boundary wall with Grill Gate at Bara Naldaha Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000281/2021-2022 | 236/AE-I/NACD-II | 17/02/2022 | 17/02/2023 | BIPLAB GUHA | 4.84 | 4.83 | 99.79 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) and also Bamboo Pilling at Baranaldaha (Vill- Choto Naldaha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000143/2021-2022 | 825/NACD-II | 25/10/2021 | 09/12/2021 | M/S ANUBHAB CONSTRUCTION | 60.17 | 60.14 | 99.94 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Damaged pipe line repair due to construction of drain at Baranaldaha W/s Scheme (Vill- Baranaldaha) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000185/2022-2023 | 600/NACD-II | 01/09/2022 | 01/10/2022 | TAPAN SAHA | 9.7 | 9.62 | 99.23 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Baranaldaha) |  |  | ORD/000162/2023-2024 | 1285/NACD-II | 21/11/2023 | 12/12/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Baranaldah Water Supply Scheme of capacity 67 Cu.m/hr in Tehatta-II Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000324/2023-2024 | 206/NACD-II | 15/02/2024 | 15/05/2024 | RITE WATER SOLUTION (INDIA) PRIVATE LIMITED | 176.73 | 0 | 0 | 0
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Bara Naldaha ( Vill- Colonypara, Baranaldaha) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000017/2023-2024 | 547/NACD-II | 11/05/2023 | 10/07/2023 | SUBHASIS MOJUMDER | 37.82 | 13.09 | 34.6 | 60
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Barbed wire fencing & painting of Headwork site and 2nd T/W site Boundary wall of Baranaldaha PWSS at Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000033/2024-2025 | 744/AE-I/NACD-II | 18/06/2024 | 18/07/2024 | A.S.CONSTRUCTION | 4.25 | 0 | 0 | 0
11 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Renovation of Head Work site and 2nd T/W site of Baranaldaha PWSS at Tehatta-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000034/2024-2025 | 745/AE-I/NACD-II | 18/06/2024 | 18/07/2024 | TAPAN SAHA | 4.69 | 0 | 0 | 0
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Bara Naldaha Piped Water Supply Scheme in Tehatta-II Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000388/2023-2024 | 145/NACD-II | 06/02/2024 | 22/03/2024 | M/S S. K. ENTERPRISE | 28.62 | 18.59 | 64.96 | 100
13 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 15/04/2023 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 0 | 0
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BARA NALDAHA WATER SUPPLY SCHEME IN TEHATTA-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09869 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS,Total station,DGPS, Auto levels etc over the command area of Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Baranaldaha W/S Scheme in Tehatta-II Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000213/2023-2024 | 611/AE-I/NACD-II | 02/02/2024 | 17/02/2024 | ECOCARE | 0.92 | 0 | 0 | 100
Total | [13 empty] | 481.65 | 168.2 | 34.92