## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Preparation of DPR for augmentation of existing Helenchi Zone-I, (Block-Krishnaganj) piped water supply schemes | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000154/2021-2022 | 153/AE-I/NACD-II | 16/11/2021 | 26/11/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD | 2.91 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Construction of Boundary wall with Grill Gate at Helenchi ZoneI Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000251/2021-2022 | 105/NACD-II | 10/02/2022 | 27/03/2022 | NISHITH BANERJEE | 8.61 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I, (Vill- Sibnibash) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000233/2021-2022 | 64/NACD-II | 25/01/2022 | 11/03/2022 | JOY GOPAL GUPTI | 21.43 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Construction of Boundary wall with Grill Gate at Helenchi Zone-III Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000261/2021-2022 | 43/AE-II/NACD-II | 17/02/2022 | 19/03/2022 | SUMIT GHOSH | 4.29 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I, (Vill- Sibnibash) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000206/2021-2022 | 991/NACD-II | 30/12/2021 | 13/02/2022 | JOY GOPAL GUPTI | 95.14 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Helenchi Zone-I W/s Scheme (Vill- Krishnapur) in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000277/2021-2022 | 125/NACD-II | 21/02/2022 | 22/05/2022 | A.P. POWER & CONCRETE | 105.67 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Construction of boundary wall with grill gate and barbed wire fencing at Helenchi Zone-I water supply scheme Head work site under Nadia Arsenic Civil Division-II, PHE Dte, Nadia District. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000261/2022-2023 | 1016/NACD-II | 29/11/2022 | 28/01/2023 | SANJIB BISWAS | 18.63 | 0 | 0 | 95
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Construction of Approach Road with land Development at Helenchi Zone-I Water Supply Scheme 2nd Pump House site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000130/2022-2023 | 66/AE-II/NACD-II | 28/06/2022 | 28/07/2022 | NISHITH BANERJEE | 2.35 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Functional House Hold Tap Connection for left out Household regarding Har Ghar Jal Certification including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Vill- Par Chandan Nagar, Shibnibas, Pabakhali) Helenchi Zone-I W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000348/2022-2023 | 148/NACD-II | 17/01/2023 | 06/02/2023 | A.K ADHIKARY | 5.95 | 0 | 0 | 100
10 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under HELENCHI (Z-I, Z-II, Z-III) (Block- Krishnaganj ) AND BANSBERIA,CHANDPUR & DAMODARKHALI (Block- Krishnagar I) W/S Scheme, , Dist. - Nadia. NIET NO.- 31 of EE/EMD of 2022-23 (Sl. No.- 02) |  |  | ORD/001771/2022-2023 | 1121/EMD | 16/03/2023 | 15/04/2023 | M.S. ENTERPRISE | 65.68 | 0 | 0 | 90
11 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Shifting of S/S Structure at Sbibniwas under KNJCCC at PH-II Z-I under Helenchi W/S Scheme. |  |  | BILL/01881/2023-2024 |  | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.96 | 0 | 0 | 0
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Shifting of S/S structure at Sbibniwas under KNJ CCC related to Helenchi Zone -I PH-2 |  |  | BILL/00350/2023-2024 | 164 | 14/09/2023 | 14/09/2023 | WEST BENGAL STATE ELECTRICTY DISTRIBUTION COMPANY LTD. | 0.96 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Providing Functional House Hold Tap Connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete (Remaining School Only) at Helenchi Zone-I W/s Scheme at Krishnaganj Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000297/2022-2023 | 1195/NACD-II | 23/12/2022 | 07/01/2023 | DYNAMIC CONSTRUCTION | 1.05 | 0 | 0 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at Helenchi Zone-I Water Supply Scheme for Swajal gram certification under Krishnaganj Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000242/2023-2024 | 18/AE-II/NACD-II | 15/02/2024 | 01/03/2024 | M/S SHILL & CO. | 0.97 | 0 | 0 | 100
15 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Chakdignagar ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No. 7) | Assistant Engineer | Junior Engineer | ORD/003198/2023-2024 | 948/EMD | 18/03/2024 | 02/05/2025 | KARTICK BAL | 22.35 | 0 | 0 | 90
16 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Laying of Distribution System including providing FHTC at left out households and repairing of damaged Pipeline for Helenchi Zone-I W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000110/2025-2026 | 940/NACD-II | 28/07/2025 | 26/09/2025 | SANJOY BAKSHI | 22.92 | 0 | 0 | 0
17 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR HELENCHI ZONE-I WATER SUPPLY SCHEME IN KRISHNAGANJ BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/09871 | Augmentation | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Helanchi zone-I PWSS in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000307/2024-2025 | 359/AE-II/NACD-II | 19/11/2024 | 26/11/2024 | MAKALI ENGINEERING CORPORATION | 0.95 | 0 | 0 | 100
Total | [13 empty] | 380.83 | 0 | 0