## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130518, 19336130521, 19336130107, 19336131005 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000098/2022-2023 | 46 /AE-II/ NACD-II | 10/06/2022 | 25/07/2022 | TAPAS GHOSH | 4.57 | 0 | 0 | 0
2 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040322, 19336040321, 19336040319, 19336040311 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000083/2022-2023 | 90/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | PARTHA DAS | 4.47 | 0 | 0 | 0
3 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310701, 19336310721, 19336310702, 19336310715 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000101/2022-2023 | 74/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | GHOSH ENTERPRISE | 4.58 | 0 | 0 | 0
4 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310704, 19336310707, 19336310710 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000103/2022-2023 | 76/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | NAMDAR ALI | 3.43 | 0 | 0 | 0
5 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KARIMPUR-II BLOCK from existing piped water supply scheme. AWC Code : 19336320323, 19336320406, 19336320402, 19336320313" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000106/2022-2023 | 79/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | SOURAV & CO. | 4.26 | 0 | 0 | 0
6 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336030918 19336030917, 19336030916, 19336030704 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000088/2022-2023 | 94/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | SANDIP ROY | 4.47 | 0 | 0 | 0
7 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336300111, 19336300214, 19336300208" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000110/2022-2023 | 83/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | CHINMOY BISWAS | 3.43 | 0 | 0 | 0
8 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336290102, 19336300107,19336300115" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000109/2022-2023 | 82/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | M/S RAJESH CONSTRUCTION | 3.43 | 0 | 0 | 90
9 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336300117, 19336290513, 19336290501, 19336300405" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000112/2022-2023 | 85/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | M/S TARUN GHOSH & CO. | 4.58 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KALIGANJ BLOCK from existing piped water supply scheme. (Phase_I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000290/2022-2023 | 1174/NACD-II | 22/12/2022 | 22/03/2023 | M. H. SUPPLIERS | 17.92 | 0 | 0 | 0
11 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under SANTIPUR BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000227/2022-2023 | 868/NACD-II | 17/11/2022 | 16/01/2023 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 25.78 | 0 | 0 | 0
12 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Karimpur-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000230/2022-2023 | 871/NACD-II | 17/11/2022 | 15/02/2023 | SUMIT GHOSH | 66.98 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336300203, 19336300205, 19336300501" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000111/2022-2023 | 84/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | SANJIT DAS | 3.43 | 0 | 0 | 0
14 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040312, 19336040325, 19336040324, 19336040512 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000082/2022-2023 | 89/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | JAYBRATO HALDER | 4.47 | 0 | 0 | 0
15 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130306, 19336130320, 19336130617, 19336130619 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000096/2022-2023 | 44 /AE-II/ NACD-II | 10/06/2022 | 25/07/2022 | AMIT KARMAKAR | 4.57 | 0 | 0 | 0
16 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040904, 19336040918, 19336040907, 19336040909 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000076/2022-2023 | 83/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | S.B. CONSTRUCTION | 4.47 | 0 | 0 | 0
17 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040711 19336030219, 19336030224, 19336030225, | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000086/2022-2023 | 92/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | SHOVON KUMAR MODAK | 4.47 | 0 | 0 | 0
18 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040104, 19336040103, 19336040106, 19336040101 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000080/2022-2023 | 87/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | GHOSH ENTERPRISE | 4.47 | 0 | 0 | 0
19 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040308, 19336040310, 19336040313, 19336040314 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000081/2022-2023 | 88/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | TAPAN SAHA | 4.47 | 0 | 0 | 0
20 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040701 19336040703, 19336040705, 19336040709 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000087/2022-2023 | 93/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | DEBASISH DEY | 4.47 | 0 | 0 | 0
21 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336030709 19336030707, 19336030607, 19336030610 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000090/2022-2023 | 96/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | BISHAL CONSTRUCTION | 4.47 | 0 | 0 | 0
22 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336030223, 19336030218, 19336030220, 19336040306, | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000084/2022-2023 | 91/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | PRADIP KUMAR BANIK | 4.46 | 0 | 0 | 0
23 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040824, 19336040902, 19336040901, 19336040903 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000075/2022-2023 | 82/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | ARIT KUMAR PAL | 4.47 | 0 | 0 | 0
24 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040211, 19336040209, 19336040213, 19336040210 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000077/2022-2023 | 84/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | M/S TARUN GHOSH & CO. | 4.47 | 0 | 0 | 0
25 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040517, 19336040514, 19336040510, 19336040508 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000078/2022-2023 | 85/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | M/S FREEDOM CONSTRUCTION | 4.47 | 0 | 0 | 0
26 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040117, 19336040120, 19336040118, 19336040119 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000079/2022-2023 | 86/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | SUMIT GHOSH | 4.47 | 0 | 0 | 0
27 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130912, 19336130901, 19336130312, 19336130318 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000095/2022-2023 | 43 /AE-II/ NACD-II | 10/06/2022 | 25/07/2022 | SHYAM SUNDAR SAHA | 4.57 | 0 | 0 | 0
28 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130609, 19336130607, 19336130605, 19336130625 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000097/2022-2023 | 45 /AE-II/ NACD-II | 10/06/2022 | 25/07/2022 | SUBHASIS MOJUMDER | 4.57 | 0 | 0 | 0
29 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336131014, 19336131003, 19336131107, 19336131110 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000099/2022-2023 | 47 /AE-II/ NACD-II | 10/06/2022 | 25/07/2022 | R.M. TRADING | 4.57 | 0 | 0 | 0
30 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310102, 19336310414, 19336310402, 19336310407 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000102/2022-2023 | 75/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | SANJIB BISWAS | 4.58 | 0 | 0 | 0
31 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310620, 19336310708, 19336310711 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000104/2022-2023 | 77/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | M/S SREE KRISHNA ENTERPRISE. | 3.43 | 0 | 0 | 0
32 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336040805 19336030713, 19336030711, 19336030613 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000091/2022-2023 | 97/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | SHYAMAL KANTI GHOSH | 4.47 | 0 | 0 | 0
33 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. AWC Code : 19336290502, 19336300708, 19336300524, 19336300508" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000113/2022-2023 | 86/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | M/S FREEDOM CONSTRUCTION | 4.58 | 0 | 0 | 0
34 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGAR-I BLOCK from existing piped water supply scheme. AWC Code: 19336150206, 19336150211, 19336150107, 19336150504 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000139/2022-2023 | 135/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | M/S S.K. CONSTRUCTION | 4.57 | 0 | 0 | 0
35 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336131111, 19336130124, 19336130220, 19336130222" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000114/2022-2023 | 87/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | ST. ANTHONY ENTERPRISE | 4.57 | 0 | 0 | 0
36 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KARIMPUR-II BLOCK from existing piped water supply scheme. AWC Code : 19336320503, 19336320411, 19336320414, 19336320508" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000107/2022-2023 | 80/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | SHYAM SUNDAR SAHA | 4.26 | 0 | 0 | 0
37 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under TEHATTA-II BLOCK from existing piped water supply scheme. AWC Code : 19336310403, 19336310705, 19336310401" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000105/2022-2023 | 78/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | BISHAL CONSTRUCTION | 3.43 | 0 | 0 | 0
38 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under CHAKDAH BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000219/2022-2023 | 860/NACD-II | 17/11/2022 | 16/01/2023 | M/S FREEDOM CONSTRUCTION | 42.41 | 0 | 0 | 100
39 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Tehatta-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000234/2022-2023 | 875/NACD-II | 17/11/2022 | 16/01/2023 | ABDUL ALIM MONDAL | 10.94 | 0 | 0 | 0
40 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Krishnaganj Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000232/2022-2023 | 873/NACD-II | 17/11/2022 | 16/01/2023 | MALI CONSTRUCTION | 25.34 | 0 | 0 | 100
41 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Tehatta-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000235/2022-2023 | 876/NACD-II | 17/11/2022 | 16/01/2023 | TRISHA ENTERPRISE AND CO. | 20.91 | 0 | 0 | 0
42 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Center under Chapra Block from existing piped water supply Scheme. AWC Code : 19336030811 19336030806, 19336030915, 19336030919 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000089/2022-2023 | 95/AE-I/NACD-II | 10/06/2022 | 25/07/2022 | SURAJIT KUMAR GHOSH | 4.47 | 0 | 0 | 0
43 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130723, 19336130907, 19336130908, 19336130909 | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000094/2022-2023 | 42/AE-II/ NACD-II | 10/06/2022 | 25/07/2022 | BIPLAB BHOWMICK | 4.57 | 0 | 0 | 100
44 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KARIMPUR-II BLOCK from existing piped water supply scheme. AWC Code : 19336320317, 19336320413, 19336320422" | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer RWS | ORD/000108/2022-2023 | 81/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | BIPLAB BHOWMICK | 3.2 | 0 | 0 | 90
45 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under NABADWIP BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000224/2022-2023 | 865/NACD-II | 17/11/2022 | 16/01/2023 | TAPAS GHOSH | 34.99 | 0 | 0 | 100
46 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KRISHNAGAR-II BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000223/2022-2023 | 864/NACD-II | 17/11/2022 | 15/02/2023 | SANDIP BISWAS | 63.77 | 0 | 0 | 100
47 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Chapra Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000220/2022-2023 | 861/NACD-II | 17/11/2022 | 16/01/2023 | BIPLAB GUHA | 49.24 | 0 | 0 | 85
48 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers underKrishnagar-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000222/2022-2023 | 863/NACD-II | 17/11/2022 | 15/02/2023 | TARUN GHOSH | 53.5 | 0 | 0 | 100
49 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Karimpur-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000231/2022-2023 | 872/NACD-II | 17/11/2022 | 16/01/2023 | SOUMYADIP MISRA | 49.95 | 0 | 0 | 100
50 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under KALIGANJ BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000229/2022-2023 | 870/NACD-II | 17/11/2022 | 15/02/2023 | BIDYUT KUMAR | 89.27 | 0 | 0 | 50
51 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Nakashipara Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000233/2022-2023 | 874/NACD-II | 17/11/2022 | 15/02/2023 | JOY GOPAL GUPTI | 71.15 | 0 | 0 | 64
52 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under Hanskhali BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000228/2022-2023 | 869/NACD-II | 17/11/2022 | 15/02/2023 | SHYAMAL SHIL | 91.75 | 0 | 0 | 70
53 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under Hanskhali BLOCK from existing piped water supply scheme. (Phase_I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000289/2022-2023 | 1173/NACD-II | 22/12/2022 | 22/03/2023 | CHOWDHURY CONSTRUCTION | 44.56 | 0 | 0 | 100
54 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under RANAGHAT-I BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000225/2022-2023 | 866/NACD-II | 17/11/2022 | 30/01/2026 | M/S GHOSH CONSTRUCTION | 92.58 | 0 | 0 | 90
55 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under RANAGHAT-II BLOCK from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000226/2022-2023 | 867/NACD-II | 17/11/2022 | 01/11/2025 | M/S SUKANTA ENTERPRISE | 75.76 | 0 | 0 | 60
56 | NADIA |  | Nadia Arsenic Civil Division II | Providing water supply facility through existing PWSS to Anganwadi Centers in Nadia District (Phase-I). (1333 Nos.) | SM/09876 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Haringhata Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-I) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000221/2022-2023 | 862/NACD-II | 17/11/2022 | 06/02/2025 | CHANDAN ROY | 68.15 | 0 | 0 | 92
Total | [13 empty] | 1153.71 | 0 | 0