## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Dhopahat water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000003/2022-2023 | 212/NACD-II | 05/04/2022 | 04/06/2022 | NAMDAR ALI | 5.37 | 5.36 | 99.87 | 100
2 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Dhopahat and adjoining mouzas under Dhopahat Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000057/2022-2023 | 288/NACD-II | 12/05/2022 | 10/08/2022 | SINGHA ROY & CO. | 253.93 | 213.88 | 84.23 | 85
3 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Dhopahat and Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000017/2022-2023 | 242/NACD-II | 19/04/2022 | 18/06/2022 | AUXILIARY TUBE WELL DRILLERS | 43.18 | 29.26 | 67.77 | 100
4 | NADIA | Tehatta-I | Eastern Mechanical | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Dhopahat Piped Water SupplyScheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 16) |  |  | ORD/000420/2022-2023 | 6253/EMD | 19/11/2022 | 19/12/2022 | S.G. ENTERPRISE | 40.81 | 0 | 0 | 0
5 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Laying of Rising Main of Dhopahat Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. (Sl. No. 01) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000015/2022-2023 | 220/NACD-II | 05/04/2022 | 05/05/2022 | GOUTAM HALDER | 5.37 | 5.33 | 99.25 | 100
6 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Earth work in filling in ditches at Dhopahat 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000128/2022-2023 | 64/AE-II/NACD-II | 28/06/2022 | 18/07/2022 | GHOSH ENTERPRISE | 3.2 | 3.2 | 99.84 | 100
7 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Dhopahat water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000050/2022-2023 | 17/AE-II/NACD-II | 11/04/2022 | 10/06/2022 | NAMDAR ALI | 2.83 | 2.81 | 99.31 | 100
8 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of Boundary wall with Grill Gate at Dhopahat Water Supply Scheme H/W site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000180/2022-2023 | 522/NACD-II | 05/08/2022 | 04/10/2022 | CHANDAN ROY | 27.92 | 19.01 | 68.11 | 85
9 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Dhopahat Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000203/2022-2023 | 632/NACD-II | 06/09/2022 | 26/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.84 | 4.84 | 100 | 100
10 | NADIA | Tehatta-I | Eastern Mechanical | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Dhopahat W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 02) | Assistant Engineer | Junior Engineer | ORD/000455/2022-2023 | 6263/EMD | 19/11/2022 | 01/04/2025 | BARISAL TRADING CO. | 9.88 | 8.89 | 89.89 | 10
11 | NADIA | Tehatta-I | Eastern Mechanical | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Dhopahat W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.-01) | Assistant Engineer | Junior Engineer | ORD/000519/2022-2023 | 6369/EMD | 23/11/2022 | 23/12/2022 | ABHISEK ENGINEERING CONCERN | 10 | 9.89 | 98.94 | 80
12 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 398/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 47.43 | 0 | 0 | 0
13 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000244/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
14 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000350/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
15 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Additional Earth work in filling in ditches at Dhopahat 2nd Tube Well Site for development of land in connection by hand roller in connection with proposed T/W Sinking & Pump House construction at Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000367/2022-2023 | 284./NACD-II | 01/03/2023 | 21/03/2023 | M/S SHAIKH ENTERPRISE | 2.45 | 2.45 | 99.89 | 100
16 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Dhopahat water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000374/2022-2023 | 360/NACD-II | 22/03/2023 | 22/03/2026 | SINGHA ROY & CO. | 143.35 | 68.84 | 48.02 | 27
17 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Dhopahat 2nd Tubwell Site within Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000329/2022-2023 | 122/NACD-II | 11/01/2023 | 12/03/2023 | BASUDEB SAHA | 6.57 | 6.49 | 98.8 | 85
18 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Dhopahat) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000057/2023-2024 | 869/NACD-II | 10/08/2023 | 31/08/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
19 | NADIA | Tehatta-I | Eastern Mechanical | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Electricity bill for new service connection at Dhopotto-I |  |  | BILL/02145/2022-2023 | 142/PFMS/EMD | 10/03/2023 | 10/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.47 | 0 | 0 | 0
20 | NADIA | Tehatta-I | Eastern Mechanical | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Electricity bill for new service connection at dhopahat-II W/S Scheme |  |  | BILL/02146/2022-2023 | 143/PFMS/EMD | 10/03/2023 | 10/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.48 | 0 | 0 | 0
21 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of 87 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Matiary Water Supply Scheme in Krishnaganj block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000217/2024-2025 | 1311/NACD-II | 20/09/2024 | 19/03/2025 | JOY HIND TUBEWELLS | 232.26 | 0 | 0 | 0
22 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000346/2024-2025 | 1627/NACD-II | 19/12/2024 | 12/06/2026 | M.R. CONSTRUCTION | 117.87 | 0 | 0 | 40
23 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 50 cum/Hour capacity for Dhopahat Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000223/2024-2025 | 1312/NACD-II | 20/09/2024 | 15/09/2025 | JOY HIND TUBEWELLS | 181.56 | 0 | 0 | 0
24 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement at Thanapara Zone-II Tube Well No-2 area according to departmental drawing (Size 3.60 mtr x 3.00 mtr ) under Thanapara Zone-II & Dhopahat Piped water supply scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000225/2024-2025 | 311AE-II/NACD-II | 06/09/2024 | 21/10/2024 | JEET ENTERPRISE | 4.18 | 0 | 0 | 100
25 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 16/09/2025 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
26 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of Pump House cum Chlorine room with sanitary arrangement at Thanarpara Zone-II Headwork site according to departmental drawing at Thanarpara Zone-II & Dhopahat Piped Water Supply Scheme under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000465/2024-2025 | 403_NACD-II | 26/03/2025 | 23/08/2025 | ROY CONSTRUCTION | 6.14 | 0 | 0 | 100
27 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | Dhopahat Piped Water Supply Scheme | SM/09942 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III Water Supply Scheme 2nd Tube Well site & Dhopahat Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000392/2024-2025 | 134/NACD-II | 29/01/2025 | 28/02/2025 | VAI ENTERPRISE | 5.99 | 0 | 0 | 100
Total | [13 empty] | 1365.32 | 385.04 | 28.2