## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030213, 19336030214, 19336030516, 19336030206, 19336030212" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000153/2022-2023 | 149/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | PRABIR KUMAR ROY | 4.87 | 4.34 | 89.11 | 0
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Nabadwip Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000240/2022-2023 | 945/NACD-II | 21/11/2022 | 20/01/2023 | ROY CONSTRUCTION | 28.22 | 23.68 | 83.91 | 0
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Tehatta-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II (HQ), Nadia Arsenic Civil Divisi,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000250/2022-2023 | 955/NACD-II | 21/11/2022 | 29/04/2025 | SOMNATH CHATTERJEE | 70.82 | 56.96 | 80.43 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Haringhata Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000237/2022-2023 | 942/NACD-II | 21/11/2022 | 20/01/2023 | SUMAN CHAKRABORTY | 49.18 | 24.18 | 49.16 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under Ranaghat_II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II PHE Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000242/2022-2023 | 947/NACD-II | 21/11/2022 | 05/11/2025 | ASIT PRAMANIK | 72.07 | 70.96 | 98.47 | 95
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Santipur Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000243/2022-2023 | 948/NACD-II | 21/11/2022 | 19/02/2023 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 65 | 56.35 | 86.7 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Ranaghat-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000241/2022-2023 | 946/NACD-II | 21/11/2022 | 20/01/2023 | INVENT ENGINEER'S COOP SOCIETY LTD. | 35.73 | 31.22 | 87.38 | 75
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030403, 19336030401, 19336030323, 19336040603, 19336040605" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000148/2022-2023 | 144/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | SHOVON KUMAR MODAK | 4.86 | 3.22 | 66.24 | 0
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040822, 19336030612, 19336030616, 19336030712, 19336030624" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000143/2022-2023 | 139/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | M/S TARUN GHOSH & CO. | 4.87 | 4.51 | 92.8 | 0
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030722, 19336030804, 19336030816, 19336030818, 19336030913" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000146/2022-2023 | 142/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | VAI ENTERPRISE | 4.86 | 2.46 | 50.56 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030209, 19336030204, 19336030226, 19336030221, 19336030215" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000152/2022-2023 | 148/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | ARIT KUMAR PAL | 4.87 | 4.45 | 91.4 | 0
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030217, 19336030518, 19336030210, 19336030203, 19336030211" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000154/2022-2023 | 150/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | TAPAN SAHA | 4.86 | 4.81 | 98.86 | 0
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030208, 19336030222, 19336030216, 19336040216, 19336040316" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000155/2022-2023 | 151/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | MUKHERJEE CONSTRUCTION | 4.86 | 3.48 | 71.48 | 0
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040302, 19336040301, 19336040218, 19336040320, 19336040513" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000156/2022-2023 | 152/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | BABLU MALLICK | 4.87 | 3.65 | 74.99 | 0
15 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040215, 19336040220, 19336040303, 19336040304, 19336040307" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000157/2022-2023 | 153/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | SAMAR ENTERPRISE | 4.86 | 3.82 | 78.51 | 0
16 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040422, 19336040414, 19336040415, 19336040406, 19336040403" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000162/2022-2023 | 159/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | BINOY DAS | 4.87 | 3.8 | 78.15 | 0
17 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040401, 19336040419, 19336040404, 19336040402, 19336040416" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000163/2022-2023 | 160/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | M/S SREE KRISHNA ENTERPRISE. | 4.86 | 3.57 | 73.4 | 0
18 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130706, 19336130709, 19336130710, 19336130717, 19336130802" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000170/2022-2023 | 92/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | SREE GURU ENTERPRISE | 4.94 | 3.57 | 72.25 | 0
19 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130822, 19336130902, 19336130903, 19336130905, 19336130913" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000171/2022-2023 | 93/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | ROY CONSTRUCTION | 4.94 | 3.64 | 73.71 | 0
20 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130922, 19336131023, 19336131102, 19336131008" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000172/2022-2023 | 94/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | AMIT KARMAKAR | 3.95 | 3.57 | 90.33 | 0
21 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040804, 19336040808, 19336040806, 19336040807, 19336040819" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000141/2022-2023 | 137/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | TAPAS GHOSH | 4.87 | 3.64 | 74.83 | 0
22 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040821, 19336040823, 19336040820, 19336040803, 19336040813" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000142/2022-2023 | 138/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | SUMIT GHOSH | 4.87 | 4.62 | 94.87 | 0
23 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030119, 19336030109, 19336030104, 19336030307, 19336030308" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000147/2022-2023 | 143/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | GHOSH & CO. | 4.86 | 4.06 | 83.41 | 0
24 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040608, 19336040712, 19336040713, 19336040708, 19336040706" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000149/2022-2023 | 145/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | DEBASISH DEY | 4.87 | 3.77 | 77.4 | 0
25 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040604, 19336040707, 19336040607, 19336030205, 19336030207" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000151/2022-2023 | 147/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | M/S FREEDOM CONSTRUCTION | 4.87 | 4.85 | 99.78 | 0
26 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040919, 19336040920, 19336040908, 19336040916, 19336040420" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000161/2022-2023 | 158/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | M/S. ASIT KUMAR BISWAS | 4.87 | 3.93 | 80.7 | 0
27 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040421, 19336040516, 19336040408, 19336040405" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000164/2022-2023 | 161/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | PARTHA DAS | 3.89 | 3.58 | 92.02 | 0
28 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030710, 19336030622, 19336030617, 19336030723, 19336030716" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000144/2022-2023 | 140/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | SURAJIT KUMAR GHOSH | 4.87 | 3.09 | 63.55 | 0
29 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040609, 19336040617, 19336040610, 19336040606, 19336040710" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000150/2022-2023 | 146/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | DEBARSHI BANERJEE | 4.86 | 4.72 | 97.12 | 0
30 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130223, 19336130301, 19336130302, 19336130303, 19336130304" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000166/2022-2023 | 88/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | S.B. CONSTRUCTION | 4.94 | 4.03 | 81.43 | 0
31 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030504, 19336030503, 19336030513, 19336030501, 19336030502" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000140/2022-2023 | 136/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | SHYAMAL KANTI GHOSH | 4.87 | 3.78 | 77.69 | 0
32 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under TEHATTA-I BLOCK from existing piped water supply scheme. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000292/2022-2023 | 1176/NACD-II | 22/12/2022 | 08/08/2025 | M/S K.P. CONSTRUCTION | 44.29 | 37.69 | 85.1 | 55
33 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwadi Centres under Hanskhali BLOCK from existing piped water supply scheme. (Phase_II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000291/2022-2023 | 1175/NACD-II | 22/12/2022 | 22/03/2023 | NATIONAL CONSTRUCTION | 19.31 | 13.28 | 68.74 | 80
34 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Karimpur-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000247/2022-2023 | 952/NACD-II | 21/11/2022 | 19/02/2023 | CHAKRABORTTI ENTERPRISE | 56.82 | 49.34 | 86.83 | 90
35 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Tehatta-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000249/2022-2023 | 954/NACD-II | 21/11/2022 | 17/02/2025 | J.D. CONSTRUCTION | 93.05 | 75.07 | 80.68 | 95
36 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Krishnagar-II Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000239/2022-2023 | 944/NACD-II | 21/11/2022 | 20/01/2023 | R.M. TRADING | 22.31 | 21.02 | 94.22 | 75
37 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Kaliganj Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000245/2022-2023 | 950/NACD-II | 21/11/2022 | 19/02/2023 | DEBASIS SAMADDAR | 87.28 | 86.93 | 99.61 | 100
38 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Karimpur-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000246/2022-2023 | 951/NACD-II | 21/11/2022 | 19/02/2023 | SANJIB DEY | 85.41 | 78.84 | 92.31 | 85
39 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Hanskhali Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000244/2022-2023 | 949/NACD-II | 21/11/2022 | 19/02/2023 | A.P. POWER & CONCRETE | 91.66 | 85.42 | 93.19 | 90
40 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Nakashipara Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000248/2022-2023 | 953/NACD-II | 21/11/2022 | 19/02/2023 | NILAY KUMAR BHATTACHARYA | 87.34 | 87.15 | 99.78 | 100
41 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040110, 19336040202, 19336040204, 19336040208, 19336040203" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000159/2022-2023 | 155/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | SAHA ENGINEERS | 4.86 | 3.54 | 72.8 | 0
42 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336030813, 19336030802, 19336030725, 19336030714, 19336030814" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000145/2022-2023 | 141/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | GHOSH ENTERPRISE | 4.87 | 3.54 | 72.75 | 0
43 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040214, 19336040217, 19336040309, 19336040323, 19336040105" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000158/2022-2023 | 154/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | BIPLAB GUHA | 4.87 | 3.18 | 65.37 | 0
44 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040205, 19336040102, 19336040206, 19336040201, 19336040409" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000160/2022-2023 | 156/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | A.K ADHIKARY | 4.86 | 3.7 | 76.01 | 0
45 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing Water supply arrangement at Anganwari Centers under CHAPRA Block from existing piped water supply scheme. AWC Code : 19336040913, 19336040912, 19336040911, 19336040905, 19336040906" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000165/2022-2023 | 157/AE-I/NACD-II | 14/07/2022 | 28/08/2022 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 4.86 | 3.81 | 78.33 | 0
46 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130507, 19336130503, 19336130510, 19336130601, 19336130603" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000168/2022-2023 | 90/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | SANJIT DAS | 4.94 | 4.35 | 88.03 | 0
47 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Chakdah Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000236/2022-2023 | 941/NACD-II | 21/11/2022 | 19/02/2023 | SANJOY BAKSHI | 94.61 | 94.1 | 99.46 | 100
48 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130615, 19336130620, 19336130522, 19336130701, 19336130703" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000169/2022-2023 | 91/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | BASUDEB SAHA | 4.94 | 4.35 | 88.05 | 0
49 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Providing water supply arrangement at Anganwari Centers under Krishnagar-I Block from existing piped water supply scheme under Nadia Arsenic Civil Division-II, P.H.E Dte. (Phase-II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000238/2022-2023 | 943/NACD-II | 21/11/2022 | 20/01/2023 | PAPAN ROY | 38.09 | 33.77 | 88.65 | 70
50 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | "Providing water supply arrangement at Anganwadi Centres under KRISHNAGANJ BLOCK from existing piped water supply scheme. AWC Code : 19336130305, 19336130311, 19336130316, 193361300418, 19336130506" | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000167/2022-2023 | 89/AE-II/NACD-II | 07/07/2022 | 21/08/2022 | CHINMOY BISWAS | 4.94 | 4.7 | 95.14 | 0
51 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING WATER SUPPLY FACILITY THROUGH EXISTING PWSS TO ANGANWADI CENTERS (1245 Nos.) IN NADIA DISTRICT (PHASE-II) | SM/10029 | Anganwadi | Field level survey of different School/Anganwadi Centre (AWC) by GPS enabled Mobile application for uploding data at IMIS website in Nadia District under the jurisdiction of Nadia Arsenic Civil Division-II, PHE Dte.(AWC Phase- I / II) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000330/2023-2024 | 668_AE-I/NACD-II | 18/03/2024 | 28/12/2024 | TECH VISION | 3.36 | 2.95 | 87.89 | 100
Total | [13 empty] | 1203.66 | 1057.03 | 87.82