## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction of Boundary wall with Grill Gate at Brittihuda 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000286/2021-2022 | 241/AE-I/NACD-II | 17/02/2022 | 19/03/2022 | TAPAS GHOSH | 3.41 | 3.36 | 98.58 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction of Boundary wall with Grill Gate at Brittihuda 3rd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000287/2021-2022 | 242/AE-I/NACD-II | 17/02/2022 | 19/03/2022 | SURAJIT KUMAR GHOSH | 3.41 | 3.37 | 98.83 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction of Boundary wall with Grill Gate at Brittihuda 4th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000288/2021-2022 | 243/AE-I/NACD-II | 17/02/2022 | 19/03/2022 | CHINMOY BISWAS | 3.41 | 3.39 | 99.39 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction of Boundary wall with Grill Gate at Brittihuda 5th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000289/2021-2022 | 244/AE-I/NACD-II | 17/02/2022 | 19/03/2022 | M/S RAJESH CONSTRUCTION | 4.05 | 3.99 | 98.42 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Baliadanga W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000276/2021-2022 | 124/NACD-II | 21/02/2022 | 22/05/2022 | SINGHA ROY & CO. | 138.93 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000292/2021-2022 | 127/NACD-II | 21/02/2022 | 22/05/2022 | MALLICK ENTERPRISE | 159.32 | 159.1 | 99.86 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From-01/03/2022 to 28/02/2023) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000405/2021-2022 | 276//AE-I/NACD-II | 25/02/2022 | 09/03/2022 | BABLU KUMAR SINGH | 4.98 | 2.32 | 46.63 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Brittihuda W/s Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000357/2022-2023 | 296/NACD-II | 09/03/2023 | 29/03/2023 | BISWANATH DAS | 2.05 | 0 | 0 | 85
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Brittihuda PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000155/2023-2024 | 520/AE-I/NACD-II | 18/12/2023 | 25/12/2023 | MAKALI ENGINEERING CORPORATION | 0.58 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000054/2022-2023 | 224/NACD-II | 05/04/2022 | 04/07/2022 | MALLICK ENTERPRISE | 154.65 | 154.65 | 100 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2022 to 28/02/2023) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000402/2021-2022 | 55//AE-II/NACD-II | 17/02/2022 | 17/02/2023 | SAJAL SAHA | 4.98 | 0.72 | 14.54 | 100
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From-01/03/2023 to 31/03/2023) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000359/2022-2023 | 253/NACD-II | 27/02/2023 | 30/03/2023 | BABLU KUMAR SINGH | 0.42 | 0.38 | 91.21 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS, Total station, DGPS, Auto levels etc over the command area of Brittihuda Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Brittihuda W/S Scheme in chapra Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000020/2023-2024 | 550/NACD_II | 11/05/2023 | 31/05/2023 | MALLICK ENTERPRISE | 10.11 | 10.11 | 100 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000035/2022-2023 | 373/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 12.32 | 0 | 0 | 0
15 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 15/04/2023 | B.T. PROJECTS PVT. LTD | 91.82 | 17.39 | 18.94 | 60
16 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Brittihuda Piped Water Supply Scheme under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000005/2023-2024 | 468/NACD-II | 20/04/2023 | 20/05/2023 | M/S GHOSH CONSTRUCTION | 29.12 | 24.73 | 84.92 | 85
17 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Gongra Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000284/2023-2024 | 176/NACD-II | 07/02/2024 | 07/04/2024 | ACQUA CONSTRUCTION CONSORTIUM | 177.79 | 0 | 0 | 0
18 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Repair and Renovation work at Brittihuda 5th tube well Site under Brittihuda Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000327/2024-2025 | 1023/AE-I/NACD-II | 10/12/2024 | 09/01/2025 | PRADUT GHOSH | 4.11 | 0 | 0 | 0
19 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Balance Laying of a dedicated UPVC pipeline for supplying drinking water from newly constructed manifold at Head Works site towards Arangsarisha, Deulia Village of Brittihuda W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000145/2023-2024 | 1414/NACD-II | 14/12/2023 | 13/03/2024 | M/S GHOSH CONSTRUCTION | 151.57 | 150.12 | 99.04 | 100
20 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-I, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000059/2024-2025 | 792/AE-I/NACD-II | 01/07/2024 | 01/07/2025 | BABLU KUMAR SINGH | 4.98 | 3.18 | 63.93 | 0
21 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Supply of Water Level Indicator at Brittihuda,Mahatpur,Bahirgachhi Zone-1,Bahirgachhi Zone-II,Bagberia,Betberia PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000427/2024-2025 | 1191/AE-I/NACD-II | 25/02/2025 | 11/04/2025 | MAYA ENTERPRISE | 4.58 | 0 | 0 | 0
22 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000386/2024-2025 | 1360/NACD-II | 30/09/2024 | 29/11/2024 | SUMIT GHOSH | 165.15 | 0 | 0 | 0
23 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at Mouza-Pitambarpur under habitation Mallickpara under Brittihuda Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000388/2024-2025 | 131/NACD-II | 29/01/2025 | 29/03/2025 | MALLICK ENTERPRISE | 23.07 | 0 | 0 | 0
24 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Brittihuda Water Supply Scheme of capacity 220 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000322/2023-2024 | 235/NACD-II | 21/02/2024 | 21/04/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 446.92 | 393.29 | 88 | 90
25 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction of pumphouse with sanitary and water supply arrangement at Pitambarpur mouza in Brittihuda Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000368/2024-2025 | 1617/NACD-II | 18/12/2024 | 17/01/2025 | M/S ARATI ENTERPRISE | 6.19 | 0 | 0 | 0
26 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Laying of Distribution Pipeline along with Parallal Line along with FHTC reconnection and leftout FHTC at Brittihuda W/s Scheme at Chapra block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000343/2024-2025 | 1568/NACD-II | 06/12/2024 | 01/03/2026 | SANJIB DEY | 101.89 | 0 | 0 | 45
27 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC under Brittihuda (Source Augmentation, Pritambarpur) ground water based water supply scheme under Block_ Chapra Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000030/2025-2026 | 702/EMD | 04/04/2025 | 04/05/2025 | M/S. G.P. ENTERPRISE | 11.6 | 0 | 0 | 0
28 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 16/09/2025 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
29 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Gokhrapota mouza in Brittihuda Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000452/2024-2025 | 344/NACD-II | 13/03/2025 | 12/04/2025 | SOMNATH GHOSH | 6.22 | 0 | 0 | 65
30 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 900 cum for providing FHTC (Functional Household Tap Connection) for Brittihuda Water Supply Scheme in Chapra Block in Nadia District under Nadia Arsenic Civil Division- II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000109/2025-2026 | 939/NACD-II | 28/07/2025 | 26/10/2025 | M/S.K.P.CONSTRUCTION | 29.21 | 0 | 0 | 0
31 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant Mouza-Pitambarpur under habitation Balirmathpara under Brittihuda Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000139/2025-2026 | 1173/NACD-II | 09/09/2025 | 09/11/2025 | SANJIB DEY | 23.07 | 0 | 0 | 0
32 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Supply of flow control devices in the closed water conduit at Brittihuda PWSS in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000131/2025-2026 | 224/AE-I/NACD-II | 01/09/2025 | 21/09/2025 | MAKALI ENGINEERING CORPORATION | 4.57 | 0 | 0 | 100
33 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Balance Laying UPVC pipeline for supplying drinking water including FHTC works and reconnection of existing FHTCs of Brittihuda W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. as per door to door survey conducted by ISA Team. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000177/2023-2024 | 1460/NACD-II | 22/12/2023 | 12/09/2025 | SANDIP BISWAS | 133.29 | 0 | 0 | 100
34 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Brittihuda Head Work site under Brittihuda Zone-III Water Supply Scheme under Nadia Arsenic Civil Division-II, PHE Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000243/2024-2025 | 1397/NACD-II | 22/10/2024 | 30/07/2025 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 10.84 | 0 | 0 | 100
35 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Repair and Renovation work at Brittihuda 4th tube well Site under Brittihuda Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000326/2024-2025 | 1022/AE-I/NACD-II | 10/12/2024 | 09/04/2025 | TAPAS GHOSH | 4.16 | 0 | 0 | 100
36 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Provisioning of Alignment by Augmenting the Prevailing Mouza's at Brittihuda W/S Scheme for Pitambarpur, Dipchandrapur, village in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000048/2024-2025 | 720/NACD-II | 07/06/2024 | 04/12/2024 | MALLICK ENTERPRISE | 127.03 | 29.13 | 22.93 | 100
37 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Repair and Renovation work at Gongra 2nd Tube Well Site water supply scheme under Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000239/2024-2025 | 1392/NACD-II | 22/10/2024 | 21/11/2024 | M/S RAJESH CONSTRUCTION | 5.79 | 0 | 0 | 100
38 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Repair and Renovation work at Brittihuda 3rd tube well Site under Brittihuda Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000206/2024-2025 | 903/AE-I/NACD-II | 10/09/2024 | 08/04/2025 | M/S. ASIT KUMAR BISWAS | 4.19 | 0 | 0 | 100
39 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Repair and Renovation work at Brittihuda 2nd tube well Site under Brittihuda Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000209/2024-2025 | 902/AE-I/NACD-II | 10/09/2024 | 08/04/2025 | NISHITH BANERJEE | 4.2 | 0 | 0 | 100
40 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Road Reastoration work along Charatala Uttar Para of Brittihuda Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000005/2025-2026 | 18/AE-I/NACD-II | 11/04/2025 | 11/05/2025 | SUMIT GHOSH | 4.8 | 0 | 0 | 100
41 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR BRITTIHUDA WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10094 | Augmentation | Road Reastoration work along Charatala Dakshin Para of Brittihuda Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000006/2025-2026 | 19/AE-I/NACD-II | 11/04/2025 | 11/05/2025 | SUMIT GHOSH | 4.76 | 0 | 0 | 100
Total | [13 empty] | 2269.96 | 959.22 | 42.26