## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Earthwork in filling in ditches at Madhupur Water Supply Scheme at Madhupur H/W site under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000122/2022-2023 | 113/AE-I/NACD-II | 28/06/2022 | 28/07/2022 | JOY HIND TUBEWELLS | 4.84 | 4.84 | 99.92 | 100
2 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Khaspu W/s Scheme, Madhupur W/s Scheme, Maniknagar W/s Scheme | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000299/2021-2022 | 251/AE-I/NACD-II | 25/02/2022 | 12/03/2022 | G. MITRA & ASSOCIATES | 2.29 | 2.29 | 100 | 100
3 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000342/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000235/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
5 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Madhupur and adjoining mouzas under Madhupur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000100/2022-2023 | 349/NACD-II | 08/06/2022 | 06/09/2022 | M/S. DIVINE | 148.51 | 125.91 | 84.78 | 85
6 | NADIA | Chapra | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Madhupur Piped Water Supply Scheme, Block: Dist. Nadia Under EMD, PHE Dte. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.-13) |  |  | ORD/000106/2022-2023 | 5020/EMD | 03/11/2022 | 03/12/2022 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 41.25 | 0 | 0 | 0
7 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Madhupur 2nd Tubewell site within Madhupur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000341/2022-2023 | 144/NACD-II | 17/01/2023 | 18/03/2023 | GANGULY ENTERPRISE | 4.8 | 4.67 | 97.35 | 85
8 | NADIA | Chapra | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Supply, delivery of PCC Pole, M.s materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection at PH-II under Madhupur W/S Scheme. |  |  | ORD/002571/2022-2023 | 1137/EMSD-III | 14/08/2022 | 13/09/2022 | NEW RANBEE ENGINEERING | 0.19 | 0.19 | 100 | 0
9 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Construction for priliminary work of the approch road at Head Works site of Madhupur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000077/2023-2024 | 416/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | B.D. COSNTRUCTION | 0.86 | 0 | 0 | 0
10 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Madhupur and Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000020/2022-2023 | 245/NACD-II | 19/04/2022 | 18/06/2022 | JOY HIND TUBEWELLS | 41.88 | 40.57 | 96.89 | 100
11 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Madhupur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II (HQ), Nadia Arsenic Civil Divisi | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000035/2022-2023 | 22/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | AMARENDRA NATH PANDAY | 2.83 | 2.81 | 99.27 | 100
12 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Madhupur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000002/2022-2023 | 211/NACD-II | 05/04/2022 | 04/06/2022 | AMARENDRA NATH PANDAY | 5.38 | 5.33 | 99.15 | 100
13 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Madhupur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000192/2022-2023 | 622/NACD-II | 06/09/2022 | 26/09/2022 | MAKALI ENGINEERING CORPORATION | 3.62 | 3.62 | 100 | 100
14 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Chapra Block of Nadia District through Jadavpur University. (Name of Scheme Madhupur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000052/2023-2024 | 857/NACD-II | 08/08/2023 | 29/08/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
15 | NADIA | Chapra | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Supply delivery of PCC Pole, MS materials and electrical accessories and installation of DTR including strings and sagging of HTOH line to WBSEDCL for new service connection at PH-I under Madhupur W/S scheme under EMSD-III |  |  | ORD/002988/2022-2023 | 1230EMD | 14/08/2022 | 13/09/2022 | NEW RANBEE ENGINEERING | 4.03 | 4.03 | 100 | 100
16 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Material Requisition To Resource Division |  |  | RTOR000008/2022-2023 | 397/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 27.35 | 0 | 0 | 0
17 | NADIA | Chapra | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Erection of 02 nos 8mtr PCC Pole with allied works IRO Madhupur PHE I under Chapra CCC |  |  | BILL/02523/2023-2024 | BP-146-23-24 | 23/08/2023 | 23/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.27 | 0 | 0 | 0
18 | NADIA | Chapra | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Madhupur W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/000100/2022-2023 | 5014/EMD | 03/11/2022 | 03/12/2022 | M/S. SAJAHAN CHOWDHURY | 10.12 | 10.08 | 99.65 | 100
19 | NADIA | Chapra | Eastern Mechanical | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Madhupur W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. NNo.- 05) | Assistant Engineer | Junior Engineer | ORD/000099/2022-2023 | 5013/EMD | 03/11/2022 | 03/12/2022 | M/S.A.K. BANERJEE. | 10.14 | 9.99 | 98.56 | 90
20 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Madhupur Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000316/2022-2023 | 80/NACD-II | 10/01/2023 | 11/03/2023 | NIVEDITA CONSTRUCTION | 15.8 | 15.77 | 99.83 | 100
21 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Madhupur water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000380/2022-2023 | 382/NACD-II | 24/03/2023 | 01/03/2026 | SUBHASH BOSE | 119.12 | 9.44 | 7.92 | 76
22 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 35 cum/Hour capacity for Madhupur Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000167/2024-2025 | 1146/NACD-II | 23/08/2024 | 19/02/2025 | MAMATA USHA ENTERPRISE | 164.41 | 0 | 0 | 0
23 | NADIA | Chapra | Nadia Arsenic Civil Division II | MADHUPUR PIPED WATER SUPPLY SCHEME | SM/10103 | New | Supply of flow control devices in the closed water conduit at Madhupur PWSS in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000259/2024-2025 | 945/AE-I/NACD-II | 24/10/2024 | 31/10/2024 | MAKALI ENGINEERING CORPORATION | 0.79 | 0.79 | 100 | 100
Total | [13 empty] | 613.3 | 245.11 | 39.97