## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Chapra | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | NEW SERVICE CONNECTION CHARGES FOR KARUIGACHHI W/S SCHEME P .H NO I &II | Assistant Engineer | Junior Engineer | ORD/000010/2022-2023 | 2868/EMD | 21/07/2022 | 20/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.24 | 0 | 0 | 0
2 | NADIA | Chapra | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | NEW SERVICE CONNECTION FOR KARUIGACHI W/S SCHEME FOR P.H NO 1 | Assistant Engineer | Junior Engineer | ORD/000011/2022-2023 | 2869/EMD | 21/07/2022 | 20/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
3 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Jitpur W/s Scheme, Kanainagar W/s Scheme, Karuigachhi W/s Scheme | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000298/2021-2022 | 250/AE-I/NACD-II | 25/02/2022 | 12/03/2022 | PROSENJIT DAS | 2.44 | 2.44 | 100 | 100
4 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Soil Investigation for Construction of 3 (Three) Nos. of Overhead Reservoir of staging height of 20 mtr. Under Nadia Arsenic Civil Division-II P.H.E. Dte. Site - Mrigi W/s Scheme, Panchdara Abhaynagar W/s Scheme, Paninala W/s Scheme | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000300/2021-2022 | 252/AE-I/NACD-II | 25/02/2022 | 12/03/2022 | PROSENJIT DAS | 2.44 | 0 | 0 | 100
5 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000232/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
6 | NADIA | Chapra | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | New service connection charges bill KARUIGACHHI W/s Scheme |  |  | VCH/001931/2022-2023 | BP-2022-23-29 | 02/08/2022 | 02/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.16 | 0 | 0 | 0
7 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000339/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
8 | NADIA | Chapra | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | New Service connection bill for KARUIGACHHI PIPED WATER SUPPLY SCHEME |  |  | VCH/001930/2022-2023 | BP-2022-23-28 | 02/08/2022 | 02/08/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
9 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Karuigachhi 2nd Tubwell site within Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000338/2022-2023 | 118/NACD-II | 11/01/2023 | 12/03/2023 | MAYA ENTERPRISE | 4.78 | 4.41 | 92.25 | 85
10 | NADIA | Chapra | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Supply delivery of PCC Pole MS materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new connectionat PH-II under Karuigachi W/S Scheme. |  |  | ORD/002600/2022-2023 | 1395/SD-III | 14/08/2022 | 13/09/2022 | R.N.S. TRADING | 1.03 | 1.03 | 100 | 0
11 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Karuigachhi water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000032/2022-2023 | 19/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | NIVEDITA CONSTRUCTION | 2.83 | 2.81 | 99.27 | 100
12 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Karuigachhi water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000004/2022-2023 | 210/NACD-II | 05/04/2022 | 04/06/2022 | NIVEDITA CONSTRUCTION | 5.38 | 5.33 | 99.16 | 100
13 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bhatgachhi and Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000021/2022-2023 | 246/NACD-II | 19/04/2022 | 18/06/2022 | JOY HIND TUBEWELLS | 41.88 | 0 | 0 | 100
14 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Karuigachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000191/2022-2023 | 621/NACD-II | 06/09/2022 | 26/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.96 | 3.96 | 100 | 100
15 | NADIA | Chapra | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Supply delivery of PCC Pole M.s materials and Electrical accessories and installation DTR of HTOH line to WBSEDCL for new service connection at PH-I under Karuigachi W/S Scheme |  |  | ORD/002688/2022-2023 | 1227/EMSD-III | 21/10/2022 | 20/11/2022 | M/S G.P. ENTERPRISE | 5.17 | 5.17 | 100 | 10
16 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Karuigachhi) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000088/2023-2024 | 917/NACD-II | 01/09/2023 | 22/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
17 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 396/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 38.34 | 0 | 0 | 0
18 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Karuigachhi Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000315/2022-2023 | 79/NACD-II | 10/01/2023 | 11/03/2023 | A.S. CONSTRUCTION | 14.61 | 14.21 | 97.28 | 85
19 | NADIA | Chapra | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Karuigachhi W/S Scheme Dist.-Nadia. NIET NO.- 16 of EE/EMD OF 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/000097/2022-2023 | 5011/EMD | 03/11/2022 | 03/12/2022 | M/S. G.P. ENTERPRISE | 10.13 | 10 | 98.77 | 100
20 | NADIA | Chapra | Eastern Mechanical | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Karuigachhi W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 04) | Assistant Engineer | Junior Engineer | ORD/000098/2022-2023 | 5012/EMD | 03/11/2022 | 03/12/2022 | JAL PRAVAHIKA PVT. LTD. | 10.11 | 10.09 | 99.79 | 100
21 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000039/2023-2024 | 404/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | SANDIP BISWAS | 0.97 | 0.96 | 99 | 100
22 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Continuation work order for Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000131/2024-2025 | 837_AE-I/NACD-II | 01/08/2024 | 16/08/2024 | SANDIP BISWAS | 0.93 | 0.92 | 99.05 | 100
23 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Karuigachi) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000355/2023-2024 | 433/NACD-II | 15/03/2024 | 05/04/2024 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
24 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Conversion of IEP to AIRP at Balidanga Water Supply Scheme of capacity 58 Cu.m/hr in Chapra Block including other works at Bhatgachhi & Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000137/2024-2025 | 1048/NACD-II | 07/08/2024 | 06/10/2024 | DEBASIS SAMADDAR | 185.55 | 0 | 0 | 0
25 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Laying of Rising Main of Karuigachhi Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000038/2022-2023 | 25/AE-I/NACD-II | 13/04/2022 | 27/01/2025 | SURAJIT KUMAR GHOSH | 4.28 | 2.43 | 56.71 | 90
26 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Continuation Work Order for Construction of approch road at Head Works site of Karuigachi Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000534/2024-2025 | 1165/AE-I/NACD-II | 31/01/2025 | 15/02/2025 | SANDIP BISWAS | 0.97 | 0 | 0 | 100
27 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Karuigachhi and adjoining mouzas under Karuigachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. |  |  | BILL/00419/2025-2026 |  | 27/08/2025 | 27/08/2025 | JOY HIND TUBEWELLS | 7.89 | 0 | 0 | 0
28 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Bhatgachhi and Karuigachhi Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. |  |  | BILL/00009/2025-2026 |  | 17/04/2025 | 17/04/2025 | JOY HIND TUBEWELLS | 2.14 | 0 | 0 | 0
29 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Karuigachhi and adjoining mouzas under Karuigachhi Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000069/2022-2023 | 303/NACD-II | 20/05/2022 | 18/08/2022 | JOY HIND TUBEWELLS | 152.87 | 147.26 | 96.33 | 100
30 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Construction and installation of MANIFOLD and allied works at OHR site under Bagberia Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000332/2024-2025 | 1582/NACD-II | 11/12/2024 | 04/06/2026 | SANDIP BISWAS | 111.44 | 0 | 0 | 75
31 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 38 cum/Hour capacity for Karuigachhi Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000211/2024-2025 | 1153/NACD-II | 27/08/2024 | 17/08/2026 | PUSPA ENTERPRISE | 168.65 | 0 | 0 | 80
32 | NADIA | Chapra | Nadia Arsenic Civil Division II | KARUIGACHHI PIPED WATER SUPPLY SCHEME | SM/10106 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Karuigachhi water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000010/2023-2024 | 525/NACD-II | 08/05/2023 | 09/05/2026 | SANDIP BISWAS | 116.49 | 49.12 | 42.16 | 95
Total | [13 empty] | 909.53 | 270.8 | 29.77