## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of Boundary wall with Grill Gate at Mahatpur 4th site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000284/2021-2022 | 239/AE-I/NACD-II | 17/02/2022 | 19/03/2022 | BASUDEB SAHA | 3.81 | 0 | 0 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Continuation work order for Piling work at Krishnagar Karimpur Road side for pipe line protection at Brittihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000343/2021-2022 | 211./AE-I/NACD-II | 20/01/2022 | 04/02/2022 | TAPAS GHOSH | 4.92 | 0 | 0 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Repairing and paitning of Overhead Reservoir and other allied works under augmentation of Lakshmipur PWSS of Chapra Block. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000344/2021-2022 | 191./AE-I/NACD-II | 29/12/2021 | 23/01/2022 | PRABIR KUMAR ROY | 4.81 | 0 | 0 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of Boundary Wall at OHR Head Work site of Madhabpur W/s Scheme under Nadia Arsenic Civil Division - II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000292/2020-2021 | 20./AE-II/NACD-II | 19/02/2021 | 01/03/2021 | B.M. ENGINEERING & CONSTRUCTION | 4.96 | 0 | 0 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Reparing and painting of Overhead Reservoir and pump house of Gongra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000026/2022-2023 | 05/AE-I/NACD-II | 04/04/2022 | 19/05/2022 | GOUTAM HALDER | 5 | 0 | 0 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Continuation work order for Electrical and Civil works and other allied works under retrofitting of Mahatpur PWSS under Chapra Block. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000333/2021-2022 | 308/AE-I/NACD-II | 23/03/2022 | 12/04/2022 | CHINMOY BISWAS | 4.92 | 0 | 0 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of Boundary wall with Grill Gate at Mahatpur 2nd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000282/2021-2022 | 237/AE-I/NACD-II | 17/02/2022 | 19/03/2022 | ROY CONSTRUCTION | 3.85 | 0 | 0 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of Boundary wall with Grill Gate at Mahatpur 3rd site Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000283/2021-2022 | 238/AE-I/NACD-II | 17/02/2022 | 19/03/2022 | SHYAMAL KANTI GHOSH | 3.84 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | RESOURCE PAYMENT MAHATPUR |  |  | VCH/000887/2021-2022 | 258 | 26/03/2022 | 26/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E DTE. | 61 | 0 | 0 | 0
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000307/2021-2022 | 42/NACD-II | 17/01/2022 | 03/03/2022 | NILAY KUMAR BHATTACHARYA | 21.05 | 0 | 0 | 100
11 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Providing Functional School Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000372/2022-2023 | 351/NACD-II | 22/03/2023 | 11/04/2023 | SAMARESH GHOSH | 1.1 | 0 | 0 | 90
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Structural Health assesment of existing shaft type OHR of Chapra Blocks and ancillary structures conducting Non-Destructive test and through visual observation under Nadia Arsenic Civil Division-II P.H.E Dte. |  |  | ORD/000149/2023-2024 | 1429/NACD-II | 15/12/2023 | 14/01/2024 | SIRCON ENGINEERING SERVICE | 8.46 | 0 | 0 | 0
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of Boundary wall with Grill Gate at Mahatpur Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000250/2021-2022 | 108/NACD-II | 10/02/2022 | 27/03/2022 | PARTHA DAS | 8.55 | 0 | 0 | 100
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mahatpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000254/2021-2022 | 117/NACD-II | 15/02/2022 | 16/05/2022 | M/S. R.K.ENTERPRISE | 173.44 | 0 | 0 | 100
15 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Route survey engaging qualified surveyors with modern instruments viz-GPS, Total station, DGPS, Auto levels etc over the command area of Mahatpur Water Supply Scheme and preparation of completion drawing of the LDS IN Auto CAD or similar software for Mahatpur W/S Scheme in chapra Block of Nadia Dist.under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000019/2023-2024 | 549/NACD_II | 11/05/2023 | 31/05/2023 | LAKSHMI CONSTRUCTION | 9.09 | 0 | 0 | 100
16 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc Augmentation to Accomodate FHTC under BRITTIHUDA (Block- Chapra), BARNIA (Block- Tehatt II ), MAHATPUR (Block- Chapra ), MATIARY (Block- Krishnaganj), BAGAKHALI (Z-I) (Block- Tehatta I ), BARA NALDAH (Block- Tehatta II ) W/S Scheme, , Dist. - Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/001768/2022-2023 | 1120/EMD | 16/03/2023 | 15/04/2023 | B.T. PROJECTS PVT. LTD | 91.82 | 0 | 0 | 60
17 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Kathgara Muslimpara mouza in Mahatpur Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte.Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000238/2024-2025 | 1391/NACD-II | 22/10/2024 | 21/11/2024 | BABLU MALLICK | 6.22 | 0 | 0 | 1
18 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Repair and Renovation work at Mahatpur 2nd tube well Site under Mahatpur Piped Water Supply Scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000330/2024-2025 | 1027/AE-I/NACD-II | 10/12/2024 | 09/01/2025 | SUPRIO MAJUMDER | 3.2 | 0 | 0 | 0
19 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD)& strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Kathgara,Habitation of Muslim Para under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000227/2024-2025 | 1322/NACD-II | 20/09/2024 | 04/11/2024 | DHELA BABA ENTERPRISES | 10.4 | 0 | 0 | 0
20 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Mahatpur Piped Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000140/2023-2024 | 1367/NACD-II | 08/12/2023 | 07/01/2024 | M/S GHOSH CONSTRUCTION | 45.3 | 0 | 0 | 100
21 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Providing Functional House Hold Tap Connection including laying of pipeline at TENGRA W/S Scheme in Tengra Village Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000252/2023-2024 | 660/AE-I/NACD-II | 21/02/2024 | 07/03/2024 | ASHIM ENTERPRISE | 3.91 | 0 | 0 | 100
22 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Continuation Work Order for Collection of Household Details at Prescribed Format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and Submission of the same to PHE Dte. in soft copy for Bagakhali Zone-I & Mahatpur PWSS under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000199/2024-2025 | 898/AE-I/NACD-II | 09/09/2024 | 08/11/2024 | JOY GOPAL GUPTI | 3.5 | 0 | 0 | 100
23 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Approximate expenditure for land registration and subsequent mutation process as compliance for PHED and Land Commissioner aiuthories to overcome the stalemate and initiation of due diligence processes in Krishnaganj Block under Nadia Arsenic Civil Division-II under Nadia District PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000232/2024-2025 | 933/AE-I/NACD-II | 04/10/2024 | 11/10/2024 | SOMNATH GHOSH | 0.75 | 0 | 0 | 100
24 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under chapra Block of Nadia District through Jadavpur University. (Name of PWSS Gongra & Mahatpur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000385/2023-2024 | 1267_NACD-II | 09/11/2023 | 30/11/2023 | JADAVPUR UNIVERSITY | 5.9 | 0 | 0 | 100
25 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Approximate expenditure for land registration and subsequent mutation process as compliance for PHED and Land Commissioner aiuthories to overcome the stalemate and initiation of due diligence processes in Krishnanagar-I Block under Nadia Arsenic Civil Division II under Nadia District PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000235/2024-2025 | 936/AE-I/NACD-II | 04/10/2024 | 11/10/2024 | SOMNATH GHOSH | 0.75 | 0 | 0 | 100
26 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Laying of pipeline Including some Additional work at Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000128/2024-2025 | 833_AE-I/NACD-II | 01/08/2024 | 16/08/2024 | BABA LOKNATH ENTERPRISE | 0.97 | 0 | 0 | 100
27 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Tengra & Mahatpur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000377/2023-2024 | 411/NACD-II | 13/03/2024 | 03/04/2024 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 100
28 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at MAHATPUR ( Vill- MAHATPUR AND SURROUNDING AREA) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000251/2023-2024 | 221/NACD-II | 21/02/2024 | 15/02/2025 | SAFTI PRIVATE LIMITED | 37.2 | 0 | 0 | 100
29 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of pumphouse cum Chlorine room with sanitary and water supply arrangement at Bhagabanpur mouza in Mahatpur Piped water supply scheme in Chapra Block under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000391/2024-2025 | 132/NACD-II | 29/01/2025 | 28/02/2025 | SHYAMAL KANTI GHOSH | 6.22 | 0 | 0 | 0
30 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Conversion of IEP to AIRP at Tengra Water Supply Scheme of capacity 36Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000386/2024-2025 | 1360/NACD-II | 30/09/2024 | 29/11/2024 | SUMIT GHOSH | 165.15 | 0 | 0 | 0
31 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Mahatpur Water Supply Scheme of capacity 172 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000320/2023-2024 | 217/NACD-II | 16/02/2024 | 07/12/2025 | HARBAUER INDIA (P) LTD | 358.83 | 0 | 0 | 50
32 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Mahatpur,Habitation of Bhagabanpur under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000218/2024-2025 | 1189/NACD-II | 02/09/2024 | 28/08/2025 | SANDIP BISWAS | 10.4 | 0 | 0 | 88
33 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | New Sinking of 1 no. 250 mm X 150 mm dia, 150 mtr deep Tube Well by Direct Rotary Method with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Mouza Mahatpur,Habitation of Jamredanga under Mahatpur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000219/2024-2025 | 1188/NACD-II | 02/09/2024 | 28/08/2025 | SANDIP BISWAS | 10.4 | 0 | 0 | 85
34 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at mouza Kathgara ,habitation Muslim Para under Mahatpur Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000192/2024-2025 | 997/NACD-II | 25/07/2024 | 18/01/2026 | TAPU SAHA | 23.06 | 0 | 0 | 80
35 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 25/12/2025 | CHANDAN ROY | 149.25 | 0 | 0 | 20
36 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Strengthening Work of existing boundary wall at Mahatpur Headwork site at Mahatpur Piped water supply scheme at Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000342/2024-2025 | 1057/AE-I/NACD-II | 19/12/2024 | 18/01/2025 | ST. ANTHONY ENTERPRISE | 3.96 | 0 | 0 | 100
37 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Construction of 50 m3/hr capacity Iron Elimination Plant at mouza Mahatpur ,habitation Jamredanga under Mahatpur Public Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000497/2024-2025 | 273/NACD-II | 03/03/2025 | 03/05/2025 | SIRCON ENGINEERING SERVICES | 23.06 | 0 | 0 | 0
38 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Providing FHTC at leftout household alongwith necessary pipeline at Ichapur and Paliyanpur village under Madhabpur Water Supply Scheme and Mahatpur Water Supply Scheme at Chapra Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000075/2025-2026 | 114/AE-I/NACD-II | 04/06/2025 | 04/07/2025 | ACHARJEE & ASSOCIATES | 4.61 | 0 | 0 | 0
39 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including laying of pipeline at TENGRA W/S Scheme in Tengra Village Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000414/2023-2024 | 673_AE-I/NACD-II | 28/03/2024 | 12/04/2024 | ASHIM ENTERPRISE | 2.98 | 0 | 0 | 0
40 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Laying of pipeline along reconnection due to construction of drain and land erosion at Mahatpur W/S Scheme in Chapra block in Nadia District under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000443/2024-2025 | 1206/AE-I/NACD-II | 27/02/2025 | 13/04/2025 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 0.92 | 0 | 0 | 100
41 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR MAHATPUR WATER SUPPLY SCHEME IN CHAPRA BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10199 | Augmentation | Repair and renovation works of R.C.C. Elevated Reservoir 800 cum for providing FHTC (Functional Household Tap Connection) for Mahatpur Water Supply Scheme in Chapra Block in Nadia District under Nadia Arsenic Civil Division- II, PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000108/2025-2026 | 938/NACD-II | 28/07/2025 | 26/10/2025 | SANJOY BAKSHI | 27.51 | 0 | 0 | 0
Total | [13 empty] | 1319.87 | 0 | 0