## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000253/2021-2022 | 116/NACD-II | 15/02/2022 | 16/05/2022 | JOY HIND TUBEWELLS | 153.21 | 153.21 | 100 | 100
2 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation Work Order for Supply of CIDF Sluice, Non return valves and DI Mechanical collar Vavle for relaying of rising main of Thanapara Piped Water Supply Scheme under Nadia Arsenic Civil Division-II P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000223/2021-2022 | 213/AE-I/NACD-II | 20/01/2022 | 27/01/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 100
3 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation Work order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000028/2022-2023 | 202/NACD-II | 01/04/2022 | 30/06/2022 | JOY HIND TUBEWELLS | 151.4 | 151.35 | 99.96 | 100
4 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement at Thanapara Tube Well No-4 area according to departmental drawing (Size 3.60 mtr x 3.00 mtr ) of Thanapara water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000294/2021-2022 | 58/AE-II/NACD-II | 23/02/2022 | 09/04/2022 | M/S SANTOSHI MAA ENTERPRISE | 3.82 | 2.82 | 73.78 | 100
5 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Repairing and Renovation of I.E Plant at Thanapara Water Supply Scheme - Capacity - 166 cum/hr, Block -Karimpur-II under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000212/2022-2023 | 747/NACD-II | 29/09/2022 | 29/10/2022 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 9.69 | 9.65 | 99.59 | 100
6 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation work Order for Providing Functional House Hold Tap Connection (Phase-I) including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Falia) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000296/2021-2022 | 112/NACD-II | 11/02/2022 | 12/05/2022 | MONDAL ENTERPRISE | 45.84 | 45.8 | 99.91 | 100
7 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara (Vill- Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000301/2021-2022 | 03./NACD-II | 03/01/2022 | 17/02/2022 | M/S SHILL & CO. | 88.07 | 88.01 | 99.94 | 100
8 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation work order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Mobarakpur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000315/2021-2022 | 173/NACD-II | 21/03/2022 | 19/06/2022 | PATHIK PABAN NANDI | 98.64 | 0 | 0 | 100
9 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Brittihuda W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000054/2022-2023 | 224/NACD-II | 05/04/2022 | 04/07/2022 | MALLICK ENTERPRISE | 154.65 | 0 | 0 | 100
10 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 372/NACD-II | 24/03/2023 |  | Resource Division | 12.32 | 0 | 0 | 0
11 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Supply, delivery and installation of submersible pumping machinery along with other allied electro-mechanical works voltage stabilizer etc. Augmentation to accommodate FHTC at for newly sunk TW (TW No. - IV) at Thanarpara water supply scheme, Karimpur II Block, Nadia under E.M.D. PHE Dte. NIET No.- 25 of EE/EMD of 2022-23 (Sl. No.- 21) | Assistant Engineer | Junior Engineer | ORD/000731/2022-2023 | 6805/EMD | 21/12/2022 | 20/01/2023 | SMILE | 8.71 | 8.71 | 100 | 0
12 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2023 to 31/03/2023) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000358/2022-2023 | 252/NACD-II | 27/02/2023 | 30/03/2023 | SAJAL SAHA | 0.42 | 0.4 | 95.33 | 100
13 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Thanapara ( Vill-Thanapara, Kalopur, Subhrajpur, Char Gourbhanga) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000263/2022-2023 | 1018/NACD-II | 29/11/2022 | 28/01/2023 | A.P. POWER & CONCRETE | 31.49 | 28.56 | 90.68 | 85
14 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Head Work Site under Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000274/2022-2023 | 1129/NACD-II | 16/12/2022 | 14/02/2023 | MUKHERJEE CONSTRUCTION | 17.21 | 17.2 | 99.98 | 95
15 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Thanapara) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000086/2023-2024 | 911/NACD-II | 29/08/2023 | 19/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
16 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Sinking of 1 nos. of 300 mm X 200 mm dia, 180 mtr deep Tube Well (as replacement of old defunct T/W) by Direct Rotary Method with UPVC pipe (CD) & strainer, (300 mm dia 36 mtr. long housing pipe &200 mm dia 30 mtr. long strainer) at Thanapara 3rd Tube Well site and 3rd Pump House site and also Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe as per required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) under Thanapara (Vill.- Gourbhanga) at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000016/2023-2024 | 546/NACD-II | 11/05/2023 | 10/07/2023 | B.M. ENGINEERING & CONSTRUCTION | 40.55 | 40.4 | 99.64 | 100
17 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000194/2022-2023 | 71/AE-II/NACD-II | 28/06/2022 | 28/06/2023 | TARUN KUMAR BHATTACHARYA | 2.07 | 3.65 | 176.18 | 50
18 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.GrF.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Thanarpara PWSS in Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000154/2023-2024 | 519/AE-I/NACD-II | 18/12/2023 | 25/12/2023 | MAKALI ENGINEERING CORPORATION | 0.58 | 0 | 0 | 0
19 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Thanapara) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000165/2023-2024 | 1279/NACD-II | 14/11/2023 | 05/12/2023 | JADAVPUR UNIVERSITY | 5.9 | 2.95 | 50 | 100
20 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Functional House Hold Tap Connection for providing connection to the School Premises including supply of 15 mm dia PVC pipe of required length, Saddle piece (As required size), 15 mm dia Bib cock etc all complete at (Remaining School only) Thanapara W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000350/2022-2023 | 150/NACD-II | 17/01/2023 | 06/02/2023 | DUTTA CONSTRUCTION | 2.68 | 0.86 | 32.06 | 100
21 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Construction and installation of MANIFOLD and allied works at OHR site under Thanarpara Piped Water Supply Scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000197/2023-2024 | 87/NACD-II | 18/01/2024 | 17/02/2024 | B.M. ENGINEERING & CONSTRUCTION | 24.4 | 0 | 0 | 0
22 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Assistant Engineer-II, under Executive Engineer, Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal.(From 01/03/2022 to 28/02/2023) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000402/2021-2022 | 55//AE-II/NACD-II | 17/02/2022 | 17/02/2023 | SAJAL SAHA | 4.98 | 0.75 | 15.1 | 100
23 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation Work Order for Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of average length of 15 mtr, Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or extension or damaged line repair) at Kadipur W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000052/2022-2023 | 222/NACD-II | 05/04/2022 | 20/05/2022 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 36.28 | 0 | 0 | 100
24 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Acceptance cum work order "Conversion of IEP to AIRP at Thanapara Water Supply Scheme of capacity 166 Cu.m/hr in Karimpur-II Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000323/2023-2024 | 236/NACD-II | 21/02/2024 | 21/04/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 354.2 | 123.97 | 35 | 65
25 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Acceptance cum work order "Construction of 50 m3/hr capacity IEP at Thanarpara Zone-II PWSS in Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000337/2023-2024 | 432/NACD-II | 15/03/2024 | 14/05/2024 | EVEREST CONSULTANT SERVICES. | 23.11 | 0 | 0 | 0
26 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000394/2022-2023 | 412/NACD-II | 30/03/2023 | 24/03/2024 | TARUN KUMAR BHATTACHARYA | 4.98 | 0.92 | 18.41 | 20
27 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/07/2023 to 31/03/2024) |  |  | ORD/000132/2023-2024 | 202/1/AE-II/NACD-II | 30/06/2023 | 31/03/2024 | TARUN KUMAR BHATTACHARYA | 3.74 | 1.32 | 35.34 | 30
28 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/07/2023 to 31/03/2024) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000358/2023-2024 | 202/1/AE-II/NACD-II | 30/06/2023 | 31/03/2024 | TARUN KUMAR BHATTACHARYA | 3.74 | 0.35 | 9.31 | 0
29 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000142/2023-2024 | 1379/NACD-II | 11/12/2023 | 10/03/2024 | M.R. CONSTRUCTION | 68.49 | 21.05 | 30.74 | 50
30 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Repair and Renovation work at Thanapara H/W site with Pathway ,Plastering ,Pump House Painting, Flooring,, PVC Water tank other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000022/2024-2025 | 145./AE-II/NACD-II | 11/06/2024 | 11/07/2024 | SOURAV & CO. | 2.91 | 0 | 0 | 0
31 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-I (Vill-Natidanga, Char Adityapur, Thanarpara) and Thanarpara Zone-II (Vill- Sobharajpur, Saguna) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000372/2023-2024 | 1281/NACD-II | 16/11/2023 | 14/02/2024 | SUJATA CONSTRUCTION | 270.68 | 0 | 0 | 0
32 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Piling work in between 4th Pump House to 3rd Pump House pond site for rising main pipe line protection at Thanapara Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000050/2024-2025 | 141/AE-II/NACD-II | 11/06/2024 | 11/07/2024 | VAI ENTERPRISE | 1.26 | 0 | 0 | 0
33 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Repair and Renovation work at Thanapara 2nd & 4th pump house site with Reinforced Barbed Tape, Pathway, Plaster and other allied works Under Nadia Arsenic Division-II,P.H.E.Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000051/2024-2025 | 160/AE-II/NACD-II | 14/06/2024 | 14/07/2024 | TAPAN SAHA | 2.61 | 0 | 0 | 0
34 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with nadia Arsenic Civil Division-II, P.H.E. Dte.under Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000063/2024-2025 | 204/AE-II/NACD-II | 01/07/2024 | 26/06/2025 | TARUN KUMAR BHATTACHARYA | 4.98 | 0 | 0 | 0
35 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, under Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, Pincode:- 741101,West Bengal. (From 01/07/2024 to 30/06/2025) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000058/2024-2025 | 791/AE-I/NACD-II | 01/07/2024 | 26/06/2025 | TARUN KUMAR BHATTACHARYA | 4.98 | 0 | 0 | 0
36 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation Work Order for Hiring of 1(one) number vehicle for day to day inspection of ongoing JJM & other works related with Nadia Arsenic Civil Division-II, P.H.E. Dte. (From 01/04/2024 to 30/06/2024) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000001/2024-2025 | 78/AE-II/NACD-II | 01/04/2024 | 30/06/2024 | TARUN KUMAR BHATTACHARYA | 1.24 | 0.97 | 78 | 0
37 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2024-2025 | 983/NACD-II | 23/07/2024 |  | Resource Division | 16.39 | 0 | 0 | 0
38 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/ LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,West Bengal | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000398/2022-2023 | 412./NACD-II | 30/03/2023 | 24/03/2024 | TARUN KUMAR BHATTACHARYA | 4.98 | 2.69 | 54.07 | 0
39 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of 3rd site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of Scheme Thanapara) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000119/2024-2025 | 972/NACD-II | 19/07/2024 | 09/08/2024 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
40 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Rendering consultancy services for Geotechnical Investigation and Report preparation of 2nd site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of Scheme Thanapara) | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000118/2024-2025 | 971/NACD-II | 19/07/2024 | 09/08/2024 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
41 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Jungle cutting and Earthwork in filling at Maheshpur, Maitari and Thanarapara Piped Water Supply Scheme in different blocks under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000120/2024-2025 | 818/AE-I/NACD-II | 25/07/2024 | 01/08/2024 | BABA LOKNATH ENTERPRISE | 0.76 | 0 | 0 | 100
42 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Wall writing work in various Gram Panchayats in Karimpur-II Block at Thanapara PWSS under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000045/2024-2025 | 756/AE-I/NACD-II | 19/06/2024 | 04/07/2024 | IMAGIN | 0.93 | 0 | 0 | 100
43 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Construction of approch road at Head Works site of Thanapara Zone-II Water Supply Scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000147/2024-2025 | 249/AE-II/NACD-II | 31/07/2024 | 15/08/2024 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0 | 0 | 0
44 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement at Thanapara Zone-III Tube Well No-2 area according to departmental drawing (Size 3.60 mtr x 3.00 mtr ) under Thanapara Zone-III Piped water supply scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000195/2024-2025 | 309AE-II/NACD-II | 06/09/2024 | 21/10/2024 | MUKHERJEE CONSTRUCTION | 4.18 | 0 | 0 | 0
45 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Continuation work order for Hiring of 1(one) number vehicle of Category Motor Days Cab/ Maruti Omni(standard) (Non Air-Conditioned)/ Diesel/LPG/ CNG Engine including Driver for performing the inspection works and official duties of the Executive Engineer, of Nadia Arsenic Civil Division-II, P.H.E. Dte.at 1 S.K Basu Road Krishnagar, District-Nadia, PINCODE:- 741101,WestBengal (From 01/04/2024 to 30/06/2024) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000003/2024-2025 | 504/NACD-II | 01/04/2024 | 30/06/2024 | TARUN KUMAR BHATTACHARYA | 1.24 | 0 | 0 | 0
46 | NADIA |  | Eastern Mechanical | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Manoharpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer |  | ORD/003362/2023-2024 | 865/EMD | 14/03/2024 | 13/04/2024 | CINZANO | 22.25 | 0 | 0 | 0
47 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Sinking of 3 nos. Tube Well at H/W site ,2nd and 3rd T/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-III & Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000136/2024-2025 | 1047/NACD-II | 07/08/2024 | 05/11/2024 | B.M. ENGINEERING & CONSTRUCTION | 34.68 | 0 | 0 | 100
48 | NADIA |  | Nadia Arsenic Civil Division II | PROVIDING FHTC (FUNCTIONAL HOUSEHOLD TAP CONNECTION ) BY AUGMENTATION UNDER JAL SWAPNA FOR THANAPARA WATER SUPPLY SCHEME IN KARIMPUR-II BLOCK OF NADIA DISTRICT UNDER NADIA ARSENIC CIVIL DIVISION-II,PHE DTE. | SM/10200 | Augmentation | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement at Thanapara Zone-III Tube Well No-3 area according to departmental drawing (Size 3.60 mtr x 3.00 mtr ) under Thanapara Zone-III Piped water supply scheme in Karimpur-II Block under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000210/2024-2025 | 310AE-II/NACD-II | 06/09/2024 | 21/10/2024 | NISHITH BANERJEE | 4.18 | 0 | 0 | 0
Total | [13 empty] | 1749.71 | 724.91 | 41.43