## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Earth work in filling in ditches at Khaspu 2nd Tube Well Site for development of land in connection with proposed T/W Sinking & Pump House construction at Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000126/2022-2023 | 62/AE-II/NACD-II | 28/06/2022 | 13/07/2022 | BASUDEB SAHA | 0.6 | 0 | 0 | 100
2 | NADIA | Tehatta-I | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | New connection charges for Khaspur PHE I Tehatta Nadia. Memo no. 3004031111/Quot/03 |  |  | VCH/003377/2022-2023 |  | 21/11/2022 | 21/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.5 | 0 | 0 | 0
3 | NADIA | Tehatta-I | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | New connection charges for Khaspur PHE I Tehatta Nadia. Memo no. 3004031098/Quot/03 |  |  | VCH/003376/2022-2023 |  | 21/11/2022 | 21/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
4 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000349/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
5 | NADIA | Tehatta-I | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | New Service Connection for PH No.-I under Khaspur Tehatta Nadia |  |  | BILL/00006/2022-2023 | 91/EMD | 26/11/2022 | 26/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.07 | 0 | 0 | 0
6 | NADIA | Tehatta-I | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | New Service Connection for PH No.-II under Khaspur Tehatta Nadia |  |  | BILL/00007/2022-2023 | 92/EMD | 26/11/2022 | 26/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.5 | 0 | 0 | 0
7 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000243/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
8 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Dhopahat and Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000017/2022-2023 | 242/NACD-II | 19/04/2022 | 18/06/2022 | AUXILIARY TUBE WELL DRILLERS | 43.18 | 0 | 0 | 100
9 | NADIA | Tehatta-I | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Supply delivery of PCC pole, M.S materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection P.H No. II under Khaspur w/s scheme under EMSD III, PHE Dte. Dhubulia Nadia. |  |  | ORD/002526/2022-2023 | 108/EMSDIII18.01.23 | 14/08/2022 | 14/12/2022 | MA ANNAPURNA ENTERPRISE | 3.12 | 0 | 0 | 0
10 | NADIA | Tehatta-I | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | PCC pole M.S materials and electrical accessories including stringing and sagging of HTOH line to WBSEDCL for new service connection at PH-I under Khaspu W/S scheme. |  |  | ORD/002573/2022-2023 | 103/EMSD-I | 18/01/2023 | 17/02/2023 | SHIVAM ENTERPRISE | 3.8 | 0 | 0 | 0
11 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Khaspu water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000013/2022-2023 | 218/NACD-II | 05/04/2022 | 04/06/2022 | PAPAN ROY | 5.37 | 0 | 0 | 100
12 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Laying of Rising Main of Khaspu Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000060/2022-2023 | 21/AE-II/NACD-II | 18/04/2022 | 18/05/2022 | A.K ADHIKARY | 4.14 | 0 | 0 | 100
13 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Khaspu Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000197/2022-2023 | 626/NACD-II | 06/09/2022 | 26/09/2022 | RAMASISH ENTERPRISE | 4.6 | 0 | 0 | 100
14 | NADIA | Tehatta-I | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Khaspu W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 05) |  |  | ORD/000447/2022-2023 | 6261/EMD | 19/11/2022 | 19/12/2022 | SHIVAM ENTERPRISE | 9.98 | 0 | 0 | 90
15 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Khaspu Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000322/2022-2023 | 86/NACD-II | 10/01/2023 | 11/03/2023 | BURIMA CONSTRUCTION | 16.35 | 0 | 0 | 100
16 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Khaspu 2nd Tubewell Site within Khaspu Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000332/2022-2023 | 125/NACD-II | 11/01/2023 | 12/03/2023 | SHYAMAL KANTI GHOSH | 6.31 | 0 | 0 | 85
17 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS: Khaspu) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000056/2023-2024 | 862/NACD-II | 10/08/2023 | 31/08/2023 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 100
18 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Khaspu water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000049/2022-2023 | 16/AE-II/NACD-II | 11/04/2022 | 10/06/2022 | PAPAN ROY | 2.83 | 0 | 0 | 100
19 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Material Requisition To Resource Division |  |  | RTOR000007/2022-2023 | 405/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 35.72 | 0 | 0 | 0
20 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Khaspu and adjoining mouzas under Khaspur Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000065/2022-2023 | 293/NACD-II | 18/05/2022 | 16/08/2022 | SUDHAMAY MAJUMDAR | 169.33 | 0 | 0 | 100
21 | NADIA | Tehatta-I | Eastern Mechanical | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Khaspu W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 06) | Assistant Engineer | Junior Engineer | ORD/000444/2022-2023 | 6260/EMD | 19/11/2022 | 19/12/2022 | A.D. CONCERN | 10 | 0 | 0 | 100
22 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of approch road at Head Works site of Khaspu Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000047/2023-2024 | 412/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | BIDYUT KUMAR | 0.97 | 0 | 0 | 100
23 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Tehatta-I Block of Nadia District through Jadavpur University. (Name of PWSS Khaspu) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000357/2023-2024 | 435/NACD-II | 15/03/2024 | 05/04/2024 | JADAVPUR UNIVERSITY | 5.9 | 0 | 0 | 100
24 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with Cl double flanged non rusting spindle sluice valves conforming to IS 14846 -2000 with latest emended having body dome/bonnet and cover of C.I.Gr-F.G 210mtr. spindle of IS-6603 G.R12/Gr-13 non-magnetic, nuts seat rings are of Gunmetal as per IS:318 LTB-2 flanges and drilled to IS: 1538 Part IV & VI valves are suitable for max. working pressure of 10kg/cm2 (seat test) and body tested to 15kg/cm2 for Khaspu, Patharghata and Chanderghat PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000179/2024-2025 | 293_AE-II/NACD-II | 30/08/2024 | 19/09/2024 | MAKALI ENGINEERING CORPORATION | 4.83 | 0 | 0 | 100
25 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of 75 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Thanarpara Zone-III Water Supply Scheme in Karimpur-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000322/2024-2025 | 1207/NACD-II | 04/09/2024 | 26/02/2026 | SINGHA ROY & CO. | 215.53 | 0 | 0 | 0
26 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Khaspu Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000222/2024-2025 | 1191/NACD-II | 02/09/2024 | 24/02/2026 | MONDAL PRECISION PRIVATE LIMITED | 164.15 | 0 | 0 | 35
27 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 16/09/2025 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
28 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Khaspu water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000011/2023-2024 | 526/NACD-II | 08/05/2023 | 01/04/2025 | BIDYUT KUMAR | 117.34 | 0 | 0 | 65
29 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | KHASPU PIPED WATER SUPPLY SCHEME | SM/10402 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III Water Supply Scheme 3rd Tube Well site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000312/2024-2025 | 1503/NACD-II | 21/11/2024 | 16/08/2025 | PARTHA DAS | 6.01 | 0 | 0 | 100
Total | [13 empty] | 1024.43 | 0 | 0