## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000242/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000348/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3 | NADIA | Krishnagar-I | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at Paninala Piped Water Supply Scheme, Block: Dist. Nadia Under EMD, PHE Dte. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.-14) |  |  | ORD/000110/2022-2023 | 6040/EMD | 07/11/2022 | 07/12/2022 | M/S S.R. ENTERPRISE | 41.38 | 0 | 0 | 0
4 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Paninala water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000029/2022-2023 | 16/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | SUMIT GHOSH | 2.83 | 2.81 | 99.27 | 100
5 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Paninala water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000005/2022-2023 | 203/NACD-II | 05/04/2022 | 04/06/2022 | SUMIT GHOSH | 5.37 | 5.32 | 99.04 | 100
6 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Paninala and Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000135/2022-2023 | 432/NACD-II | 07/07/2022 | 05/09/2022 | JOY HIND TUBEWELLS | 43.35 | 20.3 | 46.82 | 100
7 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Paninala Water Supply Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000190/2022-2023 | 620/NACD-II | 06/09/2022 | 26/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.94 | 3.94 | 100 | 100
8 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Paninala Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000318/2022-2023 | 82/NACD-II | 10/01/2023 | 11/03/2023 | ZOOM CONSTRUCTION & INTERIO | 17.3 | 17.29 | 99.95 | 85
9 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Krishnagar-I Block of Nadia District through Jadavpur University. (Name of PWSS Paninala) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000083/2023-2024 | 889/NACD-II | 18/08/2023 | 08/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
10 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hridaypur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000084/2023-2024 | 892/NACD-II | 21/08/2023 | 11/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 100
11 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Material Requisition To Resource Division |  |  | RTOR000011/2022-2023 | 401/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 55.85 | 0 | 0 | 0
12 | NADIA | Krishnagar-I | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | New service connection charges for Paninala Ph. 1 J1-43 kh-1378 |  |  | BILL/01862/2022-2023 | 140/PFMS/EMD | 06/03/2023 | 06/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0 | 0
13 | NADIA | Krishnagar-I | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | New service connection charges for Paninala Ph. 2 J1-43 kh-950 |  |  | BILL/01860/2022-2023 | 141/PFMS/EMD | 06/03/2023 | 06/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.69 | 0 | 0 | 0
14 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Paninala 2nd Tubewell site within Paninala Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000328/2022-2023 | 120/NACD-II | 11/01/2023 | 12/03/2023 | SREE GURU ENTERPRISE | 5.14 | 3.54 | 68.95 | 65
15 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 31 cum/Hour capacity for Paninala Water Supply Scheme within Krishnagar-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000166/2024-2025 | 1145/NACD-II | 23/08/2024 | 19/02/2025 | MAMATA USHA ENTERPRISE | 160.26 | 0 | 0 | 0
16 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Laying of Rising Main of Paninala Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. (Sl. No. 02) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000016/2022-2023 | 221/NACD-II | 05/04/2022 | 05/05/2022 | TAPAS GHOSH | 5.64 | 5.63 | 99.81 | 100
17 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Paninala and adjoining mouzas under Paninala Water Supply Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000115/2022-2023 | 376/NACD-II | 22/06/2022 | 20/09/2022 | KINGS & CO. | 242.52 | 163.21 | 67.3 | 90
18 | NADIA | Krishnagar-I | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Paninala W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. NNo.- 07) | Assistant Engineer | Junior Engineer | ORD/000101/2022-2023 | 5015/EMD | 03/11/2022 | 03/12/2022 | HARA PROSAD DAS | 10.11 | 9.97 | 98.59 | 100
19 | NADIA | Krishnagar-I | Eastern Mechanical | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Paninala W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer | ORD/000102/2022-2023 | 5016/EMD | 03/11/2022 | 03/12/2022 | NEW RANBEE ENGINEERING | 10.13 | 9.93 | 98.01 | 90
20 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Earth work in filling in ditches and Drum Sheet Walling at Paninala Water Supply Scheme under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000268/2022-2023 | 1070/NACD-II | 08/12/2022 | 07/01/2023 | TAPAS GHOSH | 16.37 | 16.3 | 99.58 | 100
21 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Construction for priliminary work of the approch road at Head Works site of Paninala Water Supply Scheme in Krishnagar-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000150/2023-2024 | 515/AE-I/NACD-II | 18/12/2023 | 02/01/2024 | M/S GHOSH CONSTRUCTION | 0.97 | 0.96 | 98.8 | 100
22 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Construction of a single Storied Warehouse with Steel Truss Roof at Paninala Water Supply Scheme Head Work Site under Nadia Arsenic Civil Division-II, PHE Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000296/2023-2024 | 325/NACD-II | 04/03/2024 | 26/08/2025 | AMIT KARMAKAR | 40.55 | 0 | 0 | 60
23 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | PANINALA PIPED WATER SUPPLY SCHEME | SM/10403 | New | Conversion of IEP to AIRP at KADIPUR Water Supply Scheme of capacity 55 Cu.m/hr in Krishnaganj Block & CHANDERGHAT, PANINALA & BARUIHUDA Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000419/2024-2025 | 1147/NACD-II | 23/08/2024 | 22/10/2024 | MERCURY ENGINEERING COMPANY. | 173.69 | 0 | 0 | 0
Total | [13 empty] | 852.33 | 263.97 | 30.97