## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22. |  |  | VCH/000337/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000230/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Hatkhola and adjoining mouzas under Hatkhola Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000066/2022-2023 | 298/NACD-II | 19/05/2022 | 17/08/2022 | TIRUPATI ENTERPRISES | 188.27 | 170.2 | 90.4 | 100
4 | NADIA | Chapra | Eastern Mechanical | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Providing And Installation of Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at HATKHOLA Piped Water SupplyScheme, Block: Chapra, Dist. Nadia Under EMD, PHE Dte. NIET No.- 36 of EE/EMD of 2022-23 (Sl. No.- 03) | Assistant Engineer | Junior Engineer | ORD/000013/2023-2024 | 1576/EMD | 24/04/2023 | 24/05/2023 | M/S. SAJAHAN CHOWDHURY | 40.81 | 0 | 0 | 0
5 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Hatkhola water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000033/2022-2023 | 20/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | JAYBRATO HALDER | 2.83 | 2.81 | 99.27 | 100
6 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Hatkhola water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000007/2022-2023 | 205/NACD-II | 05/04/2022 | 04/06/2022 | JAYBRATO HALDER | 5.37 | 5.32 | 99.04 | 100
7 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Sanatanpur and Hatkhola Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000136/2022-2023 | 433/NACD-II | 07/07/2022 | 05/09/2022 | B.M. ENGINEERING & CONSTRUCTION | 42.16 | 20.16 | 47.82 | 100
8 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Hatkhola Water Supply Scheme at Head Work Site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000314/2022-2023 | 78/NACD-II | 10/01/2023 | 11/03/2023 | JAYBRATO HALDER | 16.97 | 16.94 | 99.82 | 85
9 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hatkhola) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000080/2023-2024 | 880/NACD_II | 17/08/2023 | 07/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
10 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Hatkhola Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000188/2022-2023 | 618/NACD-II | 06/09/2022 | 26/09/2022 | MAKALI ENGINEERING CORPORATION | 3.86 | 3.86 | 100 | 100
11 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Material Requisition To Resource Division |  |  | RTOR000003/2022-2023 | 407/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 33.97 | 0 | 0 | 0
12 | NADIA | Chapra | Eastern Mechanical | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Electricity bill for new service connection at Hatkhola under EMSD-III |  |  | BILL/02150/2022-2023 | 144/PFMS/EMD | 10/03/2023 | 10/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.55 | 0 | 0 | 0
13 | NADIA | Chapra | Eastern Mechanical | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Electricity bill for new service connection at Hatkhola under EMSD-III |  |  | BILL/02151/2022-2023 | 145/PFMS/EMD | 10/03/2023 | 10/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0 | 0
14 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Hatkhola water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000375/2022-2023 | 361/NACD-II | 22/03/2023 | 22/03/2024 | MITRA CONSTRUCTION | 117.35 | 53.07 | 45.23 | 53
15 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Continuation work order for Construction for priliminary work of the approch road at Head Works site of Hatkhola Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000130/2024-2025 | 836_AE-I/NACD-II | 01/08/2024 | 16/08/2024 | MITRA CONSTRUCTION | 0.84 | 0 | 0 | 0
16 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Acceptance cum work order "Construction of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir at Head Works site of Tengra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000325/2023-2024 | 337/NACD-II | 05/03/2024 | 05/03/2025 | CHATTERJEE CONSTRUCTION | 94.23 | 0 | 0 | 0
17 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Acceptance cum work order "Conversion of IEP to AIRP at Bagberia & Hatkhola Water Supply Scheme of capacity 35 Cu.m/hr in Chapra Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000290/2023-2024 | 197/NACD-II | 12/02/2024 | 12/05/2024 | SINGHA ROY & CO. | 159.46 | 0 | 0 | 30
18 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Laying of Rising Main of Hatkhola Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000037/2022-2023 | 24/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | M/S. ASIT KUMAR BISWAS | 4.14 | 3.14 | 75.9 | 100
19 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Hatkhola 2nd Tubwell site within Hatkhola Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000337/2022-2023 | 117/NACD-II | 11/01/2023 | 12/03/2023 | SOMNATH GHOSH | 5.04 | 5.04 | 99.97 | 100
20 | NADIA | Chapra | Eastern Mechanical | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under HATKHOLA W/S Scheme (Block : Chapra) Dist.- Nadia. NIET No.-36 of EE/EMD of 2022-23 (Sl. No.- 01) | Assistant Engineer | Junior Engineer | ORD/000011/2023-2024 | 1574/EMD | 24/04/2023 | 24/05/2023 | BISALAXMI ENTERPRISE | 18.99 | 18.76 | 98.79 | 100
21 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Construction for priliminary work of the approch road at Head Works site of Hatkhola Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000041/2023-2024 | 406/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | MITRA CONSTRUCTION | 0.85 | 0.82 | 97.48 | 100
22 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hatkhola) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000354/2023-2024 | 420/NACD-II | 14/03/2024 | 04/04/2024 | JADAVPUR UNIVERSITY | 5.9 | 5.9 | 100 | 100
23 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Hatkhola Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000203/2024-2025 | 1152/NACD-II | 27/08/2024 | 18/02/2026 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.21 | 0 | 0 | 66
24 | NADIA | Chapra | Nadia Arsenic Civil Division II | HATKHOLA PIPED WATER SUPPLY SCHEME | SM/10404 | New | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Fatepur, Bahadurpur and Gongra Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000348/2024-2025 | 1657/NACD-II | 30/12/2024 | 25/12/2025 | CHANDAN ROY | 149.25 | 0 | 0 | 20
Total | [13 empty] | 1079.87 | 310.8 | 28.78