## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta-I | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | New connection charges for Jitpur PHE I Tehatta Nadia. Memo no. 3004031067/Quot/03 |  |  | VCH/003375/2022-2023 |  | 21/11/2022 | 21/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0 | 0
2 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000344/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000237/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4 | NADIA | Tehatta-I | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | New connection charges for Jitpur PHE I Tehatta Nadia. Memo no. 3004031024/Quot/03 |  |  | VCH/003373/2022-2023 |  | 21/11/2022 | 21/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.91 | 0 | 0 | 0
5 | NADIA | Tehatta-I | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | New Service Connection for PH No.-I under Jitpur Tehatta Nadia |  |  | BILL/00004/2022-2023 | 90/EMD | 26/11/2022 | 26/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.91 | 0 | 0 | 0
6 | NADIA | Tehatta-I | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | New Service Connection for PH No.-II under Jitpur Tehatta Nadia |  |  | BILL/00005/2022-2023 | 89/EMD | 26/11/2022 | 26/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.2 | 0 | 0 | 0
7 | NADIA | Tehatta-I | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Supply, delivery of PCC Pole, M.s materials and electrical accessories including stringing and sagging of LTOH line to WBSEDCL for new service connection at PH-II under Jitpur W/S Scheme. |  |  | ORD/002572/2022-2023 | 1365/EMSD-III | 14/08/2022 | 13/09/2022 | S.P. ENTERPRISE (SILIGURI) | 0.39 | 0.39 | 100 | 0
8 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Jitpur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000048/2022-2023 | 15/AE-II/NACD-II | 11/04/2022 | 10/06/2022 | R.M. TRADING | 2.83 | 2.81 | 99.54 | 100
9 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Jitpur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000012/2022-2023 | 217/NACD-II | 05/04/2022 | 04/06/2022 | R.M. TRADING | 5.38 | 5.37 | 99.93 | 100
10 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jitpur and Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000018/2022-2023 | 243/NACD-II | 19/04/2022 | 18/06/2022 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 38.59 | 91.02 | 100
11 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Laying of Rising Main of Jitpur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000058/2022-2023 | 19/AE-II/NACD-II | 18/04/2022 | 18/05/2022 | SANJIT DAS | 4.98 | 4.92 | 98.8 | 85
12 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Jitpur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000196/2022-2023 | 625/NACD-II | 06/09/2022 | 26/09/2022 | RAMASISH ENTERPRISE | 4.44 | 4.44 | 100 | 100
13 | NADIA | Tehatta-I | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Jitpur W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 08) |  |  | ORD/000442/2022-2023 | 6259/EMD | 14/08/2022 | 13/09/2022 | S.P. ENTERPRISE | 9.86 | 9.85 | 99.92 | 90
14 | NADIA | Tehatta-I | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Supply delivery of PCC Pole materials and electrical accessories and installation DTR including sagging of HTOH line to WBSEDCL for new service connection at PH-I under Jitpur W/S Scheme. |  |  | ORD/002821/2022-2023 | 262/EMSD-III | 28/02/2023 | 30/03/2023 | R.M.D. TRADING | 3.47 | 3.47 | 100 | 80
15 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University (Name of PWSS Jitpur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000116/2023-2024 | 1155/NACD-II | 10/10/2023 | 31/10/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
16 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Jitpur and adjoining mouzas under Jitpur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000067/2022-2023 | 297/NACD-II | 19/05/2022 | 17/08/2022 | USHA CONSTRUCTION | 134.8 | 134.5 | 99.78 | 100
17 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Material Requisition To Resource Division |  |  | RTOR000004/2022-2023 | 408/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 44.15 | 0 | 0 | 0
18 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Jitpur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000320/2022-2023 | 84/NACD-II | 10/01/2023 | 11/03/2023 | BABLU MALLICK | 21.46 | 18.43 | 85.89 | 85
19 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 34 cum/Hour capacity for Jitpur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000169/2024-2025 | 1116/NACD-II | 16/08/2024 | 12/02/2025 | DEBAPRASAD MONDAL | 163.12 | 0 | 0 | 0
20 | NADIA | Tehatta-I | Eastern Mechanical | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Jitpur W/S Scheme (Block : Tehatta-I) Dist.- Nadia. NIET No.- 21 of EE/EMD of 2022-23 (Sl. No.- 07) | Assistant Engineer | Junior Engineer | ORD/000706/2022-2023 | 6491/EMD | 30/11/2022 | 30/12/2022 | RMD TRADING | 9.97 | 9.87 | 99.04 | 100
21 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Construction of Pathway at Jitpur 2nd tube well site within Jitpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. |  | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000035/2023-2024 | 392./AE-I/NACD-II | 31/07/2023 | 14/09/2023 | SREE GURU ENTERPRISE | 4.22 | 4.2 | 99.54 | 100
22 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Jitpur 2nd Tubwell Site within Jitpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000330/2022-2023 | 123/NACD-II | 11/01/2023 | 12/03/2023 | SOURAV & CO. | 6.62 | 6.55 | 98.9 | 85
23 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Jitpur ( Vill- Chalk Jaliapara, Khaspara) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000145/2024-2025 | 247/AE-II/NACD-II | 31/07/2024 | 15/08/2024 | SUBHASIS MOJUMDER | 0.99 | 0.99 | 99.96 | 100
24 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Providing Functional House Hold Tap Connection including supply of 15 mm dia PVC pipe of required length,Saddle piece (As required size), 15 mm dia Bib cock etc all complete including newly added pipeline (parallel or damaged line repair due to construction of drain) at Jitpur ( Vill- Chalk Jaliapara) W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000055/2024-2025 | 164_AE-II/NACD-II | 14/06/2024 | 29/06/2024 | SUPRIO MAJUMDER | 0.96 | 0.95 | 99.13 | 100
25 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000346/2024-2025 | 1627/NACD-II | 19/12/2024 | 12/06/2026 | M.R. CONSTRUCTION | 117.87 | 0 | 0 | 40
26 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Jitpur water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000376/2022-2023 | 369/NACD-II | 23/03/2023 | 21/03/2025 | B.M. ENGINEERING & CONSTRUCTION | 117.24 | 85.1 | 72.59 | 100
27 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Acceptance cum work order "Conversion of IEP to AIRP at Bhagakhali Zone-I & Jitpur Water Supply Scheme of capacity 27 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000289/2023-2024 | 196/NACD-II | 12/02/2024 | 03/04/2026 | SANDIP BISWAS | 103.73 | 0 | 0 | 100
28 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Special repair of pipe line laying with casing pipe at Jitpur W/s Scheme within Tehatta-I Block in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000399/2024-2025 | 408/AE-II/NACD-II | 31/01/2025 | 17/03/2025 | SUPRIO MAJUMDER | 0.77 | 0 | 0 | 100
29 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | JITPUR PIPED WATER SUPPLY SCHEME | SM/10405 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Jitpur and adjoining mouzas under Jitpur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. |  |  | BILL/00185/2025-2026 |  | 17/06/2025 | 17/06/2025 | USHA CONSTRUCTION | 7.21 | 0 | 0 | 0
Total | [13 empty] | 813.88 | 335.24 | 41.19