## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000338/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000231/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Construction of Boundary Wall with grill gate at Head Work site of Maniknagar Water Supply Scheme Santipur Block under Nadia Arsenic Civil Division - II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000317/2022-2023 | 81/NACD-II | 09/01/2023 | 10/03/2023 | SURAJIT KUMAR GHOSH | 14.21 | 0 | 0 | 80
4 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement for Tube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Maniknagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000030/2022-2023 | 17/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | NISHITH BANERJEE | 2.83 | 0 | 0 | 100
5 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Maniknagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000006/2022-2023 | 204/NACD-II | 05/04/2022 | 04/06/2022 | NISHITH BANERJEE | 5.37 | 0 | 0 | 100
6 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Paninala and Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000135/2022-2023 | 432/NACD-II | 07/07/2022 | 05/09/2022 | JOY HIND TUBEWELLS | 43.35 | 0 | 0 | 100
7 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Earth work in filling in ditches at Maniknagar H/W Site for development of land in connection with proposed T/W Sinking & Pump House construction at Maniknagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000174/2022-2023 | 466/NACD-II | 20/07/2022 | 09/08/2022 | SAHA ENGINEERS | 7.48 | 0 | 0 | 100
8 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Construction of Boundary Wall with grill gate at 2nd Tube well site of Maniknagar W/s Scheme of Santipur Block under Nadia Arsenic Civil Division - II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000339/2022-2023 | 119/NACD-II | 11/01/2023 | 12/03/2023 | SAHA CONSTRUCTION & GENERAL ORDER SUPPLIERS | 4.39 | 0 | 0 | 85
9 | NADIA | Santipur | Eastern Mechanical | Manik Nagar Piped W/S Scheme | SM/10407 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) & II under Maniknagar W/S Scheme (Block : Shantipur) Dist.- Nadia. NIET No.- 31 of EE/EMD of 2022-23 (Sl. No.- 05) |  |  | ORD/001785/2022-2023 | 1124/EMD | 16/03/2023 | 15/04/2023 | NITESH MANAGEMENT | 18.84 | 0 | 0 | 90
10 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of OHR locations under Santipur Block of Nadia District through Jadavpur University. (Name of PWSS: Maniknagar) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000053/2023-2024 | 858/NACD-II | 08/08/2023 | 29/08/2023 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 100
11 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Maniknagar Water Supply Scheme of Santipur Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000195/2022-2023 | 624/NACD-II | 06/09/2022 | 26/09/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 3.85 | 0 | 0 | 100
12 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 403/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 39.71 | 0 | 0 | 0
13 | NADIA | Santipur | Eastern Mechanical | Manik Nagar Piped W/S Scheme | SM/10407 | New | Electric Bill payment of WBSEDCL for the month of january 2023 |  |  | BILL/00794/2022-2023 | BP-132-22-23 | 31/01/2023 | 31/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.38 | 0 | 0 | 0
14 | NADIA | Santipur | Eastern Mechanical | Manik Nagar Piped W/S Scheme | SM/10407 | New | Electric Bill payment of WBSEDCL for the month of january 2023 |  |  | BILL/00792/2022-2023 | BP-133-22-23 | 31/01/2023 | 31/01/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.24 | 0 | 0 | 0
15 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Laying of Rising Main of Maniknagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000040/2022-2023 | 27/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | BIDYUT KUMAR | 4.69 | 0 | 0 | 100
16 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Construction of approch road at Head Works site of Maniknagar Water Supply Scheme in Shantipur Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000048/2023-2024 | 414/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | JOY HIND TUBEWELLS | 0.96 | 0 | 0 | 100
17 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Maniknagar and adjoining mouzas under Maniknagar Water Supply Scheme of Santipur Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000085/2022-2023 | 336/NACD-II | 02/06/2022 | 31/08/2022 | M/S ROY CHOWDHURY & CO. | 107.96 | 0 | 0 | 100
18 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Providing Functional House Hold Tap Connection for Swajal village at Mahatopara of Maniknagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000038/2024-2025 | 752/AE-I/NACD-II | 19/06/2024 | 04/07/2024 | S.M. ENTERPRISE | 0.91 | 0 | 0 | 100
19 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Providing Functional House Hold Tap Connection for Swajal village at Kapalipara of Maniknagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000039/2024-2025 | 753/AE-I/NACD-II | 19/06/2024 | 04/07/2024 | ACHARJEE & ASSOCIATES | 0.91 | 0 | 0 | 100
20 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Laying of D.I. pipeline with allied works at Maniknagar Piped Water Supply Scheme in Shantipur Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000012/2025-2026 | 42_AE-I/NACD-II | 29/04/2025 | 28/07/2025 | SURAJIT KUMAR GHOSH | 0.96 | 0 | 0 | 100
21 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Construction of 250 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Maniknagar water supply scheme of Sanitpur Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000283/2022-2023 | 1138/NACD-II | 16/12/2022 | 05/12/2024 | JOY HIND TUBEWELLS | 95.18 | 0 | 0 | 100
22 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Supply of flow control devices in the closed water conduit at Maniknagar PWSS in Santipur Block under Nadia Arsenic Civil Division-II, P.H.E. Dte | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000262/2024-2025 | 946/AE-I/NACD-II | 24/10/2024 | 31/10/2024 | MAKALI ENGINEERING CORPORATION | 0.77 | 0 | 0 | 100
23 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Providing Functional House Hold Tap Connection for Swajal village at Maniknagar W/s Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000040/2024-2025 | 754/AE-I/NACD-II | 19/06/2024 | 16/05/2025 | DAFADAR ENTERPRISE | 0.85 | 0 | 0 | 100
24 | NADIA | Santipur | Nadia Arsenic Civil Division II | Manik Nagar Piped W/S Scheme | SM/10407 | New | Acceptance cum work order "Construction of 35 m3/hr capacity IEP at Maniknagar PWSS in Shantipur Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000292/2023-2024 | 314/NACD-II | 01/03/2024 | 01/01/2025 | PRITI ENTERPRISE | 19.86 | 0 | 0 | 80
Total | [13 empty] | 383.5 | 0 | 0