## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000229/2022-2023 | null | 20/09/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000255/2022-2023 | null | 21/09/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
3 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000245/2022-2023 | 141 | 01/11/2022 |  | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Sikra water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000008/2022-2023 | 206/NACD-II | 05/04/2022 | 04/06/2022 | BIPLAB GUHA | 5.38 | 5.33 | 99.12 | 100
5 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Laying of Rising Main of Sikra Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000041/2022-2023 | 28/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | SAHA ENGINEERS | 3.93 | 0 | 0 | 85
6 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Sikra water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000034/2022-2023 | 21/AE-I/NACD-II | 13/04/2022 | 12/06/2022 | BIPLAB GUHA | 2.83 | 2.81 | 99.27 | 100
7 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Madhupur and Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000020/2022-2023 | 245/NACD-II | 19/04/2022 | 18/06/2022 | JOY HIND TUBEWELLS | 41.88 | 0 | 0 | 100
8 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Sikra Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000193/2022-2023 | 623/NACD-II | 06/09/2022 | 26/09/2022 | MAKALI ENGINEERING CORPORATION | 3.9 | 3.9 | 100 | 100
9 | NADIA | Chapra | Eastern Mechanical | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Electricity bill for new service connection at Shikra W/S Scheme |  |  | BILL/02152/2022-2023 | 149/PFMS/EMD | 10/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.26 | 0 | 0 | 0
10 | NADIA | Chapra | Eastern Mechanical | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Electricity bill for new service connection at Shikra under EMSD-III |  |  | BILL/02153/2022-2023 | 150/PFMS/EMD | 10/03/2023 |  | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.81 | 0 | 0 | 0
11 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Sikra 2nd Tubwell site within Sikra Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000340/2022-2023 | 121/NACD-II | 11/01/2023 | 12/03/2023 | ASHIM ENTERPRISE | 4.9 | 4.69 | 95.62 | 85
12 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Sikra Water Supply Scheme at Head Work Site site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000319/2022-2023 | 83/NACD-II | 10/01/2023 | 11/03/2023 | SANDIP KUMAR NEOGI | 14.39 | 14.33 | 99.59 | 85
13 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction for priliminary work of the approch road at Head Works site of Sikra Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000042/2023-2024 | 407/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 0.85 | 0 | 0 | 0
14 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS: Sikra) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000055/2023-2024 | 863/NACD-II | 10/08/2023 | 31/08/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
15 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction of approch road at Head Works site of Panchdara Abhaynagar Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000128/2023-2024 | 468./AE-I/NACD-II | 03/10/2023 | 18/10/2023 | AMIT KUMAR BOSE | 0.97 | 0 | 0 | 0
16 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Material Requisition To Resource Division |  |  | RTOR000013/2022-2023 | 406/NACD-II | 04/07/2022 |  | Resource Division | 32.18 | 0 | 0 | 0
17 | NADIA | Chapra | Eastern Mechanical | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.II under Sikra W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 10) | Assistant Engineer | Junior Engineer | ORD/000104/2022-2023 | 5018/EMD | 03/11/2022 | 03/12/2022 | M/S DILIP MITRA | 10.12 | 9.62 | 95.07 | 100
18 | NADIA | Chapra | Eastern Mechanical | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Supply, Delivery & Installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator (in connection with Aug. work related to FHTC) at Pump House No.I (Headworks) under Sikra W/S Scheme Dist.-Nadia. NIET No.- 16 of EE/EMD of 2022-23 (Sl. No.- 09) | Assistant Engineer | Junior Engineer | ORD/000103/2022-2023 | 5017/EMD | 03/11/2022 | 03/12/2022 | S.P. ENTERPRISE | 10.12 | 9.61 | 94.91 | 100
19 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction of 300 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Sikra water supply scheme of Chapra Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000388/2022-2023 | 395/NACD-II | 28/03/2023 | 22/03/2024 | DIAMOND ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 119.11 | 17.78 | 14.93 | 28
20 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Sikra and adjoining mouzas under Sikra Water Supply Scheme of Chapra Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000070/2022-2023 | 360/NACD-II | 15/06/2022 | 13/09/2022 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 231.09 | 180.3 | 78.02 | 90
21 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Sikra Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000188/2024-2025 | 1030/NACD-II | 02/08/2024 | 29/01/2025 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.18 | 0 | 0 | 0
22 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Rendering consultancy services for Structural Health Monitoring and Report preparation of site locations (OHR Specially) under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Sikra) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000356/2023-2024 | 434/NACD-II | 15/03/2024 | 05/04/2024 | JADAVPUR UNIVERSITY | 5.9 | 2.95 | 50 | 100
23 | NADIA | Chapra | Nadia Arsenic Civil Division II | SIKRA PIPED WATER SUPPLY SCHEME | SM/10410 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 45 cum/Hour capacity for Hatkhola Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000203/2024-2025 | 1152/NACD-II | 27/08/2024 | 23/02/2025 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 176.21 | 0 | 0 | 0
Total | [13 empty] | 853.82 | 256.08 | 29.99