## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000340/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
2 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | New connection charges for Swaruppur PHE I Tehatta Nadia. Memo no. 3004031081/Quot/03 |  |  | VCH/003367/2022-2023 |  | 21/11/2022 | 21/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0 | 0
3 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | New Service Connection for Pump House -I under Suruppur W/S Scheme at Tehatta Nadia |  |  | BILL/00002/2022-2023 | 93/EMD | 26/11/2022 | 26/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0 | 0
4 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | New connection charges for Swaruppur PHE I Tehatta Nadia. Memo no. 3004031086/Quot/03 |  |  | VCH/003371/2022-2023 |  | 21/11/2022 | 21/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.23 | 0 | 0 | 0
5 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000233/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
6 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New |  |  |  | BILL/00001/2022-2023 |  | 21/11/2022 | 21/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.1 | 0 | 0 | 0
7 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | New service connection charges at P.H No. II under Suruppur Tehatta Nadia |  |  | BILL/00003/2022-2023 | 94/EMD | 26/11/2022 | 26/11/2022 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.23 | 0 | 0 | 0
8 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Suruppur 2nd Tubewell Site within Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000335/2022-2023 | 129/NACD-II | 11/01/2023 | 12/03/2023 | SANJIT DAS | 5.83 | 5.76 | 98.67 | 80
9 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Supply delivery of PCC pole, M.s and electrical accessories including stringing of LTOH line to wbsedcl for new service connection at PH-II under Suruppur W/S Scheme. under EMSD-III |  |  | ORD/002409/2022-2023 | 1366/EMSD-III | 14/08/2022 | 13/09/2022 | DEBJYOTI BASU | 0.72 | 0.72 | 100 | 0
10 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Construction of approch road at Head Works site of Suruppur Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000129/2023-2024 | 467./AE-I/NACD-II | 03/10/2023 | 18/10/2023 | MAJUMDER SYNDICATE | 0.97 | 0 | 0 | 0
11 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Suruppur and adjoining mouzas under Suruppur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000068/2022-2023 | 302/NACD-II | 20/05/2022 | 18/08/2022 | JOY GOPAL GUPTI | 104.51 | 104.4 | 99.9 | 85
12 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Suruppur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000011/2022-2023 | 216/NACD-II | 05/04/2022 | 04/06/2022 | TAPAN SAHA | 5.38 | 5.32 | 98.92 | 100
13 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Sinking of 4 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, ( 250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jitpur and Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000018/2022-2023 | 243/NACD-II | 19/04/2022 | 18/06/2022 | B.M. ENGINEERING & CONSTRUCTION | 42.4 | 0 | 0 | 100
14 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Suruppur water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000047/2022-2023 | 14/AE-II/NACD-II | 11/04/2022 | 10/06/2022 | TAPAN SAHA | 2.83 | 2.81 | 99.34 | 100
15 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Suruppur Water Supply Scheme of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000201/2022-2023 | 630/NACD-II | 06/09/2022 | 26/09/2022 | MAKALI ENGINEERING CORPORATION | 3.42 | 3.42 | 100 | 100
16 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Suruppur W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No.- 21 OF EE/EMD OF 2022-23 (Sl. No.- 12) |  |  | ORD/000702/2022-2023 | 6490/EMD | 30/11/2022 | 30/12/2022 | DEBJYOTI BASU | 9.96 | 9.91 | 99.54 | 87
17 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 410/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 35.99 | 0 | 0 | 0
18 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Suruppur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000326/2022-2023 | 90/NACD-II | 10/01/2023 | 27/08/2025 | PARTHA DAS | 17.71 | 14.12 | 79.74 | 85
19 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Construction of Toilet with sanitary and water supply arrangement at Suruppur 2nd tube well site within Suruppur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000157/2024-2025 | 168/AE-II/NACD-II | 14/06/2024 | 29/06/2024 | D.K.CONSTRUCTION | 0.97 | 0 | 0 | 0
20 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Laying of Rising Main of Suruppur Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000063/2022-2023 | 25/AE-II/NACD-II | 18/04/2022 | 18/05/2022 | BASUDEB SAHA | 4.41 | 4.39 | 99.74 | 100
21 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Suruppur W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000432/2022-2023 | 6257/EMD | 19/11/2022 | 19/12/2022 | M/S DILIP MITRA | 9.96 | 9.46 | 94.93 | 80
22 | NADIA | Tehatta-I | Eastern Mechanical | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Supply, delivery of PCC pole,M.S materials and Electricalaccessories and Installation DTR including stringing andSagging of HTOH line to WBSEDCL for newconnection at Pump House-1 under Suruppur water supplyscheme,under EMSD-III,PHE Dte,Nadia. |  |  | ORD/003025/2022-2023 | 264SD-III | 28/02/2023 | 30/03/2023 | M/S DILIP MITRA | 3.71 | 3.71 | 100 | 100
23 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Construction of 250 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Suruppur water supply scheme of Tehatta-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000352/2022-2023 | 160/NACD-II | 17/01/2023 | 19/05/2025 | JOY HIND TUBEWELLS | 94.17 | 33.17 | 35.22 | 10
24 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Manoharpur & Suruppur water supply scheme under Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000400/2024-2025 | 135/NACD-II | 09/01/2025 | 22/08/2025 | NISHITH BANERJEE | 32.78 | 0 | 0 | 50
25 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | SURUPPUR PIPED WATER SUPPLY SCHEME | SM/10411 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 22 cum/Hour capacity for Suruppur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000202/2024-2025 | 1236/NACD-II | 10/09/2024 | 09/03/2025 | SINGHA ROY & CO. | 146.67 | 0 | 0 | 0
Total | [13 empty] | 526.18 | 197.18 | 37.47