## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Sinking of 3 nos. of 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head work site and 2nd Tube Well site and 3rd Tubewell site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Panchdara Abhaynagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000134/2022-2023 | 431/NACD-II | 07/07/2022 | 21/08/2022 | JOY HIND TUBEWELLS | 32.55 | 0 | 0 | 100
2 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Earth work in filling in ditches at Panchdara Abhaynagar H/W Site for development of land in connection with proposed T/W Sinking & Pump House construction at Panchdara Abhaynagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000125/2022-2023 | 61/AE-II/NACD-II | 28/06/2022 | 18/07/2022 | VAI ENTERPRISE | 4.75 | 0 | 0 | 100
3 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000234/2022-2023 |  | 20/09/2022 | 20/09/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
4 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | SUBMISSION OF 2ND INSTALLMENT FEES FOR 30 NOS OF APPLICATION (STW) FOR OBTAINING PERMIT FOR DOMESTIC DRINKING WATER SUPPLY PURPOSES AFTER ACCEPTANCE FROM 42ND DLA MEETING HELD ON 22/06/22 |  |  | VCH/000341/2022-2023 | 141 | 01/11/2022 | 01/11/2022 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
5 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar 3rd Tubewell Site within Panchdhara Abhaynaga Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000336/2022-2023 | 128/NACD-II | 11/01/2023 | 12/03/2023 | JOY GURU ENTERPRISE | 4.5 | 0 | 0 | 90
6 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Construction of 600 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap at Panchdara Abhaynagar water supply scheme of Tehatta-II Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II |  | ORD/000012/2023-2024 | 540/NACD-II | 10/05/2023 | 10/05/2024 | AMIT KUMAR BOSE | 155.99 | 0 | 0 | 0
7 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Construction of pumphouse cum chlorine room with sanitary and water supply arrangement at Head Work Site according to departmental drawing (Size 5.90 mtr x 4.10 mtr) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000042/2022-2023 | 256/NACD-II | 25/04/2022 | 24/06/2022 | PARTHA DAS | 5.37 | 0 | 0 | 100
8 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-2 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000043/2022-2023 | 10/AE-II/NACD-II | 11/04/2022 | 10/06/2022 | PARTHA DAS | 2.83 | 0 | 0 | 100
9 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Construction of Pumphouse cum chlorine room without sanitary and water supply arrangement forTube Well No-3 according to departmental drawing (Size 4.10 mtr x 3.50 mtr ) of Panchdara Abhaynagar water supply scheme under Nadia Arsenic Civil Division-II , PHE Dte. Dist -Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000044/2022-2023 | 11/AE-II/NACD-II | 11/04/2022 | 10/06/2022 | PARTHA DAS | 2.83 | 0 | 0 | 100
10 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Supply and delivery of CIDF sluice valve (Special type) PW-1.00 of different dia make with CI double flanged non rusting spindle sluice valves including carriage at head Work site of Panchdara Abhaynagar Water Supply Scheme of Tehatta-II Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000200/2022-2023 | 629/NACD-II | 06/09/2022 | 26/09/2022 | RAMASISH ENTERPRISE | 6.88 | 0 | 0 | 100
11 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Material Requisition To Resource Division |  |  | RTOR000017/2022-2023 | 416/NACD-II | 05/07/2022 | 05/07/2022 | Resource Division | 3 | 0 | 0 | 0
12 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Material Requisition To Resource Division |  |  | RTOR000015/2022-2023 | 400/NACD-II | 04/07/2022 | 04/07/2022 | Resource Division | 40.34 | 0 | 0 | 0
13 | NADIA | Tehatta-II | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Electricity bill for new service connection at Panchdhara Abhaynagar |  |  | BILL/02149/2022-2023 | 148/PFMS/EMD | 10/03/2023 | 10/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0 | 0
14 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00086/2022-2023 | 235/2 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
15 | NADIA | Tehatta-II | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Electricity bill for new service connection at panchdhara abhaynagar |  |  | BILL/02147/2022-2023 | 146/PFMS/EMD | 10/03/2023 | 10/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.71 | 0 | 0 | 0
16 | NADIA | Tehatta-II | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Shifting of 1 Nos. PCC pole along with LTOH line for obstruction in construction work by PHE dept. |  |  | BILL/01759/2023-2024 | BP-91-23-24 | 24/07/2023 | 24/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.12 | 0 | 0 | 0
17 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Restoration of road flank of Plassey Betai road from 12.50 Kmp to 16.50 Kmp at Panchdhara Avaynagar w/s. scheme Block Tehatta-II under Nadia Arsenic Civil Division II, PHE Dte against estimate order No. 1450 DT. 21.08.2023 & this office memo no. 890/ NACD-II dt. 21.08.2023 |  |  | BILL/00333/2023-2024 |  | 07/09/2023 | 07/09/2023 | EXECUTIVE ENGINEER,NADIA HIGHWAY DIVISION NO-I, P.W.(ROADS) DIRECTORATE | 39.9 | 0 | 0 | 0
18 | NADIA | Tehatta-II | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Electricity bill for new service connection at panchdhara abhaynagar |  |  | BILL/02148/2022-2023 | 147/PFMS/EMD | 10/03/2023 | 10/03/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.52 | 0 | 0 | 0
19 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00013/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
20 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Regarding restoration of flank of Plassey Betai Road from 12.50 Kmp to 16.50 Kmp |  |  | BILL/00356/2023-2024 | 152 | 08/09/2023 | 08/09/2023 | EXECUTIVE ENGINEER,NADIA HIGHWAY DIVISION NO-I, P.W.(ROADS) DIRECTORATE | 20 | 0 | 0 | 0
21 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Laying of Distribution system including providing Functional House hold Tap connection (FHTC) for Panchdara Abhynagar and adjoining mouzas under Panchdara Abhynagar Water Supply Scheme of Tehatta-II Block, under Nadia Arsenic Civil Division II P.H.E. Dte., Dist - Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000173/2022-2023 | 460/NACD-II | 18/07/2022 | 16/10/2022 | GHOSH BROTHERS | 520.23 | 0 | 0 | 80
22 | NADIA | Tehatta-II | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.III under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 15) | Assistant Engineer | Junior Engineer | ORD/000424/2022-2023 | 6254/EMD | 19/11/2022 | 19/12/2022 | HARA PROSAD DAS | 10 | 0 | 0 | 70
23 | NADIA | Tehatta-II | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.II under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 14) | Assistant Engineer | Junior Engineer | ORD/000427/2022-2023 | 6255/EMD | 19/11/2022 | 19/12/2022 | MASSK ENGINEERING WORKS | 9.96 | 0 | 0 | 80
24 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar 2nd Tubewell Site within Panchdhara Abhaynaga Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000334/2022-2023 | 127/NACD-II | 11/01/2023 | 12/03/2023 | VAI ENTERPRISE | 5.7 | 0 | 0 | 90
25 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Panchdhara Abhaynagar Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000324/2022-2023 | 88/NACD-II | 10/01/2023 | 11/03/2023 | SHYAM SUNDAR SAHA | 15.89 | 0 | 0 | 90
26 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 113 cum/Hour capacity for Panchdara Abhaynagar Water Supply Scheme within Tehatta-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000189/2024-2025 | 1031/NACD-II | 02/08/2024 | 29/01/2025 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 282.81 | 0 | 0 | 0
27 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-II Block of Nadia District through Jadavpur University. (Name of PWSS Panchdhara Abhynagar) |  |  | ORD/000175/2023-2024 | 1263/NACD-II | 09/11/2023 | 30/11/2023 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 100
28 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Material Requisition To Resource Division |  |  | RTOR000007/2023-2024 | 80/NACD-II | 15/01/2024 | 15/01/2024 | Resource Division | 13.52 | 0 | 0 | 0
29 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Laying of Rising Main of Panchdara Abhyanagar Water Supply Scheme and other necessary allied works in this connection under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000062/2022-2023 | 23/AE-II/NACD-II | 18/04/2022 | 22/07/2025 | PARTHA DAS | 4.96 | 0 | 0 | 100
30 | NADIA | Tehatta-II | Eastern Mechanical | PANCHDARA ABHYNAGAR PIPED W/S SCHEME | SM/10613 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I (Headworks) under Panchdara W/S Scheme (Block : Tehatta-II) Dist.- Nadia. NIET No. 21 of EE/EMD of 2022-23 (Sl. No.- 13) | Assistant Engineer | Junior Engineer | ORD/000429/2022-2023 | 6256/EMD | 19/11/2022 | 19/12/2022 | BISALAXMI ENTERPRISE | 9.99 | 0 | 0 | 100
Total | [13 empty] | 1213.34 | 0 | 0