## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Tarinipur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000282/2022-2023 | 1137/NACD-II | 16/12/2022 | 15/01/2023 | AUXILIARY TUBE WELL DRILLERS | 21.03 | 19.17 | 91.19 | 100
2 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 1090/NACD-II | 09/12/2022 | 09/12/2022 | Resource Division | 63.84 | 0 | 0 | 0
3 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Taranipur Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000393/2022-2023 | 402/NACD-II | 28/03/2023 | 17/09/2025 | B.M. ENGINEERING & CONSTRUCTION | 345.19 | 172.16 | 49.87 | 43
4 | NADIA | Tehatta-I | Eastern Mechanical | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at TARINIPUR Piped Water Supply Scheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001119/2023-2024 | 4707/EMD | 04/08/2023 | 03/09/2023 | HARA PROSAD DAS | 51.92 | 0 | 0 | 0
5 | NADIA | Tehatta-I | Eastern Mechanical | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under TARINIPUR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 08) | Assistant Engineer | Junior Engineer | ORD/000028/2023-2024 | 1607/EMD | 26/04/2023 | 01/01/2025 | SHIVAM ENTERPRISE | 18.99 | 18.74 | 98.64 | 70
6 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Construction of approch road at Head Works site of Taranipur Water Supply Scheme in Tehatta-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000046/2023-2024 | 411/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | B.M. ENGINEERING & CONSTRUCTION | 0.97 | 0 | 0 | 100
7 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Taranipur water supply scheme under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000143/2023-2024 | 1386/NACD-II | 12/12/2023 | 26/01/2024 | CHINMOY BISWAS | 11.33 | 11.26 | 99.41 | 100
8 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Material Requisition To Resource Division |  |  | RTOR000026/2022-2023 | 379/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 11.38 | 0 | 0 | 0
9 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00094/2022-2023 | 235/9 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
10 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00021/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
11 | NADIA | Tehatta-I | Eastern Mechanical | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | New Service Connection under Ae, EMSD-III, Taranipur PH_I |  |  | BILL/01872/2023-2024 | BP-107-23-24 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.78 | 0 | 0 | 0
12 | NADIA | Tehatta-I | Eastern Mechanical | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | New Service Connection under Ae, EMSD-III, Taranipur PH_I |  |  | BILL/01871/2023-2024 | BP-108-23-24 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.34 | 0 | 0 | 0
13 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Additional instrumentation with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Taranipur Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000323/2024-2025 | 1521/NACD-II | 26/11/2024 | 26/12/2024 | NEER UDYOG | 31.56 | 0 | 0 | 0
14 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Laying of distribution system including providing FHTC at left out households for Thanarpara Zone-III (Vill- Char Gaurbhanga, Falia, Yusufpur) , Jitpur , Taranipur & Dhopahat W/S Scheme in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000346/2024-2025 | 1627/NACD-II | 19/12/2024 | 12/06/2026 | M.R. CONSTRUCTION | 117.87 | 0 | 0 | 40
15 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Conversion of IEP to AIRP at Patharghata Water Supply Scheme of capacity 96 Cu.m/hr in Tehatta - I Block under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000295/2024-2025 | 1396/NACD-II | 22/10/2024 | 17/10/2025 | JOY HIND TUBEWELLS | 258.38 | 0 | 0 | 0
16 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Acceptance cum work order "Construction of 50 m3/hr capacity IEP at Taranipur PWSS in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000294/2023-2024 | 324/NACD-II | 04/03/2024 | 04/05/2024 | NEER UDYOG | 23.2 | 0 | 0 | 0
17 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Acceptance cum work order "Conversion of IEP to AIRP at Mobarakpur, Binodnagar & Taranipur Water Supply Scheme of capacity 93 Cu.m/hr in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000282/2023-2024 | 152/NACD-II | 02/02/2024 | 17/09/2026 | B.M. ENGINEERING & CONSTRUCTION | 241.81 | 0 | 0 | 0
18 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-III & Taranipur Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000338/2024-2025 | 1398/NACD-II | 22/10/2024 | 20/01/2025 | PAPAN ROY | 16.66 | 12.85 | 77.08 | 60
19 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Construction and installation of MANIFOLD with dedicated Pipe Line including laying of distribution network for left out FHTC under Bagakhali Zone-I and Bagakhali Zone-II Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000325/2024-2025 | 1562/NACD-II | 05/12/2024 | 30/11/2025 | DEBASIS SAMADDAR | 157.57 | 0 | 0 | 40
20 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Taranipur water supply scheme under Tehatta- I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000228/2023-2024 | 165/NACD-II | 07/02/2024 | 07/04/2024 | M/S K.P. CONSTRUCTION | 32.46 | 28.03 | 86.33 | 100
21 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Incorporation of the system of adsorption by Inorganic sustances for multivalent metalloid expulsion for improving potability in coordination with IS 10500 With latest edition at Taranipur Piped Water Supply Scheme in Tehatta-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000378/2024-2025 | 47/NACD-II | 10/01/2025 | 09/02/2025 | NEER UDYOG | 29.92 | 0 | 0 | 0
22 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | TARANIPUR PIPED WATER SUPPLY SCHEME | SM/11964 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000001/2025-2026 | 428/NACD-II | 07/04/2025 | 04/10/2025 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 0 | 30
Total | [13 empty] | 1460.5 | 262.2 | 17.95