## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Material Requisition To Resource Division |  |  | RTOR000021/2022-2023 | 1091/NACD-II | 09/12/2022 | 09/12/2022 | Resource Division | 27.83 | 0 | 0 | 0
2 | NADIA | Tehatta-I | Eastern Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at RAJAPUR Piped Water Supply Scheme, Block: Tehatta-I, Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001123/2023-2024 | 4711/EMD | 04/08/2023 | 03/09/2023 | INDIA ENTERPRISE | 40.8 | 0 | 0 | 0
3 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Construction for priliminary work of the approch road at Head Works site of Rajapur Water Supply Scheme in Tehatta-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000045/2023-2024 | 410/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | JOY HIND TUBEWELLS | 0.97 | 0 | 0 | 0
4 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Rajapur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000281/2022-2023 | 1136/NACD-II | 16/12/2022 | 15/01/2023 | AUXILIARY TUBE WELL DRILLERS | 21.03 | 0 | 0 | 100
5 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Tehatta-I Block of Nadia District through Jadavpur University (Name of PWSS Rajapur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000115/2023-2024 | 1154/NACD-II | 10/10/2023 | 31/10/2023 | JADAVPUR UNIVERSITY | 4.78 | 0 | 0 | 100
6 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 376/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 12.69 | 0 | 0 | 0
7 | NADIA | Tehatta-I | Eastern Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | New Service Connection at Pump House-II under Rajapur Water Supply Scheme |  |  | BILL/01879/2023-2024 | BP-110-23-24 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.66 | 0 | 0 | 0
8 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00093/2022-2023 | 235/8 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
9 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00020/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
10 | NADIA | Tehatta-I | Eastern Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | New Service Connection at Pump House-I under Rajapur Water Supply Scheme |  |  | BILL/01878/2023-2024 | BP-111-23-24 | 02/08/2023 | 02/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.88 | 0 | 0 | 0
11 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Rajapur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000100/2023-2024 | 1132/NACD-II | 09/10/2023 | 23/11/2023 | SANJIT DAS | 11.34 | 0 | 0 | 90
12 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Renovation of Arsenic cum Iron treatment Plant of Khanjipur PWSS (Capacity- 21 m3/hr) and ancillary works of Rajapur W/s Scheme at Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000340/2023-2024 | 38/NACD-II | 09/01/2024 | 09/03/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 61.75 | 0 | 0 | 70
13 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 74/NACD-II | 15/01/2024 | 15/01/2024 | Resource Division | 12.69 | 0 | 0 | 0
14 | NADIA | Tehatta-I | Eastern Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Supplimentary Quotation for new service connection against Application No-3004365000 for NSC at Rajapur P.H-II w/s scheme |  |  | BILL/00070/2024-2025 | BP-07-24-25 | 23/04/2024 | 23/04/2024 | W.B.S.E.D.C.L (GROUP NAZIRPUR C.C.C) | 0.74 | 0 | 0 | 0
15 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 350 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Rajapur Water Supply Scheme and other necessary allied works in this connection of Tehatta-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000392/2022-2023 | 401/NACD-II | 28/03/2023 | 26/03/2026 | JOY HIND TUBEWELLS | 442.76 | 0 | 0 | 40
16 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Acceptance cum work order "Conversion of IEP to AIRP at Bahadurpur & Rajapur Water Supply Scheme of capacity 16 Cu.m/hr under in Tehatta-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000308/2023-2024 | 424/NACD-II | 15/03/2024 | 09/05/2025 | CHAKRABORTTI ENTERPRISE | 92.52 | 0 | 0 | 70
17 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 53.24 cum/Hour capacity for Rajapur Water Supply Scheme within Tehatta-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000261/2024-2025 | 1399/NACD-II | 23/10/2024 | 18/10/2025 | JOY HIND TUBEWELLS | 185.73 | 0 | 0 | 0
18 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Acceptance cum work order "Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Rajapur water supply scheme under Tehatta- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000332/2023-2024 | 408/NACD-II | 13/03/2024 | 22/01/2025 | DEBASIS SAMADDAR | 26.21 | 0 | 0 | 1
19 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000001/2025-2026 | 428/NACD-II | 07/04/2025 | 04/10/2025 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 0 | 30
20 | NADIA | Tehatta-I | Nadia Arsenic Civil Division II | RAJAPUR PIPED WATER SUPPLY SCHEME | SM/11966 | New | Laying of distribution system including providing FHTC at left out households for Bahadurpur, Khaspu, Dhopahat and Rajapur W/s Scheme and restoration of the damaged portion of roads in Nadia District under Nadia Arsenic Civil Division-II, P.H.E. Dte and Brittihuda W/S Scheme & Barnia W/S Scheme included. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000080/2025-2026 | 736/NACD-II | 18/06/2025 | 16/09/2025 | JOY HIND TUBEWELLS | 186.42 | 0 | 0 | 40
Total | [13 empty] | 1163.1 | 0 | 0