## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 1087/NACD-II | 09/12/2022 | 09/12/2022 | Resource Division | 0.44 | 0 | 0 | 0
2 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Sinking of 2 nos. 200 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (200 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Chakdignagar Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000276/2022-2023 | 1131/NACD-II | 16/12/2022 | 15/01/2023 | JOY HIND TUBEWELLS | 20.39 | 19.8 | 97.14 | 100
3 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 380/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 2.85 | 0 | 0 | 0
4 | NADIA | Krishnagar-I | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | NEW SERVICE CONNECTION CHARGES FOR WBSEDCL UNDER CHAKDINAGAR PHE-II P.O. KALIRHAT |  |  | BILL/02540/2023-2024 | BP-149-23-24 | 24/08/2023 | 24/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0 | 0
5 | NADIA | Krishnagar-I | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | New service connection for Chakdinagar PH-I P.O.- Kalirhat |  |  | BILL/04043/2023-2024 | BP-248-23-24 | 20/12/2023 | 20/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.87 | 0 | 0 | 0
6 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00089/2022-2023 | 235/4 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
7 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00016/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
8 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Chakdignagar water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000201/2023-2024 | 94/NACD-II | 22/01/2024 | 16/01/2025 | ZOOM CONSTRUCTION & INTERIO | 20.02 | 7.32 | 36.57 | 90
9 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Acceptance cum work order "Construction of 30 m3/hr capacity IEP at Chakdignagar PWSS in Krishnanagar-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000334/2023-2024 | 338/NACD-II | 05/03/2024 | 05/05/2024 | GHOSH & CO. | 19.79 | 0 | 0 | 0
10 | NADIA | Krishnagar-I | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in Chakdignagar PWSS, Block- Krishnagar-I, District- Nadia. Under EMD PHE Dte | Assistant Engineer |  | ORD/003257/2023-2024 | 810./EMD | 11/03/2024 | 10/04/2024 | M/S. G.P. ENTERPRISE | 9.66 | 0 | 0 | 0
11 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Additional instrumentation with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Chakdignagar Piped Water Supply Scheme in Krishnagar-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000315/2024-2025 | 1512/NACD-II | 25/11/2024 | 25/12/2024 | SANDIP BISWAS | 20.55 | 0 | 0 | 0
12 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Chakdignagar water supply scheme under Krishnanagar- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000134/2023-2024 | 1252/NACD-II | 08/11/2023 | 23/12/2023 | SHYAM SUNDAR SAHA | 26.42 | 25.76 | 97.48 | 100
13 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Providing 1 no. Guard at Chakdignagar Head work Water Supply Scheme for guarding of various Departmental materials under Nadia Arsenic Civil Division-II,P.H.E. Dte.[Period of work :01/02/2024 to 31/05/2024] | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000230/2023-2024 | 600/AE-I/NACD-II | 31/01/2024 | 31/05/2024 | M/S S.K. CONSTRUCTION | 0.96 | 0.69 | 71.76 | 100
14 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 78/NACD-II | 15/01/2024 | 15/01/2024 | Resource Division | 2.85 | 0 | 0 | 0
15 | NADIA | Krishnagar-I | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Load enhancement charges and security deposit for Chakdignagar PWSS PH-II |  |  | BILL/02155/2024-2025 | BP-173-24-25 | 05/12/2024 | 05/12/2024 | W.B.S.E.D.C.L (GROUP KRISHNAGAR ROAD STATION C.C.C) | 3.06 | 0 | 0 | 0
16 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Provisioning of automation as well as adsorption technology with augmentation of backwashing system with appropriate wattage including recirculation in compliance with 12699: 1989 as well as reaffirmation there into for contamination removal of various valent systems at Chak Dignagar corresponding Piped Water Supply Scheme in Krishnagar I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000401/2024-2025 | 41/NACD-II | 10/01/2025 | 09/02/2025 | SANDIP BISWAS | 39.26 | 0 | 0 | 0
17 | NADIA | Krishnagar-I | Eastern Mechanical | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Chakdignagar ground water based water supply scheme under Block_ Karimpur-I Dist. - Nadia under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No. 7) | Assistant Engineer | Junior Engineer | ORD/003198/2023-2024 | 948/EMD | 18/03/2024 | 02/05/2025 | KARTICK BAL | 22.35 | 0 | 0 | 90
18 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | CHAKDIGNAGAR PIPED WATER SUPPLY SCHEME | SM/12419 | New | Laying of Distraibution system including providing Functional House Hold Tap Connection (FHTC) for Chakdignagar and adjoining mouzas under Chakdignagar W/s Scheme of Krishnagar-I Block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist-Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000342/2022-2023 | 152/NACD-II | 17/01/2023 | 03/09/2025 | JOY GOPAL GUPTI | 36.69 | 29.93 | 81.58 | 100
Total | [13 empty] | 233.14 | 83.5 | 35.82