## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Material Requisition To Resource Division |  |  | RTOR000025/2022-2023 | 1088/NACD-II | 09/12/2022 | 09/12/2022 | Resource Division | 0.55 | 0 | 0 | 0
2 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Sinking of 2 nos. 200 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (200 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000277/2022-2023 | 1132/NACD-II | 16/12/2022 | 15/01/2023 | GENUINE | 20.4 | 16.66 | 81.64 | 100
3 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-II Block of Nadia District through Jadavpur University. (Name of PWSS Manoharpur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000087/2023-2024 | 916/NACD-II | 01/09/2023 | 22/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
4 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 378/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 3.14 | 0 | 0 | 0
5 | NADIA | Karimpur-II | Eastern Mechanical | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | New Service connection at PH-I under Manoharpur W/S scheme. |  |  | BILL/02373/2023-2024 | BP-136-23-24 | 16/08/2023 | 16/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.46 | 0 | 0 | 0
6 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00017/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
7 | NADIA | Karimpur-II | Eastern Mechanical | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | New Service connection at PH-II under Manoharpur W/S scheme. |  |  | BILL/02375/2023-2024 | BP-137-23-24 | 16/08/2023 | 16/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.48 | 0 | 0 | 0
8 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00090/2022-2023 | 235/5 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
9 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Laying of Distraibution system including providing Functional House Hold Tap Connection (FHTC) for Manoharpur and adjoining mouzas under Manoharpur W/s Scheme of Karimpur-II Block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist-Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000343/2022-2023 | 153/NACD-II | 17/01/2023 | 16/02/2023 | NATIONAL CONSTRUCTION | 40.06 | 30.43 | 75.96 | 75
10 | NADIA | Karimpur-II | Eastern Mechanical | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in MANOHARPUR PWSS, Block_ KARIMPUR-II, District- Nadia. Under EMD PHE Dte. 2024_PHED_664112_4 | Assistant Engineer |  | ORD/003004/2023-2024 | 926/EMD | 15/03/2024 | 14/04/2024 | DIPALI CONSTRUCTION | 9.65 | 0 | 0 | 0
11 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Manoharpur water supply scheme under Nadia Arsenic Civil Division-II, PHE Dte. Dist- Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000141/2023-2024 | 1363/NACD-II | 08/12/2023 | 22/01/2024 | EVEREST CONSULTANT SERVICES. | 20.96 | 18.27 | 87.18 | 80
12 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Sinking of 3 nos. Tube Well at H/W site ,2nd and 3rd T/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-III & Manoharpur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000136/2024-2025 | 1047/NACD-II | 07/08/2024 | 05/11/2024 | B.M. ENGINEERING & CONSTRUCTION | 34.68 | 17.34 | 50 | 100
13 | NADIA | Karimpur-II | Eastern Mechanical | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sinkinng Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Manoharpur ground water based water supply scheme under Block_ Karimpur-II Dist. - Nadia under EMD, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/003362/2023-2024 | 865/EMD | 14/03/2024 | 13/04/2024 | CINZANO | 22.25 | 0 | 0 | 85
14 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Manoharpur & Suruppur water supply scheme under Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000400/2024-2025 | 135/NACD-II | 09/01/2025 | 22/08/2025 | NISHITH BANERJEE | 32.78 | 0 | 0 | 50
15 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Construction of 75 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Thanarpara Zone-III Water Supply Scheme in Karimpur-II block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000322/2024-2025 | 1207/NACD-II | 04/09/2024 | 03/03/2025 | SINGHA ROY & CO. | 215.53 | 0 | 0 | 0
16 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Acceptance cum work order "Construction of 30 m3/hr capacity IEP at Manoharpur PWSS in Karimpur-II Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000293/2023-2024 | 399/NACD-II | 13/03/2024 | 04/11/2025 | MASUM CONSTRUCTION | 19.23 | 0 | 0 | 75
17 | NADIA | Karimpur-II | Nadia Arsenic Civil Division II | MANOHARPUR PIPED WATER SUPPLY SCHEME | SM/12421 | New | Construction of Boundary wall with Grill Gate and Barbed wire fencing at Thanapara Zone-II Water Supply Scheme Head Work site under Nadia Arsenic Civil Division-II PHE Dte. & including Binodnagar PWSS,Manoharpur PWSS, Rajapur PWSS & Taranipur PWSS. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000001/2025-2026 | 428/NACD-II | 07/04/2025 | 04/10/2025 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 19.28 | 0 | 0 | 30
Total | [13 empty] | 453.24 | 87.47 | 19.3