## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Material Requisition To Resource Division |  |  | RTOR000022/2022-2023 | 1086/NACD-II | 09/12/2022 | 09/12/2022 | Resource Division | 16.04 | 0 | 0 | 0
2 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 100 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Jayrampur PWSS of Karimpur-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000391/2022-2023 | 400/NACD-II | 28/03/2023 | 28/03/2024 | M/S. R.M. CONSTRUCTION | 173.44 | 0 | 0 | 10
3 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Construction of approch road at Head Works site of Jayrampur Water Supply Scheme in Karimpur-I Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio |  | ORD/000044/2023-2024 | 409/AE-I/NACD-II | 08/08/2023 | 23/08/2023 | BASUDEB SAHA | 0.97 | 0 | 0 | 0
4 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Jayrampur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000280/2022-2023 | 1135/NACD-II | 16/12/2022 | 15/01/2023 | JOY HIND TUBEWELLS | 21.46 | 20.09 | 93.63 | 100
5 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Karimpur-I Block of Nadia District through Jadavpur University. (Name of PWSS Jayrampur) |  |  | ORD/000163/2023-2024 | 1289/NACD-II | 21/11/2023 | 12/12/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
6 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 381/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 5.57 | 0 | 0 | 0
7 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00018/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
8 | NADIA | Karimpur-I | Eastern Mechanical | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | New Service connection at PH-I under Jayrampur W/S scheme. |  |  | BILL/02376/2023-2024 | BP-138-23-24 | 16/08/2023 | 16/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.52 | 0 | 0 | 0
9 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00091/2022-2023 | 235/6 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.01 | 0 | 0 | 0
10 | NADIA | Karimpur-I | Eastern Mechanical | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | New Service connection at PH-II under Jayrampur W/S scheme. |  |  | BILL/02378/2023-2024 | BP-138-23-24 | 16/08/2023 | 16/08/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.08 | 0 | 0 | 0
11 | NADIA | Karimpur-I | Eastern Mechanical | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Supply, delivery, installation and commissioning of electro-mechanical accessories in connection with installation of Clear Water Pumping machinery in JAYRAMPUR PWSS, Block_ KARIMPUR-I, District- Nadia. Under EMD PHE Dte. | Assistant Engineer |  | ORD/002822/2023-2024 | 812/EMD | 11/03/2024 | 10/04/2024 | STANDARD ENGINEERING | 9.68 | 0 | 0 | 0
12 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Acceptance cum work order "Construction of 25 m3/hr capacity IEP at Jayrampur PWSS in Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000331/2023-2024 | 313/NACD-II | 01/03/2024 | 01/05/2024 | HYDROTECH ASSOCIATES | 18.68 | 0 | 0 | 0
13 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Jayrampur water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000133/2023-2024 | 1251/NACD-II | 08/11/2023 | 23/12/2023 | BASUDEB SAHA | 11.38 | 11.32 | 99.46 | 100
14 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Sinking of Tube Well at H/W site of 300 mm X 200 mm dia, 150 mtr deep by Direct Rotary Method with UPVC pipe (CD) & Fibre Glass Strainer, ( 300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Thanapara Zone-II & Jayrampur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000408/2024-2025 | 149/NACD-II | 04/02/2025 | 21/03/2025 | MANISHIKA CONSTRUCTION | 11.56 | 0 | 0 | 0
15 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Acceptance cum work order "Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Jayrampur water supply scheme under Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000333/2023-2024 | 409/NACD-II | 13/03/2024 | 04/09/2025 | JAYBRATO HALDER | 33.53 | 0 | 0 | 70
16 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Acceptance cum work order "Conversion of IEP to AIRP at Joyghata Water Supply Scheme of capacity 64 Cu.m/hr under Krishnaganj Block & Jayrampur water Supply Scheme under Karimpur-I Block under Nadia Arsenic Civil Division -II, PHE Dte." | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000283/2023-2024 | 140/NACD-II | 01/02/2024 | 23/09/2025 | GHOSH ENTERPRISE | 202.08 | 0 | 0 | 0
17 | NADIA | Karimpur-I | Nadia Arsenic Civil Division II | JAYRAMPUR PIPED WATER SUPPLY SCHEME | SM/12423 | New | Incorporation of the system of adsorption by Inorganic sustances for multivalent metalloid expulsion for improving potability in coordination with IS 10500 With latest edition at Jayrampur Piped Water Supply Scheme in Karimpur-I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II | Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000375/2024-2025 | 1650/NACD-II | 27/12/2024 | 26/01/2025 | HYDROTECH ASSOCIATES | 20.92 | 0 | 0 | 0
Total | [13 empty] | 540.7 | 36.19 | 6.69