## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Material Requisition To Resource Division |  |  | RTOR000023/2022-2023 | 1085/NACD-II | 09/12/2022 | 09/12/2022 | Resource Division | 26.69 | 0 | 0 | 0
2 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Hridaypur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000279/2022-2023 | 1134/NACD-II | 16/12/2022 | 15/01/2023 | JOY HIND TUBEWELLS | 21.46 | 20.98 | 97.75 | 100
3 | NADIA | Chapra | Eastern Mechanical | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under HRIDAYPUR W/S Scheme (Block : Tehatta I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 11) | Assistant Engineer | Junior Engineer | ORD/000031/2023-2024 | 1610/EMD | 26/04/2023 | 26/05/2023 | SARKAR ELECTRICAL | 19 | 0 | 0 | 0
4 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P in the proposed sites of Hridaypur water supply scheme under Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. Nadia | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000144/2023-2024 | 1396/NACD-II | 13/12/2023 | 27/01/2024 | PAPAN ROY | 25.75 | 0 | 0 | 0
5 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Rendering consultancy services for Geotechnical Investigation and Report preparation of site locations under Chapra Block of Nadia District through Jadavpur University. (Name of PWSS Hridaypur) | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000085/2023-2024 | 892/NACD-II | 21/08/2023 | 11/09/2023 | JADAVPUR UNIVERSITY | 4.78 | 4.78 | 100 | 100
6 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 377/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 17.35 | 0 | 0 | 0
7 | NADIA | Chapra | Eastern Mechanical | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | New Service connection under AE-III Hridaypur |  |  | BILL/01860/2023-2024 | BP-95-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.17 | 0 | 0 | 0
8 | NADIA | Chapra | Eastern Mechanical | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | New Service Connection under AE-III Hridaypur |  |  | BILL/01859/2023-2024 | BP-96-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.64 | 0 | 0 | 0
9 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00088/2022-2023 | 235/3 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
10 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00015/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.04 | 0 | 0 | 0
11 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 01 (One) No of 400 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Hridaypur Water Supply Scheme and other necessary allied works in this connection of Chapra Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000002/2023-2024 | 466/NACD-II | 20/04/2023 | 20/04/2024 | RADIANT | 591.46 | 134.67 | 22.77 | 26
12 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Construction of Arsenic-Cum-Iron Removal Plant (AIRP) of 73 cum/Hour capacity for Hridaypur Water Supply Scheme within Chapra block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000168/2024-2025 | 1052/NACD-II | 07/08/2024 | 03/02/2025 | ALOK ENTERPRISE (A UNIT OF SAKETTREXIM PVT LTD.) | 212.91 | 0 | 0 | 0
13 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Portal framed structural arrangement as well as Water supply/Sanitation arrangement and left out hydraulics in the proposed sites of Hridaypur Water Supply Scheme in Chapra Block under Nadia Arsenic Civil Division-II, PHE Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000326/2023-2024 | 431/NACD-II | 15/03/2024 | 29/04/2024 | BIPLAB BHOWMICK | 11.31 | 0 | 0 | 0
14 | NADIA | Chapra | Eastern Mechanical | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Providing Electro-Mechanical Equipments and Allied Works for Arsenic Removal Plant at HRIDAYPUR Piped Water Supply Scheme, Block_ Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. WBPHED/EE/EMD/NIeT-37 of 2023-24 (Sl. No.19) | Assistant Engineer |  | ORD/003197/2023-2024 | 946/EMD | 18/03/2024 | 17/04/2024 | M.S. ENTERPRISE | 52.66 | 0 | 0 | 0
15 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in Hridaypur Piped Water Supply Scheme and other schemes in different Blocks in the District of Nadia under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II,Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000165/2024-2025 | 873/AE-I/NACD-II | 23/08/2024 | 07/10/2024 | TECH VISION | 4.77 | 4.77 | 100 | 100
16 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Material Requisition To Resource Division |  |  | RTOR000002/2023-2024 | 77/NACD-II | 15/01/2024 | 15/01/2024 | Resource Division | 17.35 | 0 | 0 | 0
17 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Providing Functional House Hold Tap Connection including laying of pipeline at Betberia W/S Scheme & Hridaypur W/S Scheme in Chapra Block under Nadia Arsenic Civil Division-II, P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000135/2024-2025 | 748_NACD-II | 14/06/2024 | 29/07/2024 | SAFTI PRIVATE LIMITED | 18.22 | 0 | 0 | 100
18 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Sinking of 2 nos. 250 mm X 150 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (250 mm dia 36 mtr. long housing pipe & 150 mm dia 30 mtr. long strainer) at Hridaypur Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. |  |  | BILL/00008/2025-2026 |  | 17/04/2025 | 17/04/2025 | JOY HIND TUBEWELLS | 1.12 | 0 | 0 | 0
19 | NADIA | Chapra | Nadia Arsenic Civil Division II | HRIDAYPUR PIPED WATER SUPPLY SCHEME | SM/12624 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in Hridaypur Piped Water Supply Scheme and other schemes in different Blocks in the District of Nadia under Nadia Arsenic Civil Division-II,P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 1, Nadia Arsenic Civil Division-II | ORD/000417/2024-2025 | 1150/AE-I/NACD-II | 31/01/2025 | 12/03/2026 | TECH VISION | 4.77 | 0 | 0 | 100
Total | [13 empty] | 1040.47 | 165.2 | 15.88