## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Sinking of 2 nos. 300 mm X 200 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Baruihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000275/2022-2023 | 175/NACD-II | 24/01/2023 | 23/02/2023 | B.M. ENGINEERING & CONSTRUCTION | 27.71 | 25.99 | 93.8 | 100
2 | NADIA | Krishnagar-I | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Providing Electro Mechanical Equipments and Allied Works for Arsenic Removal Plant at BARUIHUDA Piped Water Supply Scheme, Block Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001122/2023-2024 | 4710/EMD | 04/08/2023 | 03/09/2023 | DEY ENTERPRISE | 53.06 | 0 | 0 | 0
3 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Construction of approch road at Head Works site of Baruihuda Water Supply Scheme in Krishnanagar-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia |  |  | ORD/000113/2023-2024 | 413_1AE-I/NACD-II | 08/08/2023 | 23/08/2023 | MANGES INDUSTRIAL CORPORATION. | 0.98 | 0 | 0 | 0
4 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 375/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 44.86 | 0 | 0 | 0
5 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00087/2022-2023 | 235/1 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
6 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00014/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.04 | 0 | 0 | 0
7 | NADIA | Krishnagar-I | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | New Service Connection under AE-III Baruihuda |  |  | BILL/01862/2023-2024 | BP-106-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0 | 0
8 | NADIA | Krishnagar-I | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | New Service Connection under AE-III Baruihuda |  |  | BILL/01863/2023-2024 | BP-105-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.95 | 0 | 0 | 0
9 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Construction of 92 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Baruihuda Water Supply Scheme in Krishnagar-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000193/2024-2025 | 1034/NACD-II | 05/08/2024 | 01/02/2025 | GHOSH ENTERPRISE | 239.9 | 0 | 0 | 0
10 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Baruihuda water supply scheme under Krishnanagar- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000139/2023-2024 | 1338/NACD-II | 05/12/2023 | 19/01/2024 | JAYBRATO HALDER | 29.32 | 7.43 | 25.34 | 100
11 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Renovation of Arsenic cum Iron treatment Plant of Damodarkhali PWSS (Capacity- 56 m3/hr) and ancillary works of Baruihuda W/S Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000328/2023-2024 | 37/NACD-II | 09/01/2024 | 09/03/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.41 | 78.35 | 78.03 | 100
12 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 75/NACD-II | 15/01/2024 | 15/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
13 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-84. Payment of way leave plan & survey charges |  |  | BILL/00501/2023-2024 | 295 | 27/12/2023 | 27/12/2023 | EASTERN RAILWAY | 0.2 | 0 | 0 | 0
14 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-83 payment of Wayleave Facility charge. |  |  | BILL/00580/2023-2024 | 359 | 04/03/2024 | 04/03/2024 | EASTERN RAILWAY | 8.98 | 0 | 0 | 0
15 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-82 payment of Wayleave Facility charge. |  |  | BILL/00578/2023-2024 | 358 | 04/03/2024 | 04/03/2024 | EASTERN RAILWAY | 8.98 | 0 | 0 | 0
16 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-83. Payment of way leave plan & survey charges |  |  | BILL/00500/2023-2024 | 294 | 27/12/2023 | 27/12/2023 | EASTERN RAILWAY | 0.14 | 0 | 0 | 0
17 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-82. Payment of way leave plan & survey charges |  |  | BILL/00499/2023-2024 | 293 | 27/12/2023 | 27/12/2023 | EASTERN RAILWAY | 0.14 | 0 | 0 | 0
18 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-84 payment of Wayleave Facility charge. |  |  | BILL/00579/2023-2024 | 360 | 04/03/2024 | 04/03/2024 | EASTERN RAILWAY | 12.73 | 0 | 0 | 0
19 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Baruihuda water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000255/2023-2024 | 232/NACD-II | 21/02/2024 | 06/04/2024 | ARIT KUMAR PAL | 11.29 | 0 | 0 | 100
20 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Construction and installation of MANIFOLD and allied works at OHR site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000416/2024-2025 | 09/NACD-II | 06/02/2025 | 07/05/2025 | SUMIT GHOSH | 105.58 | 0 | 0 | 0
21 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Supply of documents for way leave permission from the Eastern Railways authority at 1 no. location on Ranaghat-Krishnagar & Ranaghat -Shantipur Railway track under Baruihuda Piped Water Supply Scheme for Krishnagar-I Block under Nadia Arsenic Civil Division-II, PHE Dte.[Period of Work : 01-03-2025 to 28-02-2026] | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000425/2024-2025 | 1189/AE-I/NACD-II | 25/02/2025 | 26/04/2025 | SUMAN CHAKRABORTY | 1.92 | 0 | 0 | 100
22 | NADIA | Krishnagar-I | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under BARUIHUDA W/S Scheme (Block : Krishnagar I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000032/2023-2024 | 1611/EMD | 26/04/2023 | 01/11/2024 | M/S DAS ENTERPRISE | 19.54 | 0 | 0 | 100
Total | [13 empty] | 687.82 | 111.77 | 16.25