## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Sinking of 2 nos. 300 mm X 200 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Baruihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000275/2022-2023 | 175/NACD-II | 24/01/2023 | 23/02/2023 | B.M. ENGINEERING & CONSTRUCTION | 27.71 | 25.99 | 93.8 | 100
2 | NADIA | Krishnagar-I | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Providing Electro Mechanical Equipments and Allied Works for Arsenic Removal Plant at BARUIHUDA Piped Water Supply Scheme, Block Krishnagar-I, Dist. Nadia Under EMD, PHE Dte. |  |  | ORD/001122/2023-2024 | 4710/EMD | 04/08/2023 | 03/09/2023 | DEY ENTERPRISE | 53.06 | 0 | 0 | 0
3 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Construction of approch road at Head Works site of Baruihuda Water Supply Scheme in Krishnanagar-1 Block under Nadia Arsenic Civil Division-II P.H.E Dte. Dist.-Nadia |  |  | ORD/000113/2023-2024 | 413_1AE-I/NACD-II | 08/08/2023 | 23/08/2023 | MANGES INDUSTRIAL CORPORATION. | 0.98 | 0 | 0 | 0
4 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 375/NACD-II | 24/03/2023 | 24/03/2023 | Resource Division | 44.86 | 0 | 0 | 0
5 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | APPLICATION FOR OBTAINING PERMIT FOR SINKING OF NEW WELL |  |  | BILL/00087/2022-2023 | 235/1 | 21/02/2023 | 21/02/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.02 | 0 | 0 | 0
6 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Acceptance of 17 nos. of application (STW) for obtaining permit for domestic drinking water supply purposes. |  |  | BILL/00014/2023-2024 | 23 | 19/04/2023 | 19/04/2023 | GEOLOGIST GEOLOGICAL SUB-DIVN NO-III/A STATE WATER INVESTIGATION & DEVELOPMENT DTE. | 0.04 | 0 | 0 | 0
7 | NADIA | Krishnagar-I | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | New Service Connection under AE-III Baruihuda |  |  | BILL/01862/2023-2024 | BP-106-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0 | 0
8 | NADIA | Krishnagar-I | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | New Service Connection under AE-III Baruihuda |  |  | BILL/01863/2023-2024 | BP-105-23-24 | 31/07/2023 | 31/07/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.95 | 0 | 0 | 0
9 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Construction of 92 cum/Hour of Arsenic-Cum-Iron Removal Plant (AIRP) of Baruihuda Water Supply Scheme in Krishnagar-I block under Nadia Arsenic Civil Division-II, P.H.E. Dte., Dist. - Nadia | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000193/2024-2025 | 1034/NACD-II | 05/08/2024 | 01/02/2025 | GHOSH ENTERPRISE | 239.9 | 0 | 0 | 0
10 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Securitization arrangement by composite RCC Masonry structures without harming the T & P In the proposed sites of Baruihuda water supply scheme under Krishnanagar- I Block under Nadia Arsenic Civil Division-II,P.H.E. Dte. Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II,Junior Engineer 4, Nadia Arsenic Civil Division-II | ORD/000139/2023-2024 | 1338/NACD-II | 05/12/2023 | 19/01/2024 | JAYBRATO HALDER | 29.32 | 7.43 | 25.34 | 100
11 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Renovation of Arsenic cum Iron treatment Plant of Damodarkhali PWSS (Capacity- 56 m3/hr) and ancillary works of Baruihuda W/S Scheme at Krishnagar-I Block under Nadia Arsenic Civil Division-II P.H.E. Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000328/2023-2024 | 37/NACD-II | 09/01/2024 | 09/03/2024 | EFFLUENT & WATER TREATMENT ENGINEERS PVT. LTD. | 100.41 | 78.35 | 78.03 | 100
12 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Material Requisition To Resource Division |  |  | RTOR000003/2023-2024 | 75/NACD-II | 15/01/2024 | 15/01/2024 | Resource Division | 12.32 | 0 | 0 | 0
13 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-84. Payment of way leave plan & survey charges |  |  | BILL/00501/2023-2024 | 295 | 27/12/2023 | 27/12/2023 | EASTERN RAILWAY | 0.2 | 0 | 0 | 0
14 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-83 payment of Wayleave Facility charge. |  |  | BILL/00580/2023-2024 | 359 | 04/03/2024 | 04/03/2024 | EASTERN RAILWAY | 8.98 | 0 | 0 | 0
15 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-82 payment of Wayleave Facility charge. |  |  | BILL/00578/2023-2024 | 358 | 04/03/2024 | 04/03/2024 | EASTERN RAILWAY | 8.98 | 0 | 0 | 0
16 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-83. Payment of way leave plan & survey charges |  |  | BILL/00500/2023-2024 | 294 | 27/12/2023 | 27/12/2023 | EASTERN RAILWAY | 0.14 | 0 | 0 | 0
17 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-82. Payment of way leave plan & survey charges |  |  | BILL/00499/2023-2024 | 293 | 27/12/2023 | 27/12/2023 | EASTERN RAILWAY | 0.14 | 0 | 0 | 0
18 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Track crossing proposal with Application ID: ER-SDAH-2023-WL-84 payment of Wayleave Facility charge. |  |  | BILL/00579/2023-2024 | 360 | 04/03/2024 | 04/03/2024 | EASTERN RAILWAY | 12.73 | 0 | 0 | 0
19 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Portal framed structural arrangement as well as Water supply / sanitation arrangement and left out hydraulics in the proposed sites of Baruihuda water supply scheme under Nadia Arsenic Civil Division-II ,PHE Dte. Dist- Nadia | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000255/2023-2024 | 232/NACD-II | 21/02/2024 | 06/04/2024 | ARIT KUMAR PAL | 11.29 | 0 | 0 | 100
20 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Construction and installation of MANIFOLD and allied works at OHR site under Shyamnagar Piped Water Supply Scheme in Krishnaganj Block under Nadia Arsenic Civil Division-II,P.H.E Dte. | Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000416/2024-2025 | 09/NACD-II | 06/02/2025 | 07/05/2025 | SUMIT GHOSH | 105.58 | 0 | 0 | 0
21 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Supply of documents for way leave permission from the Eastern Railways authority at 1 no. location on Ranaghat-Krishnagar & Ranaghat -Shantipur Railway track under Baruihuda Piped Water Supply Scheme for Krishnagar-I Block under Nadia Arsenic Civil Division-II, PHE Dte.[Period of Work : 01-03-2025 to 28-02-2026] | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000425/2024-2025 | 1189/AE-I/NACD-II | 25/02/2025 | 26/04/2025 | SUMAN CHAKRABORTY | 1.92 | 0 | 0 | 100
22 | NADIA | Krishnagar-I | Eastern Mechanical | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Supply, delivery & installation of Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer and Automatic Chlorinator in connection with Aug. work related to FHTC at Pump House No.I & II under BARUIHUDA W/S Scheme (Block : Krishnagar I) Dist.- Nadia. NIET No.- 39 of EE/EMD of 2022-23 (Sl. No.- 12) | Assistant Engineer | Junior Engineer | ORD/000032/2023-2024 | 1611/EMD | 26/04/2023 | 01/11/2024 | M/S DAS ENTERPRISE | 19.54 | 0 | 0 | 100
23 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 38/NACD-II | 09/01/2025 | 09/01/2025 | Resource Division | 18.48 | 0 | 0 | 0
24 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Sinking of 2 nos. 300 mm X 200 mm dia, 180 mtr deep Tube Well by Direct Rotary Method at Head Work site and 2nd Tube Well site with UPVC pipe (CD) & strainer, (300 mm dia 36 mtr. long housing pipe & 200 mm dia 30 mtr. long strainer) at Baruihuda Water Supply Scheme under Nadia Arsenic Civil Division-II PHE Dte. |  |  | BILL/00034/2025-2026 |  | 23/04/2025 | 23/04/2025 | B.M. ENGINEERING & CONSTRUCTION | 1.39 | 0 | 0 | 0
25 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Soil Investigation for Construction of 01 (One) No of Overhead Reservoir, Construction of 500 Cum capacity 20 mtr staging height R.C.C. Over Head Water Reservoir as per Departmental design, Drawing, and specification including bored pile & pile cap, Laying of Distribution system including providing Functional House Hold Tap Connection (FHTC) and Laying of Rising Main and other necessary allied works at Baruihuda water supply scheme of Krishnagar-I Block under Nadia Arsenic Civil Division - II P.H.E. Dte. Dist - Nadia. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 2, Nadia Arsenic Civil Division-II | ORD/000389/2022-2023 | 396/NACD-II | 28/03/2023 | 27/03/2028 | MANGES INDUSTRIAL CORPORATION. | 423.86 | 138.08 | 32.58 | 45
26 | NADIA | Krishnagar-I | Nadia Arsenic Civil Division II | BARUIHUDA PIPED WATER SUPPLY SCHEME | SM/14423 | New | Conversion of IEP to AIRP at KADIPUR Water Supply Scheme of capacity 55 Cu.m/hr in Krishnaganj Block & CHANDERGHAT, PANINALA & BARUIHUDA Water Supply Scheme under Nadia Arsenic Civil Division -II, PHE Dte. | Assistant Engineer -II, Nadia Arsenic Civil Division-II,Assistant Engineer(Contractual), Nadia Arsenic Civil Di | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000419/2024-2025 | 1147/NACD-II | 23/08/2024 | 15/04/2026 | MERCURY ENGINEERING COMPANY. | 173.69 | 0 | 0 | 8
Total | [13 empty] | 1305.24 | 249.85 | 19.14