## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA | Tehatta-II | Eastern Mechanical | Mini Piped Water Supply Scheme at Dharammpur (Part-A) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16100 | New | Supply and Installation of single phase Submersible Pumping Machinery alongwith allied Electro-Mechanical works, Voltage Stabilizer, Automatic Chlorinator etc for 10 nos Mini Piped water Supply Scheme Dharampur part-A, Dharampur part-B, Satikhali part-A , Satikhali part-B, Chak Rudranagar, Labangola, Chak Ramnagar, Jaba part-A, Jaba part-B and Jayghata for 7 nos. Mouza under Tehatta-II, Krishnagar-I and Karimpur-I Block, Augmentation to Accomodate FHTC , Dist. - Nadia. | Assistant Engineer | Junior Engineer | ORD/000355/2023-2024 | 4491/EMD | 14/07/2023 | 13/08/2023 | ORIENTAL ENGINEERING CO. | 54.05 | 0 | 0 | 80
2 | NADIA | Tehatta-II | Nadia Arsenic Civil Division II | Mini Piped Water Supply Scheme at Dharammpur (Part-A) village, Block- Tehatta-II, Nadia District, under Nadia Arsenic Civil Division-II. | SM/16100 | New | Sinking of Tubewell, Laying of distribution system, providing FHTC, construction of Arsenic cum Iron treatment plant and ancillary works for Mini Piped Water Supply Scheme (upto 100 HHs) at Dharammpur (Part-A) of Tehatta-II Block under Nadia Arsenic Civil Division-II PHE Dte. | Assistant Engineer -I (HQ), Nadia Arsenic Civil Divisio | Junior Engineer 3 ,Nadia Arsenic Civil Division-II | ORD/000029/2023-2024 | 583/NACD-II | 17/05/2023 | 01/05/2026 | PAPAN ROY | 25.74 | 0 | 0 | 25
Total | [13 empty] | 79.79 | 0 | 0