## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Supply of Chemicals and accessories for different NGO managed Water Testing Laboratories on emergency basis of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.01 | Assistant Engineer |  | ORD/001827/2021-2022 | 175/BST | 08/03/2022 | 08/04/2022 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 4.97 | 4.97 | 100 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Supply of Silver diethyl -dithio- carbamate for analysis,( 5 gm pack) Merck for different Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.01 | Assistant Engineer |  | ORD/001828/2021-2022 | 176/BST | 08/03/2022 | 08/04/2022 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 4.83 | 4.83 | 100 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Supply of Ferrospectral Reagent (Fe.1) Range 0.005-5.00 mg/l Fe 2+(1000) test pack for different Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.03 | Assistant Engineer |  | ORD/001830/2021-2022 | 178/BST | 08/03/2022 | 08/04/2022 | LAB. SOLUTION | 4.89 | 4.89 | 100 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | 3rd Party Calibration of pH Meter, Turbidity meter, Oven, Weight Box, Analytical Balance, Burette, Pipette of different volume, Volumetric Flask of different volume, measuring cylinder of different volume, Thermometer & any other measuring Instruments required for calibration as per NABL traceability & conformity under Barasat Sub Division, P.H.E. Dte. Sl. No.-01 | Assistant Engineer |  | ORD/001928/2021-2022 | 778/A/BSD | 26/11/2021 | 29/11/2021 | LAB. SOLUTION | 0.58 | 0.58 | 100 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Renovation of laboratory building for NABL accreditation at Barasat District Laboratory under Barasat Sub Division, P.H.E. Dte. Part-B Sl. No.-13 | Assistant Engineer |  | ORD/000176/2022-2023 | 342/BSD | 12/04/2022 | 02/05/2022 | P.ENTERPRISE. | 4.43 | 4.43 | 100 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Acceptance cum work order for Supply of Chemicals, Glass Ware and accessories for different Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000165/2022-2023 | 1592/BD | 03/06/2022 | 03/07/2022 | BHARATI CHEMICAL & SCIENTIFIC WORK. | 41.92 | 41.92 | 100 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Procurement of consumables of OMAS for the month of June to July'2022 for the District of North 24 Parganas under Barasat Division, P.H.Engineering Dte. Sl.No.02 | Assistant Engineer | Junior Engineer | ORD/000179/2022-2023 | 464/BST | 08/06/2022 | 08/08/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.29 | 4.29 | 100 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Electrification Works of laboratory building for NABL accreadiation at Barasat District Laboratory under Barasat Sub Division, P.H.E. Dte. Sl. No.-14 | Assistant Engineer |  | ORD/000203/2022-2023 | 343/BSD | 12/04/2022 | 19/04/2022 | ANJALI ENTERPRISE. | 4.6 | 4.6 | 100 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Renovation of laboratory building for NABL accreditation at Barasat District Laboratory under Barasat Sub Division, P.H.E. Dte. Part-A Sl. No.-12 | Assistant Engineer |  | ORD/000177/2022-2023 | 341/BSD | 12/04/2022 | 02/05/2022 | M/S K.P.PAL. | 4.58 | 4.58 | 100 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Engagement of Computer Operator / Data Entry Operator of different categories for the office of the Assistant Engineer, R.W.S Barasat Sub- Division, PHE Dte. (Period 01.11.2020 to 31.10.2021). |  |  | ORD/000310/2020-2021 | 551/BST | 14/10/2020 | 14/01/2021 | M/S B.K.ENTERPRISE. | 0 | 0 | NAN | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Supply of Chemicals and accessories for different Sub-Divisional Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.02 | Assistant Engineer |  | ORD/001829/2021-2022 | 177/BST | 08/03/2022 | 08/04/2022 | M/S LAXMI ENTERPRISE | 4.96 | 4.95 | 99.92 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Supply of Certified traceable to SI unit of Pt-Co-Color units Calibration Standard CRM at Asesh Roy Water Testing Laboratory, Chandpara Sub-District Water Testing laboratory & Turbidity standard solution at Bagdah Sub-District Water Testing Laboratory under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000240/2023-2024 | 509/BST | 08/06/2023 | 15/06/2023 | LAB. SOLUTION | 0.65 | 0.65 | 100 | 100
13 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Supply Turbidity standard solution at Asesh Roy Water Testing Laboratory & Chandpara Sub-District Water Testing laboratory under Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000239/2023-2024 | 508/BST | 08/06/2023 | 15/06/2023 | LAB. SOLUTION | 0.84 | 0.84 | 100 | 100
14 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Supply installation & calibration of Turbidity Meter for Bagdah & Gokna Water Testing Laboratories of North 24Pgs District Under Barasat Division, PHE Dte. Sl.No.01 | Assistant Engineer |  | ORD/000079/2022-2023 | 334/BST | 21/04/2022 | 01/05/2022 | LAB ANALYTICS | 2.13 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Payment of NGO Laboratory for the month of Nov'2023. |  |  | BILL/02964/2023-2024 | BP-2023-24-623 | 20/12/2023 | 20/12/2023 | WEST BENGAL COMPREHENSIVE AREA DEVELOPMENT CORPORATION, DEGANGA PROJECT. | 0.51 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Payment of NGO laboratory for the Month of Nov'2023 |  |  | BILL/02961/2023-2024 | BP-2023-24-619 | 20/12/2023 | 20/12/2023 | PATHER PANCHALI SEVA SAMITY. | 0.51 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Operation, Maintenance, procurement of Chemicals, Consumables, Glassware & AMC of Computers of different water testing laboratories under Barasat Division, PHE Dte. | SM/06629 | Support-WQMSP | Acceptance cum work order for Engagement of 16 nos. personnel (1 no. Chemist/Bacteriologist & 1 nos. Lab Assistant) ) in 8 nos. laboratories under Barasat Division,PHE Dte.(Bodai Sub-District Water Testing Lab, Bishnupur Sub-District Water Testing Lab, Bagda Sub-District Water Testing Lab, Chandpara Sub-District Water Testing Lab, Habra Sub-District Water Testing Lab, Basirhat Sub-District Water Testing Lab ,Gokna Sub-District Water Testing Lab, Haroa Sub-District Water Testing Lab ) for 1(one) year)(Effect from 01-01-2023 to 31.12.2023.) | Assistant Engineer |  | ORD/001027/2022-2023 | 184/BD | 19/01/2023 | 19/01/2024 | FRONTLINE EX-SERVICEMEN BUREAU. | 36.96 | 6.11 | 16.52 | 100
Total | [13 empty] | 121.65 | 87.64 | 72.04