## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000921/2021-2022 | 1861/HSD.. | 17/11/2021 | 02/12/2021 | M/S NIRMAN CONSTRUCTION. | 2.37 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000920/2021-2022 | 1861/HSD. | 17/11/2021 | 02/12/2021 | M/S NIRMAN CONSTRUCTION. | 2.37 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Construction of approach road with cement concrete at PH No.-3 within Joygopalpur w/s scheme, Sandehkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2022-2023 | 792/HSD | 13/05/2022 | 23/05/2022 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.8 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Emergent supply, fitting & fixing of Main gate and other allied works at OHR site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000756/2022-2023 | 617/HSD | 07/04/2022 | 22/04/2022 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 0.6 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Restoration of existing concrete road for damaged portion due to movement of heavy vehicles during construction of OHR at Bermajur H.W. site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/000704/2021-2022 | 1992/HSD | 02/12/2021 | 17/12/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.4 | 0 | 0 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Protection of UPVC distribution pipeline by UC bullah pile at different places for protection of different dia UPVC distribution pipe line within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001526/2021-2022 | 1865/HSD | 17/11/2021 | 02/12/2021 | M/S NIRMAN CONSTRUCTION. | 4.79 | 0 | 0 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Restoration of existing concrete road for damaged portion due to movement of heavy vehicles during construction of OHR at Bermajur H.W. site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/000705/2021-2022 | 1993/HSD | 02/12/2021 | 17/12/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 4.78 | 0 | 0 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Bhabanipur (Zone-I & Zone-II) Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000960/2021-2022 | 2156/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.76 | 0 | 0 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Malancha Zone I Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000955/2021-2022 | 2151/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.43 | 0 | 0 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Malancha Zone II Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000956/2021-2022 | 2152/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.77 | 0 | 0 | 1
11 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001759/2021-2022 | 470/HSD | 10/03/2022 | 20/03/2022 | ARBINA ENTERPRISE. | 3.89 | 0 | 0 | 1
12 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Bermajur Taltala Para, Molla para, Hatkhola Para, Dangal para, Kalyani para, Kachari para & Pol para within Bermajur W/S/Scheme Sandeshkhali-II Block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002121/2021-2022 | 1465/BD. | 13/08/2021 | 12/09/2021 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 32.29 | 0 | 0 | 1
13 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Protection works for protection of UPVC distribution pipe line at N/H/O Laxmikanta Singh within Bermajur w/s Scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000322/2022-2023 | 1243/HSD | 20/07/2022 | 04/08/2022 | M/S ANUBHAB CONSTRUCTION. | 0.56 | 0 | 0 | 1
14 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Emergent restoration of existing pilling works to sustain the protection of UPVC distribution pipe line at different places within Bermajur w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/002573/2021-2022 | 417/HSD | 04/03/2022 | 14/03/2022 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 3.87 | 0 | 0 | 1
15 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Connection of OHR from rising main and other allied works at Head Work site within Bermajur w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000243/2022-2023 | 1152/HSD | 12/07/2022 | 27/07/2022 | M/S NIRMAN CONSTRUCTION. | 4.11 | 0 | 0 | 1
16 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Additional works for approach road with cement concrete and other allied works at Head Work site within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000244/2022-2023 | 1153/HSD | 12/07/2022 | 27/07/2022 | M/S NIRMAN CONSTRUCTION. | 1.55 | 0 | 0 | 1
17 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Bermajur mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Bermajur w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000665/2022-2023 | 2920/BD | 26/09/2022 | 26/10/2022 | UNIFIED ENGINEERS' CO-OPERATIVE SOCIETYLTD. | 24.18 | 0 | 0 | 1
18 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Kalitala Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000999/2021-2022 | 2179/HSD | 28/12/2021 | 18/01/2022 | TIYAS CONSULTANCY AND INFRASTRUCTURE PVT.LTD. | 3.93 | 0 | 0 | 1
19 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Acceptance cum work order for Supply of Mechanized boat on hire basis with providing driver, helper and other requirement as per terms condition and specification as per direction of the EIC under Hasnabad Sub-Division, P.H.E. Dte. Period : 01.07.2021 to 30.06.2022 = 365 days | Assistant Engineer | Junior Engineer | ORD/002867/2021-2022 | 1112/HSD | 29/06/2021 | 29/06/2022 | RANJIT KUMAR MANDAL. | 3.15 | 0 | 0 | 1
20 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000194/2022-2023 | 677/BD | 01/03/2023 | 01/03/2023 | Resource Division | 61.6 | 0 | 0 | 0
21 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bermajur Water Supply Scheme, Sandeshkhali - II Block. | SM/07610 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 1820/BD | 19/06/2023 | 19/06/2023 | Resource Division | 20.33 | 0 | 0 | 0
Total | [13 empty] | 192.52 | 0 | 0