## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. | SM/07611 | Retrofitting | Acceptance cum work order for Construction of boundary wall with RCC column structure at Head Work site (PH No-1) within Chunchura & Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/001303/2023-2024 | 4376/BD | 10/11/2023 | 08/02/2024 | MONDAL & CO. (BASIRHAT). | 23.88 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. | SM/07611 | Retrofitting | Acceptance cum work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000168/2022-2023 | 1152/BD | 12/04/2022 | 08/12/2022 | S.S.ENTERPRISE. (BAMANGACHI) | 97.05 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. | SM/07611 | Retrofitting | Acceptance cum work order for Construction of 300 cum capacity 20 mtr. staging height R.C.C. Over Head Water Reservoir as per Departmental design, drawing and specification including bored pile & pile cap at Rajbari water supply scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000664/2022-2023 | 1152/ BD | 12/04/2022 | 08/12/2022 | S.S.ENTERPRISE. (BAMANGACHI) | 97.05 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rajbari Water Supply Scheme, Sandeshkhali - I Block. | SM/07611 | Retrofitting | Work order for Providing Functional Household Tap Connection (FHTC) to the uncovered household as well as convert the Rajbari mouza into Swajal Gram i/c laying of UPVC/PVC pipe & supply of necessary fittings within Rajbari w/s scheme, Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000668/2022-2023 | 2923/BD | 26/09/2022 | 26/10/2022 | ABDUL HAMID GAZI. | 11.33 | 0 | 0 | 1
Total | [13 empty] | 229.31 | 0 | 0