## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) | SM/07612 | Retrofitting | Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Talsa & Adjoining Mouzas Water Supply Scheme at Habra-II Block under Barasat Division, PHE Dte. (Phase-II). | Assistant Engineer | Junior Engineer | ORD/001841/2020-2021 | 388/BD. | 18/02/2021 | 19/05/2021 | PUSPA ENTERPRISE. | 84.95 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Talsa and Adjoining mouzas Water Supply Scheme at Habra-II Block, Dist.-North 24 Parganas (Phase-II) | SM/07612 | Retrofitting | Acceptance cum work order for Providing Functional House Hold Tap Connection (FHTC) from existing distribution system at Talsa & Adj. Mouzas Water Supply Scheme within the jurisdiction of Habra Sub-Division under Barasat Division, P.H.E. Dte.( For balance work of Retrofitting). | Assistant Engineer | Junior Engineer | ORD/000838/2022-2023 | 3583/ BD | 08/12/2022 | 07/01/2023 | TRISHA ENTERPRISE & CO. | 42.66 | 0 | 0 | 1
Total | [13 empty] | 127.61 | 0 | 0