## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-II) | SM/07616 | Retrofitting | providing of Functional House hold Tap connection (FHTC) in connection with JJM under command area of Malidah Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/002299/2020-2021 | 276/BD. | 05/02/2021 | 12/02/2021 | ORIENT CONSTRUCTION. | 11 | 11 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Malidah Water Supply Scheme at Bagdah Block (Phase-II) | SM/07616 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 2858/BD | 21/09/2022 | 21/09/2022 | Resource Division | 1.85 | 0 | 0 | 0
Total | [13 empty] | 12.85 | 11 | 85.62