## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07617 | Retrofitting | Formal work order for "Providing Functional Household Tap Connection (FHTC) from existing and new proposed distribution system within the command area Malatipur & Chaita (Part) Mouzas under Sadiknagar Zone - II Water Supply Scheme at Basirhat - II Block Under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001760/2020-2021 | 495/BD. | 26/02/2021 | 27/05/2021 | ORIENT CONSTRUCTION. | 97.09 | 56.62 | 58.32 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07617 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for SADIKNAGAR-II Water Supply Scheme in Basirhat-II Block under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001951/2021-2022 | 207/BHTSD | 28/02/2022 | 15/03/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.51 | 3.5 | 99.57 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07617 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Khulna Bhandarkhali Zone-I Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/002035/2021-2022 | 2177/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.92 | 3.93 | 100.1 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07617 | Retrofitting | Route Survey, Design Drawing & DPR Preparation for Krishnachandrapur Water Supply Scheme under Bongaon Sub-Division, under Barasat Division, PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/001118/2021-2022 | 612/Bon | 31/12/2021 | 20/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.09 | 4.07 | 99.67 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sadiknagar Zone-II Water Supply Scheme at Basirhat-II Block, Dist.-North 24 Parganas (Phase-I) | SM/07617 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000076/2022-2023 | 2988/BD | 29/09/2022 | 29/09/2022 | Resource Division | 0.01 | 0 | 0 | 0
Total | [13 empty] | 108.62 | 68.12 | 62.71