## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) | SM/07842 | Retrofitting | Acceptance cum work order for laying of distribution pipe line by UPVC pipe and providing FHTC to uncovered village of Humaipur Water Supply Scheme under Barasat Sub Division, P.H.E. Dte. | Assistant Engineer |  | ORD/002327/2023-2024 | 935/BD | 15/03/2024 | 14/04/2024 | SUN ENTERPRISE. | 6.94 | 0 | 0 | 0
2 | NORTH 24 PARAGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) | SM/07842 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Banspol, Dariala & Birpur mouzas within Humaipur Water Supply Scheme at Barasat-II Block under Barasat Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000591/2022-2023 | 2626/BD | 05/09/2022 | 05/10/2022 | M/S K.B.ENTERPRISE. | 43.06 | 38.98 | 90.52 | 1
Total | [13 empty] | 50 | 38.98 | 77.96