## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) | SM/07842 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Banspol, Dariala & Birpur mouzas within Humaipur Water Supply Scheme at Barasat-II Block under Barasat Sub Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000591/2022-2023 | 2626/BD | 05/09/2022 | 05/10/2022 | M/S K.B.ENTERPRISE. | 43.06 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) | SM/07842 | Retrofitting | Acceptance cum work order for Repair & Renovation work at Head work site in connection with Augmentation of Humaipur Water Supply Scheme under Barasat Sub Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002061/2024-2025 | 1033/BD | 28/03/2025 | 12/05/2025 | MUKHERJEE CONSTRUCTION (NADIA) | 19.71 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Humaipur Piped Water Supply Scheme at Barasat-II Block (Phase-I) | SM/07842 | Retrofitting | Acceptance cum work order for Construction and installation of MANIFOLD and allied works at Humaipur OHR site under Humipur Water Supply Scheme within Barasat Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000043/2025-2026 | 1724/BD | 27/05/2025 | 24/09/2025 | MONDAL ENTERPRISE. (BARASAT) | 31.87 | 0 | 0 | 0
Total | [13 empty] | 94.64 | 0 | 0