## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) | SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001026/2021-2022 | 14/HSD | 04/01/2022 | 19/01/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) | SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Bouthakurani Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001032/2021-2022 | 20/HSD | 04/01/2022 | 19/01/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) | SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001037/2021-2022 | 24/HSD | 04/01/2022 | 19/01/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 100 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) | SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-C) | Assistant Engineer | Junior Engineer | ORD/001040/2021-2022 | 26/HSD | 04/01/2022 | 19/01/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.79 | 4.76 | 99.41 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) | SM/07851 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-B) | Assistant Engineer | Junior Engineer | ORD/001028/2021-2022 | 16/HSD | 04/01/2022 | 19/01/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 100 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-I) | SM/07851 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000085/2023-2024 | 1813/BD | 19/06/2023 | 19/06/2023 | Resource Division | 2.59 | 0 | 0 | 0
Total | [13 empty] | 27 | 19.48 | 72.14