## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Construction of boundary wall at East & West side for damaged portion at PH No.-4 for Rejuvenation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000527/2020-2021 | 393/HSD | 11/02/2021 | 26/02/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.87 | 0 | 0 | 0
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Repairing of Pump House No.-3 for Rejuvenation of Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000647/2020-2021 | 385/HSD | 11/02/2021 | 26/02/2021 | M/S LALTI ENTERPRISE | 1.31 | 0 | 0 | 0
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Additional Emergent restoration of concrete road for damage portion at different places due to newly laid HDPE/DI pipeline within Hasnabad w/s scheme, Hasnabad block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000553/2021-2022 | 1658/HSD | 05/10/2021 | 15/10/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 2.86 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Joykrisnapur mouza including laying of UPVC/PVC pipe & supply of necessary fittings Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000547/2021-2022 | 1652/HSD | 05/10/2021 | 20/10/2021 | MONDAL & CO. (BASIRHAT). | 3.04 | 0 | 0 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Restoration of pipeline by withdrawn & relaying of different dia. UPVC pipe line for extra widening of PWD road from Sri Chaitanya Math to Pather Dabi More within Hingalganj W/S Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000549/2021-2022 | 1654/HSD | 05/10/2021 | 20/10/2021 | MONDAL & CO. (BASIRHAT). | 4.6 | 0 | 0 | 0
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Additional Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Bouthakurani water supply scheme (For Bouthakurani & Tongtala Mouza) at Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer |  | ORD/000550/2021-2022 | 1655/HSD | 05/10/2021 | 20/10/2021 | M/S B.K.ENTERPRISE. | 4.35 | 0 | 0 | 0
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/HDPE/UPVC) of Hasnabad w/s Scheme, Hasnabad block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000554/2021-2022 | 1659/HSD | 05/10/2021 | 26/10/2021 | MONDAL & CO. (BASIRHAT). | 4.4 | 0 | 0 | 0
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Khosbas & Singerkati mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Hingalganj w/s scheme (Zone-II), Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000556/2021-2022 | 1661/HSD | 05/10/2021 | 15/10/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.2 | 0 | 0 | 0
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/UPVC) for Mamudpur Mouza within Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000540/2021-2022 | 1645/HSD | 05/10/2021 | 20/10/2021 | TRISHA ENTERPRISE & CO. | 2.54 | 0 | 0 | 0
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for OHR connection with distribution main including Laying of balance laying work of rising main and distribution pipe line within Hingalganj water supply scheme (Zone-I), Hingalganj Block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000541/2021-2022 | 1646/HSD | 05/10/2021 | 20/10/2021 | ANKUSH CONSTRUCTION & CO. | 4.51 | 0 | 0 | 0
11 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Special Repair & Maintenance of Rising main & Distribution system (CI/DI/UPVC) for Hingalganj Mouza within Hingalganj w/s Scheme (Zone-I), Hingalganj block under Hasnabad Sub-Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000539/2021-2022 | 1644/HSD | 05/10/2021 | 20/10/2021 | MONDAL & CO. (BASIRHAT). | 2.59 | 0 | 0 | 0
12 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Additional Land development at Pump House No.-1 (New site) within Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000542/2021-2022 | 1647/HSD | 05/10/2021 | 15/10/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 1.14 | 0 | 0 | 0
13 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Laying of 150 mm dia. DI rising main from Pump House No-2 to Pump House No.-1 (New site) within Sultanpur w/s scheme, Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000543/2021-2022 | 1648/HSD | 05/10/2021 | 15/10/2021 | R.K.MANDAL AND CO. | 1.2 | 0 | 0 | 0
14 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Paitkelpota & Paitkelpota Abad mouza including laying of UPVC/PVC pipe & supply of necessary fittings Sultanpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000544/2021-2022 | 1649/HSD | 05/10/2021 | 20/10/2021 | MONDAL & CO. (BASIRHAT). | 1.9 | 0 | 0 | 0
15 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Additional land development at tube well site-3 (CWR site) within Hingalganj w/s scheme (Zone-II), Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/000555/2021-2022 | 1660/HSD | 05/10/2021 | 15/10/2021 | TRISHA ENTERPRISE & CO. | 0.92 | 0 | 0 | 0
16 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Supply of different dia. Sluice Valve & construction of different dia. Sluice Valve chamber at different places within Hingalganj w/s scheme (Zone-I), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer |  | ORD/000558/2021-2022 | 1663/HSD | 05/10/2021 | 15/10/2021 | MONDAL & CO. (BASIRHAT). | 4.88 | 0 | 0 | 0
17 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Additional Functional Household Tap Connection (FHTC) in Radhanagar mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Chotto Sehara w/s scheme Sandeshkhali-I block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000560/2021-2022 | 1665/HSD | 05/10/2021 | 15/10/2021 | TRISHA ENTERPRISE & CO. | 3.56 | 0 | 0 | 0
18 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Sultanpur Water Supply Scheme, Minakhan Block, | SM/07852 | Retrofitting | Acceptance cum work order for Restoration of pipeline by withdrawn & relaying of different dia. UPVC pipe line for extra widening of PWD road from Ghoshpara More to Sri Chaitanya Math within Hingalganj W/S Scheme (Zone-I), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer |  | ORD/000548/2021-2022 | 1653/HSD | 05/10/2021 | 20/10/2021 | MONDAL & CO. (BASIRHAT). | 4.61 | 0 | 0 | 0
Total | [13 empty] | 51.47 | 0 | 0