## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-II) | SM/08068 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Gadpukuria Water Supply Scheme at Bagdah Block under Barasat Division, PHE Dte. (Phase-II). | Assistant Engineer | Junior Engineer | ORD/001732/2020-2021 | 423/BD. | 19/02/2021 | 05/04/2021 | M/S S.S.ENTERPRISE. (SOUTH) | 84.66 | 49.4 | 58.35 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Gadpukuria Piped Water Supply Scheme at Bagdah Block (Phase-II) | SM/08068 | Retrofitting | Repairing & Renovation 2(Two) nos of Pump House and allied works of Gadpukuria water supply scheme under Bongaon Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002925/2021-2022 | 531/Bon | 03/11/2021 | 24/11/2021 | MA CONSTRUCTION. | 2.52 | 2.49 | 98.91 | 1
Total | [13 empty] | 87.18 | 51.89 | 59.52