## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000706/2021-2022 | 1994/HSD | 02/12/2021 | 09/12/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 2 | 2 | 100 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Dholkhali & Tongtala mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000338/2021-2022 | 1670/BD | 08/09/2021 | 08/10/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 49.88 | 17.52 | 35.12 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Dholkhali Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001035/2021-2022 | 22/HSD | 04/01/2022 | 19/01/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.9 | 4.9 | 100 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Tongtala Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001111/2021-2022 | 14/HSD | 04/01/2022 | 19/01/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.91 | 4.91 | 100 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Additional Laying of diff. dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Bouthakurani Mouza within Bouthakurani W/S scheme, Sandeshkhali-II block under Hasnabad Sub-Division within Barasat Division, PHE Dte. (Part-A) | Assistant Engineer | Junior Engineer | ORD/001030/2021-2022 | 18/HSD | 04/01/2022 | 19/01/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.9 | 4.9 | 100 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bouthakurani w/s scheme (Zone-I to III), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001667/2021-2022 | 421/HSD | 04/03/2022 | 14/03/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.73 | 4.78 | 101.08 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Bouthakurani w/s scheme (Zone-IV to V), Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001668/2021-2022 | 422/HSD | 04/03/2022 | 14/03/2022 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 4.73 | 4.73 | 100.08 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line for providing FHTC by bamboo pilling at different places within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001750/2021-2022 | 465/HSD | 10/03/2022 | 20/03/2022 | R.K.MANDAL AND CO. | 4.85 | 4.85 | 100 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Bouthakurani w/s scheme, Sandeshkhali-II Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001748/2021-2022 | 464/HSD | 10/03/2022 | 20/03/2022 | R.K.MANDAL AND CO. | 3.39 | 3.39 | 100 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Bouthakurani Water Supply Scheme, Sandeshkhali - II Block. (Phase-II) | SM/08072 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000086/2023-2024 | 1818/BD | 19/06/2023 | 19/06/2023 | Resource Division | 16.39 | 0 | 0 | 0
Total | [13 empty] | 100.67 | 51.98 | 51.64