## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | SM/08073 | Retrofitting | Acceptance cum work order for Protection works for newly laid different dia.UPVC/DI pipe line at different places in Radhanagar laskar para, majher para, Singh para & Tati Para within Chhoto Sehara W/S/Scheme, Sandeshkhali-I Block under Hasnabad Sub-Division P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/002120/2021-2022 | 1467/BD. | 13/08/2021 | 12/09/2021 | M/S DATTA ENTERPRISE. | 31.6 | 4.63 | 14.65 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | SM/08073 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in Dholkhali & Tongtala mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Bouthakurani w/s scheme, Sandeshkhali-II block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000338/2021-2022 | 1670/BD | 08/09/2021 | 08/10/2021 | SRI KRISHNA CO-OP-LABOUR CONTRACT AND CONST SOC LTD. | 49.88 | 31.41 | 62.97 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | SM/08073 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Chotto Sehara mouza within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2024-2025 | 1172/HSD | 26/09/2024 | 06/10/2024 | TRISHA ENTERPRISE & CO. | 0.97 | 0.97 | 100 | 100
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | SM/08073 | Retrofitting | Acceptance cum work order for Supply and installation of 150mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000557/2024-2025 | 999/HSD | 29/08/2024 | 08/09/2024 | TRISHA ENTERPRISE & CO. | 0.97 | 0.97 | 100 | 100
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | SM/08073 | Retrofitting | Acceptance cum work order for Emergency repairing of existing FHTC along with pipe line in connection with retrofitting work at different places of Radhanagar mouza within Chotto Sehara w/s scheme, Sandeshkhali-I block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2024-2025 | 994/HSD | 29/08/2024 | 08/09/2024 | TRISHA ENTERPRISE & CO. | 0.97 | 0.97 | 100 | 100
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | SM/08073 | Retrofitting | Acceptance cum work order for Supply and installation of 200mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000559/2024-2025 | 1001/HSD | 29/08/2024 | 08/09/2024 | TRISHA ENTERPRISE & CO. | 0.97 | 0.97 | 100 | 100
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Chotto Sehara Piped Water Supply Scheme, Sandeshkhali-I Block | SM/08073 | Retrofitting | Acceptance cum work order for Supply and installation of 100mm dia sluice valve in distribution pipe line for smooth supply of water at different palces within Chotto Sehara water supply scheme, Sandeshkhali-I Block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000555/2024-2025 | 997/HSD | 29/08/2024 | 08/09/2024 | TRISHA ENTERPRISE & CO. | 0.84 | 0.84 | 100 | 100
Total | [13 empty] | 86.19 | 40.75 | 47.28