## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work order for Construction of Anchor block for resting of 100 mm dia DI Distribution main for low areas at different places within Rupmari w/s scheme, Hingalganj Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001644/2021-2022 | 400/HSD | 04/03/2022 | 19/03/2022 | M/S PROGATI ENTERPRISE. | 3.86 | 3.86 | 100.02 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work order for Laying of 100 mm dia. DI distribution main from near PH No-3 towards Halda more for damage portion within Rupmari w/s scheme (Zone-III), Hingalganj Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001646/2021-2022 | 402/HSD | 04/03/2022 | 14/03/2022 | M/S PROGATI ENTERPRISE. | 1.53 | 1.53 | 99.92 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work order for Protection of newly laid different dia. UPVC distribution pipeline for providing FHTC by UC bullah pile at different places within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001648/2021-2022 | 404/HSD | 04/03/2022 | 14/03/2022 | M/S PROGATI ENTERPRISE. | 4.95 | 5 | 101.02 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work order for Protection of newly laid UPVC pipe line for providing FHTC by bamboo pilling at different places within Rupmari w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001647/2021-2022 | 403/HSD | 04/03/2022 | 14/03/2022 | M/S DATTA ENTERPRISE. | 4.93 | 4.91 | 99.58 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work Order for Providing Functional Household Tap Connection (FHTC) in Rupmari & Bastali mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Rupmari W/S scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001074/2021-2022 | 95/BD | 17/01/2022 | 03/03/2022 | M/S DATTA ENTERPRISE. | 96.84 | 96.43 | 99.58 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-IV to VI), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001989/2021-2022 | 253/HSD | 07/02/2022 | 17/02/2022 | M/S DATTA ENTERPRISE. | 4.86 | 3.46 | 71.06 | 1
7 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Rupmari w/s scheme (For Zone-I to III), Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001990/2021-2022 | 256/HSD | 07/02/2022 | 17/02/2022 | M/S PROGATI ENTERPRISE. | 3.46 | 3.46 | 100 | 1
8 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC within Rupmari w/s scheme (Zone-III to VI), Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000125/2022-2023 | 940/HSD | 07/06/2022 | 22/06/2022 | M/S DATTA ENTERPRISE. | 3.08 | 3.08 | 99.99 | 1
9 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Acceptance cum work order for Withdrawing & relaying of 75 mm dia. HDPE pipe line from near Halda High School towards Kumirmari kheya Ghat for damage portion within Rupmari W/S Scheme (Z-III & IV), Hingalganj block under Hasnasbad Sub-Division, P.H.E.Dte. | Assistant Engineer | Junior Engineer | ORD/000126/2022-2023 | 941/HSD | 07/06/2022 | 17/06/2022 | M/S PROGATI ENTERPRISE. | 4.92 | 4.92 | 100 | 1
10 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Rupmari Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08074 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000150/2022-2023 | 44/BD | 04/01/2023 | 04/01/2023 | Resource Division | 61.6 | 0 | 0 | 0
Total | [13 empty] | 190.02 | 126.63 | 66.64