## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- | SM/08076 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gopalpur Chandigarh Mouza (Part) within Humaipur Water Supply Scheme at Barasat II Block under Barasat Division, PHE Dte. Part-I Sl.No.4 | Assistant Engineer | Junior Engineer | ORD/000789/2020-2021 | 171/BSD | 18/02/2021 | 04/03/2021 | ANJALI ENTERPRISE. | 2.18 | 1.91 | 87.4 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- | SM/08076 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gopalpur Chandigarh Mouza (Part-I), and Dariala, Birpur, Banspol mouzas within Humaipur Water Supply Scheme at Barasat II Block under Barasat Division, PHE Dte. Part-A(Phase-II). | Assistant Engineer | Junior Engineer | ORD/001121/2021-2022 | 182/BD | 20/01/2022 | 06/03/2022 | MONDAL ENTERPRISE. (BARASAT) | 88.28 | 86.9 | 98.44 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- | SM/08076 | Retrofitting | Restoration works |  |  | BILL/00744/2024-2025 | BP-2024-25-240 | 06/09/2024 | 06/09/2024 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 2.8 | 0 | 0 | 0
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gopalpur Chandigarh Mouza (Part), Dariala, Birpur and Banspol mouzas within Humaipur Piped Water Supply Scheme at Barasat- | SM/08076 | Retrofitting | Restoration works |  |  | BILL/00743/2024-2025 | BP-2024-25-240 | 06/09/2024 | 06/09/2024 | EXECUTIVE ENGINEER-II, P.W.D,BARASAT DIVN | 16.77 | 0 | 0 | 0
Total | [13 empty] | 110.04 | 88.81 | 80.71