## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08256 | Retrofitting | Acceptance cum Work Order for Providing Functional Household Tap Connection (FHTC) in different mouza including laying of UPVC/PVC pipe line and necessary fittings within Gabberia Water Supply Scheme at Sandeshkhali-II Block under Hsnabad Sub-Division, PHE Dte.(Phase-I) | Assistant Engineer | Junior Engineer | ORD/001851/2020-2021 | 435/BD. | 22/02/2021 | 24/03/2021 | DEBAPRASAD MONDAL. | 77.8 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08256 | Retrofitting | Acceptance cum work order for Route Survey, Design Drawing & DPR Preparation for Durgapur Baylani Zone I Water Supply Scheme under Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000961/2021-2022 | 2158/HSD | 28/12/2021 | 18/01/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.18 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Gabberia Piped Water Supply Scheme, Sandeshkhali-II Block (Phase-I) | SM/08256 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 1819/BD | 19/06/2023 | 19/06/2023 | Resource Division | 21.78 | 0 | 0 | 0
Total | [13 empty] | 103.75 | 0 | 0