## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08257 | Retrofitting | Acceptance cum work Order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/001070/2021-2022 | 94/BD | 17/01/2022 | 03/03/2022 | MONDAL & CO. (BASIRHAT). | 80.01 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08257 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001178/2021-2022 | 251/HSD | 07/02/2022 | 17/02/2022 | MONDAL & CO. (BASIRHAT). | 4.62 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08257 | Retrofitting | Acceptance cum work order for Additional Laying of 75 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001181/2021-2022 | 254/HSD | 07/02/2022 | 17/02/2022 | MONDAL & CO. (BASIRHAT). | 4.54 | 0 | 0 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08257 | Retrofitting | Acceptance cum work order for Additional Laying of 50 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001182/2021-2022 | 255/HSD | 07/02/2022 | 17/02/2022 | MONDAL & CO. (BASIRHAT). | 4.54 | 0 | 0 | 1
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08257 | Retrofitting | Acceptance cum work order for Additional Laying of 63 mm dia. UPVC pipe line for Providing FHTC in connection with JJM and Jal Swapna at diff. places in Parghumti Mouza within Kalitala W/S scheme, Hingalganj block under Hasnabad Sub-Division within Barasat Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001720/2021-2022 | 257/HSD | 07/02/2022 | 17/02/2022 | MONDAL & CO. (BASIRHAT). | 4.52 | 0 | 0 | 1
6 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kalitala Piped Water Supply Scheme, Hingalganj Block (Phase-I) | SM/08257 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places due to laying of new UPVC pipe line within Kalitala w/s scheme, Hingalganj block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001179/2021-2022 | 252/HSD | 07/02/2022 | 14/02/2022 | MONDAL & CO. (BASIRHAT). | 2.06 | 0 | 0 | 1
Total | [13 empty] | 100.31 | 0 | 0