## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08258 | Retrofitting | Acceptance cum work order for Protection of UPVC rising main by UC bullah pile at Joygram Fisheries for Rejuvenation of Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000585/2021-2022 | 1851/HSD | 17/11/2021 | 02/12/2021 | ABDUL ALIM MONDAL. | 3.36 | 3.34 | 99.36 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08258 | Retrofitting | Acceptance cum work order for Supply of sluice valve i/c Construction of Sluice valve chamber and other allied works at different location within Kumarjole w/s scheme, Minakhan Block under Hasnabad Sub- Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000926/2021-2022 | 1995/HSD.. | 02/12/2021 | 17/12/2021 | ABDUL ALIM MONDAL. | 3.5 | 3.5 | 100 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08258 | Retrofitting | Acceptance cum work order for Protection Emergent restoration of concrete road for damage portion at different places for providing FHTC within Kumarjole w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000696/2021-2022 | 1984/HSD | 02/12/2021 | 09/12/2021 | ABDUL ALIM MONDAL. | 2.46 | 2.46 | 100 | 1
4 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08258 | Retrofitting | Acceptance cum work order for Construction of protection wall for protection of UPVC pipe line at N/H of Majed Gazi at Uttar Kumarjole Purba para for Retrofitting of Kumarjole W/S Scheme, Minakhan Block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer |  | ORD/002303/2020-2021 | 2055/BD | 18/09/2020 | 28/09/2020 | RUDRA DAS. | 3.27 | 3.27 | 99.97 | 0
5 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Kumarjole Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08258 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 1817/BD | 19/06/2023 | 19/06/2023 | Resource Division | 52.67 | 0 | 0 | 0
Total | [13 empty] | 65.26 | 12.57 | 19.26