## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08259 | Retrofitting | Acceptance cum work order for Providing Functional Household Tap Connection (FHTC) in diff. mouza including laying of UPVC/PVC pipe & supply of necessary fittings within Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division, PHE Dte. (Phase-I) | Assistant Engineer | Junior Engineer | ORD/000340/2021-2022 | 1672/BD | 08/09/2021 | 23/10/2021 | MONDAL & CO. (BASIRHAT). | 84.12 | 0 | 0 | 1
2 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08259 | Retrofitting | Acceptance cum work order for Emergent restoration of concrete road for damage portion at different places for providing FHTC in Noorpur/Bokchara mouza within Noorpur w/s scheme, Minakhan block under Hasnabad Sub-Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000701/2021-2022 | 1989/HSD | 02/12/2021 | 09/12/2021 | MONDAL & CO. (BASIRHAT). | 1.63 | 0 | 0 | 1
3 | NORTH 24 PARGANAS |  | Barasat Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jivan Mission (JJM and Jal Swapna) under command area of Noorpur Piped Water Supply Scheme, Minakhan Block (Phase-I) | SM/08259 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 1809/BD | 19/06/2023 | 19/06/2023 | Resource Division | 14.78 | 0 | 0 | 0
Total | [13 empty] | 100.54 | 0 | 0